## Sheet1
Date | Block | Floor | Machinery Name | Estimated Machinery Hours
2025-01-02 | A | 10 | Material Hoist | 6
2025-01-02 | A | 10 | Concrete Pump | 5
2025-01-02 | A | 10 | Needle Vibrators | 5
2025-01-02 | A | All Floors | Tower Crane | 8
2025-01-02 | B | 6 | Material Hoist | 6
2025-01-02 | B | 6 | Concrete Pump | 5
2025-01-02 | B | 6 | Needle Vibrators | 5
2025-01-02 | B | All Floors | Tower Crane | 8
2025-01-04 | A | 10 | Material Hoist | 6
2025-01-04 | A | 10 | Concrete Pump | 5
2025-01-04 | A | 10 | Needle Vibrators | 5
2025-01-04 | A | All Floors | Tower Crane | 8
2025-01-04 | B | 6 | Material Hoist | 6
2025-01-04 | B | 6 | Concrete Pump | 5
2025-01-04 | B | 6 | Needle Vibrators | 5
2025-01-04 | B | All Floors | Tower Crane | 8
2025-01-05 | A | 10 | Material Hoist | 6
2025-01-05 | A | 10 | Concrete Pump | 5
2025-01-05 | A | 10 | Needle Vibrators | 5
2025-01-05 | A | All Floors | Tower Crane | 8
2025-01-05 | B | 6 | Material Hoist | 6
2025-01-05 | B | 6 | Concrete Pump | 5
2025-01-05 | B | 6 | Needle Vibrators | 5
2025-01-05 | B | All Floors | Tower Crane | 8
2025-01-06 | A | 10 | Material Hoist | 6
2025-01-06 | A | 10 | Concrete Pump | 5
2025-01-06 | A | 10 | Needle Vibrators | 5
2025-01-06 | A | All Floors | Tower Crane | 8
2025-01-06 | B | 6 | Material Hoist | 6
2025-01-06 | B | 6 | Concrete Pump | 5
2025-01-06 | B | 6 | Needle Vibrators | 5
2025-01-06 | B | All Floors | Tower Crane | 8
2025-01-07 | A | 10 | Material Hoist | 6
2025-01-07 | A | 10 | Concrete Pump | 5
2025-01-07 | A | 10 | Needle Vibrators | 5
2025-01-07 | A | All Floors | Tower Crane | 8
2025-01-07 | B | 6 | Material Hoist | 6
2025-01-07 | B | 6 | Concrete Pump | 5
2025-01-07 | B | 6 | Needle Vibrators | 5
2025-01-07 | B | All Floors | Tower Crane | 8
2025-01-08 | A | 10 | Material Hoist | 6
2025-01-08 | A | 10 | Concrete Pump | 5
2025-01-08 | A | 10 | Needle Vibrators | 5
2025-01-08 | A | All Floors | Tower Crane | 8
2025-01-08 | B | 6 | Material Hoist | 6
2025-01-08 | B | 6 | Concrete Pump | 5
2025-01-08 | B | 6 | Needle Vibrators | 5
2025-01-08 | B | All Floors | Tower Crane | 8
2025-01-09 | A | 11 | Material Hoist | 6
2025-01-09 | A | 11 | Concrete Pump | 5
2025-01-09 | A | 11 | Needle Vibrators | 5
2025-01-09 | A | All Floors | Tower Crane | 8
2025-01-09 | B | 6 | Material Hoist | 6
2025-01-09 | B | 6 | Concrete Pump | 5
2025-01-09 | B | 6 | Needle Vibrators | 5
2025-01-09 | B | All Floors | Tower Crane | 8
2025-01-11 | A | 11 | Material Hoist | 6
2025-01-11 | A | 11 | Concrete Pump | 5
2025-01-11 | A | 11 | Needle Vibrators | 5
2025-01-11 | A | All Floors | Tower Crane | 8
2025-01-11 | B | 6 | Material Hoist | 6
2025-01-11 | B | 6 | Concrete Pump | 5
2025-01-11 | B | 6 | Needle Vibrators | 5
2025-01-11 | B | All Floors | Tower Crane | 8
2025-01-12 | A | 11 | Material Hoist | 6
2025-01-12 | A | 11 | Concrete Pump | 5
2025-01-12 | A | 11 | Needle Vibrators | 5
2025-01-12 | A | All Floors | Tower Crane | 8
2025-01-12 | B | 6 | Material Hoist | 6
2025-01-12 | B | 6 | Concrete Pump | 5
2025-01-12 | B | 6 | Needle Vibrators | 5
2025-01-12 | B | All Floors | Tower Crane | 8
2025-01-13 | A | 11 | Material Hoist | 6
2025-01-13 | A | 11 | Concrete Pump | 5
2025-01-13 | A | 11 | Needle Vibrators | 5
2025-01-13 | A | All Floors | Tower Crane | 8
2025-01-13 | B | 6 | Material Hoist | 6
2025-01-13 | B | 6 | Concrete Pump | 5
2025-01-13 | B | 6 | Needle Vibrators | 5
2025-01-13 | B | All Floors | Tower Crane | 8
2025-01-14 | A | 11 | Material Hoist | 6
2025-01-14 | A | 11 | Concrete Pump | 5
2025-01-14 | A | 11 | Needle Vibrators | 5
2025-01-14 | A | All Floors | Tower Crane | 8
2025-01-14 | B | 6 | Material Hoist | 6
2025-01-14 | B | 6 | Concrete Pump | 5
2025-01-14 | B | 6 | Needle Vibrators | 5
2025-01-14 | B | All Floors | Tower Crane | 8
2025-01-15 | A | 11 | Material Hoist | 6
2025-01-15 | A | 11 | Concrete Pump | 5
2025-01-15 | A | 11 | Needle Vibrators | 5
2025-01-15 | A | All Floors | Tower Crane | 8
2025-01-15 | B | 6 | Material Hoist | 6
2025-01-15 | B | 6 | Concrete Pump | 5
2025-01-15 | B | 6 | Needle Vibrators | 5
2025-01-15 | B | All Floors | Tower Crane | 8
2025-01-16 | A | 11 | Material Hoist | 6
2025-01-16 | A | 11 | Concrete Pump | 5
2025-01-16 | A | 11 | Needle Vibrators | 5
2025-01-16 | A | All Floors | Tower Crane | 8
2025-01-16 | B | 6 | Material Hoist | 6
2025-01-16 | B | 6 | Concrete Pump | 5
2025-01-16 | B | 6 | Needle Vibrators | 5
2025-01-16 | B | All Floors | Tower Crane | 8
2025-01-18 | A | 12 | Material Hoist | 6
2025-01-18 | A | 12 | Concrete Pump | 5
2025-01-18 | A | 12 | Needle Vibrators | 5
2025-01-18 | A | All Floors | Tower Crane | 8
2025-01-18 | B | 6 | Material Hoist | 6
2025-01-18 | B | 6 | Concrete Pump | 5
2025-01-18 | B | 6 | Needle Vibrators | 5
2025-01-18 | B | All Floors | Tower Crane | 8
2025-01-19 | A | 12 | Material Hoist | 6
2025-01-19 | A | 12 | Concrete Pump | 5
2025-01-19 | A | 12 | Needle Vibrators | 5
2025-01-19 | A | All Floors | Tower Crane | 8
2025-01-19 | B | 6 | Material Hoist | 6
2025-01-19 | B | 6 | Concrete Pump | 5
2025-01-19 | B | 6 | Needle Vibrators | 5
2025-01-19 | B | All Floors | Tower Crane | 8
2025-01-20 | A | 12 | Material Hoist | 6
2025-01-20 | A | 12 | Concrete Pump | 5
2025-01-20 | A | 12 | Needle Vibrators | 5
2025-01-20 | A | All Floors | Tower Crane | 8
2025-01-20 | B | 6 | Material Hoist | 6
2025-01-20 | B | 6 | Concrete Pump | 5
2025-01-20 | B | 6 | Needle Vibrators | 5
2025-01-20 | B | All Floors | Tower Crane | 8
2025-01-21 | A | 12 | Material Hoist | 6
2025-01-21 | A | 12 | Concrete Pump | 5
2025-01-21 | A | 12 | Needle Vibrators | 5
2025-01-21 | A | All Floors | Tower Crane | 8
2025-01-21 | B | 6 | Material Hoist | 6
2025-01-21 | B | 6 | Concrete Pump | 5
2025-01-21 | B | 6 | Needle Vibrators | 5
2025-01-21 | B | All Floors | Tower Crane | 8
2025-01-22 | A | 12 | Material Hoist | 6
2025-01-22 | A | 12 | Concrete Pump | 5
2025-01-22 | A | 12 | Needle Vibrators | 5
2025-01-22 | A | All Floors | Tower Crane | 8
2025-01-22 | B | 6 | Material Hoist | 6
2025-01-22 | B | 6 | Concrete Pump | 5
2025-01-22 | B | 6 | Needle Vibrators | 5
2025-01-22 | B | All Floors | Tower Crane | 8
2025-01-23 | A | 12 | Material Hoist | 6
2025-01-23 | A | 12 | Concrete Pump | 5
2025-01-23 | A | 12 | Needle Vibrators | 5
2025-01-23 | A | All Floors | Tower Crane | 8
2025-01-23 | B | 6 | Material Hoist | 6
2025-01-23 | B | 6 | Concrete Pump | 5
2025-01-23 | B | 6 | Needle Vibrators | 5
2025-01-23 | B | All Floors | Tower Crane | 8
2025-01-25 | A | 12 | Material Hoist | 6
2025-01-25 | A | 12 | Concrete Pump | 5
2025-01-25 | A | 12 | Needle Vibrators | 5
2025-01-25 | A | All Floors | Tower Crane | 8
2025-01-25 | B | 6 | Material Hoist | 6
2025-01-25 | B | 6 | Concrete Pump | 5
2025-01-25 | B | 6 | Needle Vibrators | 5
2025-01-25 | B | All Floors | Tower Crane | 8
2025-01-26 | A | 13 | Material Hoist | 6
2025-01-26 | A | 13 | Concrete Pump | 5
2025-01-26 | A | 13 | Needle Vibrators | 5
2025-01-26 | A | All Floors | Tower Crane | 8
2025-01-26 | B | 6 | Material Hoist | 6
2025-01-26 | B | 6 | Concrete Pump | 5
2025-01-26 | B | 6 | Needle Vibrators | 5
2025-01-26 | B | All Floors | Tower Crane | 8
2025-01-27 | A | 13 | Material Hoist | 6
2025-01-27 | A | 13 | Concrete Pump | 5
2025-01-27 | A | 13 | Needle Vibrators | 5
2025-01-27 | A | All Floors | Tower Crane | 8
2025-01-27 | B | 6 | Material Hoist | 6
2025-01-27 | B | 6 | Concrete Pump | 5
2025-01-27 | B | 6 | Needle Vibrators | 5
2025-01-27 | B | All Floors | Tower Crane | 8
2025-01-28 | A | 13 | Material Hoist | 6
2025-01-28 | A | 13 | Concrete Pump | 5
2025-01-28 | A | 13 | Needle Vibrators | 5
2025-01-28 | A | All Floors | Tower Crane | 8
2025-01-28 | B | 6 | Material Hoist | 6
2025-01-28 | B | 6 | Concrete Pump | 5
2025-01-28 | B | 6 | Needle Vibrators | 5
2025-01-28 | B | All Floors | Tower Crane | 8
2025-01-29 | A | 13 | Material Hoist | 6
2025-01-29 | A | 13 | Concrete Pump | 5
2025-01-29 | A | 13 | Needle Vibrators | 5
2025-01-29 | A | All Floors | Tower Crane | 8
2025-01-29 | B | 6 | Material Hoist | 6
2025-01-29 | B | 6 | Concrete Pump | 5
2025-01-29 | B | 6 | Needle Vibrators | 5
2025-01-29 | B | All Floors | Tower Crane | 8
2025-01-30 | A | 13 | Material Hoist | 6
2025-01-30 | A | 13 | Concrete Pump | 5
2025-01-30 | A | 13 | Needle Vibrators | 5
2025-01-30 | A | All Floors | Tower Crane | 8
2025-01-30 | B | 6 | Material Hoist | 6
2025-01-30 | B | 6 | Concrete Pump | 5
2025-01-30 | B | 6 | Needle Vibrators | 5
2025-01-30 | B | All Floors | Tower Crane | 8
2025-02-01 | A | 13 | Material Hoist | 6
2025-02-01 | A | 13 | Concrete Pump | 5
2025-02-01 | A | 13 | Needle Vibrators | 5
2025-02-01 | A | All Floors | Tower Crane | 8
2025-02-01 | B | 6 | Material Hoist | 6
2025-02-01 | B | 6 | Concrete Pump | 5
2025-02-01 | B | 6 | Needle Vibrators | 5
2025-02-01 | B | All Floors | Tower Crane | 8
2025-02-02 | A | 13 | Material Hoist | 6
2025-02-02 | A | 13 | Concrete Pump | 5
2025-02-02 | A | 13 | Needle Vibrators | 5
2025-02-02 | A | All Floors | Tower Crane | 8
2025-02-02 | B | 6 | Material Hoist | 6
2025-02-02 | B | 6 | Concrete Pump | 5
2025-02-02 | B | 6 | Needle Vibrators | 5
2025-02-02 | B | All Floors | Tower Crane | 8
2025-02-03 | A | 14 | Material Hoist | 6
2025-02-03 | A | 14 | Concrete Pump | 5
2025-02-03 | A | 14 | Needle Vibrators | 5
2025-02-03 | A | All Floors | Tower Crane | 8
2025-02-03 | B | 6 | Material Hoist | 6
2025-02-03 | B | 6 | Concrete Pump | 5
2025-02-03 | B | 6 | Needle Vibrators | 5
2025-02-03 | B | All Floors | Tower Crane | 8
2025-02-04 | A | 14 | Material Hoist | 6
2025-02-04 | A | 14 | Concrete Pump | 5
2025-02-04 | A | 14 | Needle Vibrators | 5
2025-02-04 | A | All Floors | Tower Crane | 8
2025-02-04 | B | 6 | Material Hoist | 6
2025-02-04 | B | 6 | Concrete Pump | 5
2025-02-04 | B | 6 | Needle Vibrators | 5
2025-02-04 | B | All Floors | Tower Crane | 8
2025-02-05 | A | 14 | Material Hoist | 6
2025-02-05 | A | 14 | Concrete Pump | 5
2025-02-05 | A | 14 | Needle Vibrators | 5
2025-02-05 | A | All Floors | Tower Crane | 8
2025-02-05 | B | 6 | Material Hoist | 6
2025-02-05 | B | 6 | Concrete Pump | 5
2025-02-05 | B | 6 | Needle Vibrators | 5
2025-02-05 | B | All Floors | Tower Crane | 8
2025-02-06 | A | 14 | Material Hoist | 6
2025-02-06 | A | 14 | Concrete Pump | 5
2025-02-06 | A | 14 | Needle Vibrators | 5
2025-02-06 | A | All Floors | Tower Crane | 8
2025-02-06 | B | 6 | Material Hoist | 6
2025-02-06 | B | 6 | Concrete Pump | 5
2025-02-06 | B | 6 | Needle Vibrators | 5
2025-02-06 | B | All Floors | Tower Crane | 8
2025-02-08 | A | 14 | Material Hoist | 6
2025-02-08 | A | 14 | Concrete Pump | 5
2025-02-08 | A | 14 | Needle Vibrators | 5
2025-02-08 | A | All Floors | Tower Crane | 8
2025-02-08 | B | 6 | Material Hoist | 6
2025-02-08 | B | 6 | Concrete Pump | 5
2025-02-08 | B | 6 | Needle Vibrators | 5
2025-02-08 | B | All Floors | Tower Crane | 8
2025-02-09 | A | 14 | Material Hoist | 6
2025-02-09 | A | 14 | Concrete Pump | 5
2025-02-09 | A | 14 | Needle Vibrators | 5
2025-02-09 | A | All Floors | Tower Crane | 8
2025-02-09 | B | 6 | Material Hoist | 6
2025-02-09 | B | 6 | Concrete Pump | 5
2025-02-09 | B | 6 | Needle Vibrators | 5
2025-02-09 | B | All Floors | Tower Crane | 8
2025-02-10 | A | 14 | Material Hoist | 6
2025-02-10 | A | 14 | Concrete Pump | 5
2025-02-10 | A | 14 | Needle Vibrators | 5
2025-02-10 | A | All Floors | Tower Crane | 8
2025-02-10 | B | 6 | Material Hoist | 6
2025-02-10 | B | 6 | Concrete Pump | 5
2025-02-10 | B | 6 | Needle Vibrators | 5
2025-02-10 | B | All Floors | Tower Crane | 8
2025-02-11 | A | 15 | Material Hoist | 6
2025-02-11 | A | 15 | Concrete Pump | 5
2025-02-11 | A | 15 | Needle Vibrators | 5
2025-02-11 | A | All Floors | Tower Crane | 8
2025-02-11 | B | 6 | Material Hoist | 6
2025-02-11 | B | 6 | Concrete Pump | 5
2025-02-11 | B | 6 | Needle Vibrators | 5
2025-02-11 | B | All Floors | Tower Crane | 8
2025-02-12 | A | 15 | Material Hoist | 6
2025-02-12 | A | 15 | Concrete Pump | 5
2025-02-12 | A | 15 | Needle Vibrators | 5
2025-02-12 | A | All Floors | Tower Crane | 8
2025-02-12 | B | 6 | Material Hoist | 6
2025-02-12 | B | 6 | Concrete Pump | 5
2025-02-12 | B | 6 | Needle Vibrators | 5
2025-02-12 | B | All Floors | Tower Crane | 8
2025-02-13 | A | 15 | Material Hoist | 6
2025-02-13 | A | 15 | Concrete Pump | 5
2025-02-13 | A | 15 | Needle Vibrators | 5
2025-02-13 | A | All Floors | Tower Crane | 8
2025-02-13 | B | 7 | Material Hoist | 6
2025-02-13 | B | 7 | Concrete Pump | 5
2025-02-13 | B | 7 | Needle Vibrators | 5
2025-02-13 | B | All Floors | Tower Crane | 8
2025-02-15 | A | 15 | Material Hoist | 6
2025-02-15 | A | 15 | Concrete Pump | 5
2025-02-15 | A | 15 | Needle Vibrators | 5
2025-02-15 | A | All Floors | Tower Crane | 8
2025-02-15 | B | 7 | Material Hoist | 6
2025-02-15 | B | 7 | Concrete Pump | 5
2025-02-15 | B | 7 | Needle Vibrators | 5
2025-02-15 | B | All Floors | Tower Crane | 8
2025-02-16 | A | 15 | Material Hoist | 6
2025-02-16 | A | 15 | Concrete Pump | 5
2025-02-16 | A | 15 | Needle Vibrators | 5
2025-02-16 | A | All Floors | Tower Crane | 8
2025-02-16 | B | 7 | Material Hoist | 6
2025-02-16 | B | 7 | Concrete Pump | 5
2025-02-16 | B | 7 | Needle Vibrators | 5
2025-02-16 | B | All Floors | Tower Crane | 8
2025-02-17 | A | 15 | Material Hoist | 6
2025-02-17 | A | 15 | Concrete Pump | 5
2025-02-17 | A | 15 | Needle Vibrators | 5
2025-02-17 | A | All Floors | Tower Crane | 8
2025-02-17 | B | 7 | Material Hoist | 6
2025-02-17 | B | 7 | Concrete Pump | 5
2025-02-17 | B | 7 | Needle Vibrators | 5
2025-02-17 | B | All Floors | Tower Crane | 8
2025-02-18 | A | 15 | Material Hoist | 6
2025-02-18 | A | 15 | Concrete Pump | 5
2025-02-18 | A | 15 | Needle Vibrators | 5
2025-02-18 | A | All Floors | Tower Crane | 8
2025-02-18 | B | 7 | Material Hoist | 6
2025-02-18 | B | 7 | Concrete Pump | 5
2025-02-18 | B | 7 | Needle Vibrators | 5
2025-02-18 | B | All Floors | Tower Crane | 8
2025-02-19 | A | 16 | Material Hoist | 6
2025-02-19 | A | 16 | Concrete Pump | 5
2025-02-19 | A | 16 | Needle Vibrators | 5
2025-02-19 | A | All Floors | Tower Crane | 8
2025-02-19 | B | 7 | Material Hoist | 6
2025-02-19 | B | 7 | Concrete Pump | 5
2025-02-19 | B | 7 | Needle Vibrators | 5
2025-02-19 | B | All Floors | Tower Crane | 8
2025-02-20 | A | 16 | Material Hoist | 6
2025-02-20 | A | 16 | Concrete Pump | 5
2025-02-20 | A | 16 | Needle Vibrators | 5
2025-02-20 | A | All Floors | Tower Crane | 8
2025-02-20 | B | 7 | Material Hoist | 6
2025-02-20 | B | 7 | Concrete Pump | 5
2025-02-20 | B | 7 | Needle Vibrators | 5
2025-02-20 | B | All Floors | Tower Crane | 8
2025-02-22 | A | 16 | Material Hoist | 6
2025-02-22 | A | 16 | Concrete Pump | 5
2025-02-22 | A | 16 | Needle Vibrators | 5
2025-02-22 | A | All Floors | Tower Crane | 8
2025-02-22 | B | 8 | Material Hoist | 6
2025-02-22 | B | 8 | Concrete Pump | 5
2025-02-22 | B | 8 | Needle Vibrators | 5
2025-02-22 | B | All Floors | Tower Crane | 8
2025-02-23 | A | 16 | Material Hoist | 6
2025-02-23 | A | 16 | Concrete Pump | 5
2025-02-23 | A | 16 | Needle Vibrators | 5
2025-02-23 | A | All Floors | Tower Crane | 8
2025-02-23 | B | 8 | Material Hoist | 6
2025-02-23 | B | 8 | Concrete Pump | 5
2025-02-23 | B | 8 | Needle Vibrators | 5
2025-02-23 | B | All Floors | Tower Crane | 8
2025-02-24 | A | 16 | Material Hoist | 6
2025-02-24 | A | 16 | Concrete Pump | 5
2025-02-24 | A | 16 | Needle Vibrators | 5
2025-02-24 | A | All Floors | Tower Crane | 8
2025-02-24 | B | 8 | Material Hoist | 6
2025-02-24 | B | 8 | Concrete Pump | 5
2025-02-24 | B | 8 | Needle Vibrators | 5
2025-02-24 | B | All Floors | Tower Crane | 8
2025-02-25 | A | 16 | Material Hoist | 6
2025-02-25 | A | 16 | Concrete Pump | 5
2025-02-25 | A | 16 | Needle Vibrators | 5
2025-02-25 | A | All Floors | Tower Crane | 8
2025-02-25 | B | 8 | Material Hoist | 6
2025-02-25 | B | 8 | Concrete Pump | 5
2025-02-25 | B | 8 | Needle Vibrators | 5
2025-02-25 | B | All Floors | Tower Crane | 8
2025-02-26 | A | 16 | Material Hoist | 6
2025-02-26 | A | 16 | Concrete Pump | 5
2025-02-26 | A | 16 | Needle Vibrators | 5
2025-02-26 | A | All Floors | Tower Crane | 8
2025-02-26 | B | 8 | Material Hoist | 6
2025-02-26 | B | 8 | Concrete Pump | 5
2025-02-26 | B | 8 | Needle Vibrators | 5
2025-02-26 | B | All Floors | Tower Crane | 8
2025-02-27 | A | 17 | Material Hoist | 6
2025-02-27 | A | 17 | Concrete Pump | 5
2025-02-27 | A | 17 | Needle Vibrators | 5
2025-02-27 | A | All Floors | Tower Crane | 8
2025-02-27 | B | 8 | Material Hoist | 6
2025-02-27 | B | 8 | Concrete Pump | 5
2025-02-27 | B | 8 | Needle Vibrators | 5
2025-02-27 | B | All Floors | Tower Crane | 8
2025-03-01 | A | 17 | Material Hoist | 6
2025-03-01 | A | 17 | Concrete Pump | 5
2025-03-01 | A | 17 | Needle Vibrators | 5
2025-03-01 | A | All Floors | Tower Crane | 8
2025-03-01 | B | 8 | Material Hoist | 6
2025-03-01 | B | 8 | Concrete Pump | 5
2025-03-01 | B | 8 | Needle Vibrators | 5
2025-03-01 | B | All Floors | Tower Crane | 8
2025-03-02 | A | 17 | Material Hoist | 6
2025-03-02 | A | 17 | Concrete Pump | 5
2025-03-02 | A | 17 | Needle Vibrators | 5
2025-03-02 | A | All Floors | Tower Crane | 8
2025-03-02 | B | 9 | Material Hoist | 6
2025-03-02 | B | 9 | Concrete Pump | 5
2025-03-02 | B | 9 | Needle Vibrators | 5
2025-03-02 | B | All Floors | Tower Crane | 8
2025-03-03 | A | 17 | Material Hoist | 6
2025-03-03 | A | 17 | Concrete Pump | 5
2025-03-03 | A | 17 | Needle Vibrators | 5
2025-03-03 | A | All Floors | Tower Crane | 8
2025-03-03 | B | 9 | Material Hoist | 6
2025-03-03 | B | 9 | Concrete Pump | 5
2025-03-03 | B | 9 | Needle Vibrators | 5
2025-03-03 | B | All Floors | Tower Crane | 8
2025-03-04 | A | 17 | Material Hoist | 6
2025-03-04 | A | 17 | Concrete Pump | 5
2025-03-04 | A | 17 | Needle Vibrators | 5
2025-03-04 | A | All Floors | Tower Crane | 8
2025-03-04 | B | 9 | Material Hoist | 6
2025-03-04 | B | 9 | Concrete Pump | 5
2025-03-04 | B | 9 | Needle Vibrators | 5
2025-03-04 | B | All Floors | Tower Crane | 8
2025-03-05 | A | 17 | Material Hoist | 6
2025-03-05 | A | 17 | Concrete Pump | 5
2025-03-05 | A | 17 | Needle Vibrators | 5
2025-03-05 | A | All Floors | Tower Crane | 8
2025-03-05 | B | 9 | Material Hoist | 6
2025-03-05 | B | 9 | Concrete Pump | 5
2025-03-05 | B | 9 | Needle Vibrators | 5
2025-03-05 | B | All Floors | Tower Crane | 8
2025-03-06 | A | 17 | Material Hoist | 6
2025-03-06 | A | 17 | Concrete Pump | 5
2025-03-06 | A | 17 | Needle Vibrators | 5
2025-03-06 | A | All Floors | Tower Crane | 8
2025-03-06 | B | 9 | Material Hoist | 6
2025-03-06 | B | 9 | Concrete Pump | 5
2025-03-06 | B | 9 | Needle Vibrators | 5
2025-03-06 | B | All Floors | Tower Crane | 8
2025-03-08 | A | 18 | Material Hoist | 6
2025-03-08 | A | 18 | Concrete Pump | 5
2025-03-08 | A | 18 | Needle Vibrators | 5
2025-03-08 | A | All Floors | Tower Crane | 8
2025-03-08 | B | 9 | Material Hoist | 6
2025-03-08 | B | 9 | Concrete Pump | 5
2025-03-08 | B | 9 | Needle Vibrators | 5
2025-03-08 | B | All Floors | Tower Crane | 8
2025-03-09 | A | 18 | Material Hoist | 6
2025-03-09 | A | 18 | Concrete Pump | 5
2025-03-09 | A | 18 | Needle Vibrators | 5
2025-03-09 | A | All Floors | Tower Crane | 8
2025-03-09 | B | 9 | Material Hoist | 6
2025-03-09 | B | 9 | Concrete Pump | 5
2025-03-09 | B | 9 | Needle Vibrators | 5
2025-03-09 | B | All Floors | Tower Crane | 8
2025-03-10 | A | 18 | Material Hoist | 6
2025-03-10 | A | 18 | Concrete Pump | 5
2025-03-10 | A | 18 | Needle Vibrators | 5
2025-03-10 | A | All Floors | Tower Crane | 8
2025-03-10 | B | 10 | Material Hoist | 6
2025-03-10 | B | 10 | Concrete Pump | 5
2025-03-10 | B | 10 | Needle Vibrators | 5
2025-03-10 | B | All Floors | Tower Crane | 8
2025-03-11 | A | 18 | Material Hoist | 6
2025-03-11 | A | 18 | Concrete Pump | 5
2025-03-11 | A | 18 | Needle Vibrators | 5
2025-03-11 | A | All Floors | Tower Crane | 8
2025-03-11 | B | 10 | Material Hoist | 6
2025-03-11 | B | 10 | Concrete Pump | 5
2025-03-11 | B | 10 | Needle Vibrators | 5
2025-03-11 | B | All Floors | Tower Crane | 8
2025-03-12 | A | 18 | Material Hoist | 6
2025-03-12 | A | 18 | Concrete Pump | 5
2025-03-12 | A | 18 | Needle Vibrators | 5
2025-03-12 | A | All Floors | Tower Crane | 8
2025-03-12 | B | 10 | Material Hoist | 6
2025-03-12 | B | 10 | Concrete Pump | 5
2025-03-12 | B | 10 | Needle Vibrators | 5
2025-03-12 | B | All Floors | Tower Crane | 8
2025-03-13 | A | 18 | Material Hoist | 6
2025-03-13 | A | 18 | Concrete Pump | 5
2025-03-13 | A | 18 | Needle Vibrators | 5
2025-03-13 | A | All Floors | Tower Crane | 8
2025-03-13 | B | 10 | Material Hoist | 6
2025-03-13 | B | 10 | Concrete Pump | 5
2025-03-13 | B | 10 | Needle Vibrators | 5
2025-03-13 | B | All Floors | Tower Crane | 8
2025-03-15 | A | 18 | Material Hoist | 6
2025-03-15 | A | 18 | Concrete Pump | 5
2025-03-15 | A | 18 | Needle Vibrators | 5
2025-03-15 | A | All Floors | Tower Crane | 8
2025-03-15 | B | 10 | Material Hoist | 6
2025-03-15 | B | 10 | Concrete Pump | 5
2025-03-15 | B | 10 | Needle Vibrators | 5
2025-03-15 | B | All Floors | Tower Crane | 8
2025-03-16 | A | 19 | Material Hoist | 6
2025-03-16 | A | 19 | Concrete Pump | 5
2025-03-16 | A | 19 | Needle Vibrators | 5
2025-03-16 | A | All Floors | Tower Crane | 8
2025-03-16 | B | 10 | Material Hoist | 6
2025-03-16 | B | 10 | Concrete Pump | 5
2025-03-16 | B | 10 | Needle Vibrators | 5
2025-03-16 | B | All Floors | Tower Crane | 8
2025-03-17 | A | 19 | Material Hoist | 6
2025-03-17 | A | 19 | Concrete Pump | 5
2025-03-17 | A | 19 | Needle Vibrators | 5
2025-03-17 | A | All Floors | Tower Crane | 8
2025-03-17 | B | 10 | Material Hoist | 6
2025-03-17 | B | 10 | Concrete Pump | 5
2025-03-17 | B | 10 | Needle Vibrators | 5
2025-03-17 | B | All Floors | Tower Crane | 8
2025-03-18 | A | 19 | Material Hoist | 6
2025-03-18 | A | 19 | Concrete Pump | 5
2025-03-18 | A | 19 | Needle Vibrators | 5
2025-03-18 | A | All Floors | Tower Crane | 8
2025-03-18 | B | 11 | Material Hoist | 6
2025-03-18 | B | 11 | Concrete Pump | 5
2025-03-18 | B | 11 | Needle Vibrators | 5
2025-03-18 | B | All Floors | Tower Crane | 8
2025-03-19 | A | 19 | Material Hoist | 6
2025-03-19 | A | 19 | Concrete Pump | 5
2025-03-19 | A | 19 | Needle Vibrators | 5
2025-03-19 | A | All Floors | Tower Crane | 8
2025-03-19 | B | 11 | Material Hoist | 6
2025-03-19 | B | 11 | Concrete Pump | 5
2025-03-19 | B | 11 | Needle Vibrators | 5
2025-03-19 | B | All Floors | Tower Crane | 8
2025-03-20 | A | 19 | Material Hoist | 6
2025-03-20 | A | 19 | Concrete Pump | 5
2025-03-20 | A | 19 | Needle Vibrators | 5
2025-03-20 | A | All Floors | Tower Crane | 8
2025-03-20 | B | 11 | Material Hoist | 6
2025-03-20 | B | 11 | Concrete Pump | 5
2025-03-20 | B | 11 | Needle Vibrators | 5
2025-03-20 | B | All Floors | Tower Crane | 8
2025-03-22 | A | 19 | Material Hoist | 6
2025-03-22 | A | 19 | Concrete Pump | 5
2025-03-22 | A | 19 | Needle Vibrators | 5
2025-03-22 | A | All Floors | Tower Crane | 8
2025-03-22 | B | 11 | Material Hoist | 6
2025-03-22 | B | 11 | Concrete Pump | 5
2025-03-22 | B | 11 | Needle Vibrators | 5
2025-03-22 | B | All Floors | Tower Crane | 8
2025-03-23 | A | 19 | Material Hoist | 6
2025-03-23 | A | 19 | Concrete Pump | 5
2025-03-23 | A | 19 | Needle Vibrators | 5
2025-03-23 | A | All Floors | Tower Crane | 8
2025-03-23 | B | 11 | Material Hoist | 6
2025-03-23 | B | 11 | Concrete Pump | 5
2025-03-23 | B | 11 | Needle Vibrators | 5
2025-03-23 | B | All Floors | Tower Crane | 8
2025-03-24 | A | 20 | Material Hoist | 6
2025-03-24 | A | 20 | Concrete Pump | 5
2025-03-24 | A | 20 | Needle Vibrators | 5
2025-03-24 | A | All Floors | Tower Crane | 8
2025-03-24 | B | 11 | Material Hoist | 6
2025-03-24 | B | 11 | Concrete Pump | 5
2025-03-24 | B | 11 | Needle Vibrators | 5
2025-03-24 | B | All Floors | Tower Crane | 8
2025-03-25 | A | 20 | Material Hoist | 6
2025-03-25 | A | 20 | Concrete Pump | 5
2025-03-25 | A | 20 | Needle Vibrators | 5
2025-03-25 | A | All Floors | Tower Crane | 8
2025-03-25 | B | 11 | Material Hoist | 6
2025-03-25 | B | 11 | Concrete Pump | 5
2025-03-25 | B | 11 | Needle Vibrators | 5
2025-03-25 | B | All Floors | Tower Crane | 8
2025-03-26 | A | 20 | Material Hoist | 6
2025-03-26 | A | 20 | Concrete Pump | 5
2025-03-26 | A | 20 | Needle Vibrators | 5
2025-03-26 | A | All Floors | Tower Crane | 8
2025-03-26 | B | 12 | Material Hoist | 6
2025-03-26 | B | 12 | Concrete Pump | 5
2025-03-26 | B | 12 | Needle Vibrators | 5
2025-03-26 | B | All Floors | Tower Crane | 8
2025-03-27 | A | 20 | Material Hoist | 6
2025-03-27 | A | 20 | Concrete Pump | 5
2025-03-27 | A | 20 | Needle Vibrators | 5
2025-03-27 | A | All Floors | Tower Crane | 8
2025-03-27 | B | 12 | Material Hoist | 6
2025-03-27 | B | 12 | Concrete Pump | 5
2025-03-27 | B | 12 | Needle Vibrators | 5
2025-03-27 | B | All Floors | Tower Crane | 8
2025-03-29 | A | 20 | Material Hoist | 6
2025-03-29 | A | 20 | Concrete Pump | 5
2025-03-29 | A | 20 | Needle Vibrators | 5
2025-03-29 | A | All Floors | Tower Crane | 8
2025-03-29 | B | 12 | Material Hoist | 6
2025-03-29 | B | 12 | Concrete Pump | 5
2025-03-29 | B | 12 | Needle Vibrators | 5
2025-03-29 | B | All Floors | Tower Crane | 8
2025-03-30 | A | 20 | Material Hoist | 6
2025-03-30 | A | 20 | Concrete Pump | 5
2025-03-30 | A | 20 | Needle Vibrators | 5
2025-03-30 | A | All Floors | Tower Crane | 8
2025-03-30 | B | 12 | Material Hoist | 6
2025-03-30 | B | 12 | Concrete Pump | 5
2025-03-30 | B | 12 | Needle Vibrators | 5
2025-03-30 | B | All Floors | Tower Crane | 8
2025-04-01 | A | 20 | Material Hoist | 6
2025-04-01 | A | 20 | Concrete Pump | 5
2025-04-01 | A | 20 | Needle Vibrators | 5
2025-04-01 | A | All Floors | Tower Crane | 8
2025-04-01 | B | 12 | Material Hoist | 6
2025-04-01 | B | 12 | Concrete Pump | 5
2025-04-01 | B | 12 | Needle Vibrators | 5
2025-04-01 | B | All Floors | Tower Crane | 8