## IPC_Apr_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 849792.76 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 52085.9 | 52085.9 |  | 0 | 13.18% | 6862.37 | 13.18% | 6862.37 | 0 | 0.13 | 0.13
1.2 | Site Fencing and Hoarding | LS | 1 | 45685.08 | 45685.08 |  | 0 | 25.63% | 11709.25 | 25.63% | 11709.25 | 0 | 0.26 | 0.26
1.3 | Temporary Facilities Setup | LS | 1 | 428111.8 | 428111.8 |  | 0 | 4.87% | 20829.22 | 4.87% | 20829.22 | 0 | 0.05 | 0.05
1.4 | Soil Testing and Survey | LS | 1 | 210377.3 | 210377.3 |  | 0 | 33.74% | 70987.31 | 33.74% | 70987.31 | 0 | 0.34 | 0.34
1.5 | Excavation | LS | 1 | 48545.32 | 48545.32 |  | 0 | 28.11% | 13645.11 | 28.11% | 13645.11 | 0 | 0.28 | 0.28
1.6 | Dewatering | LS | 1 | 45740.6 | 45740.6 |  | 0 | 14.38% | 6575.63 | 14.38% | 6575.63 | 0 | 0.14 | 0.14
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4278344.58 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 328.19 | 1640950 |  | 0 | 9.54% | 156540.85 | 9.54% | 156540.85 | 0 | 476.98 | 476.98
2.2 | Raft Foundation | m3 | 3500 | 261.54 | 915390 |  | 0 | 34.33% | 314295.94 | 34.33% | 314295.94 | 0 | 1201.71 | 1201.71
2.3 | Basement Slab and Walls | m3 | 4000 | 355.05 | 1420200 |  | 0 | 15.67% | 222488.45 | 15.67% | 222488.45 | 0 | 626.64 | 626.64
3 | Superstructure | LS | LS | - | 3536669.8 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 413.95 | 198696 |  | 0 | 25.33% | 50320.96 | 25.33% | 50320.96 | 0 | 121.56 | 121.56
3.2 | Vertical Elements | m3 | 3600 | 214.46 | 772056 |  | 0 | 23.92% | 184693.67 | 23.92% | 184693.67 | 0 | 861.2 | 861.2
3.3 | Floor Slabs | m3 | 6000 | 300.78 | 1804680 |  | 0 | 10.01% | 180666.92 | 10.01% | 180666.92 | 0 | 600.66 | 600.66
3.4 | Staircase Construction | m3 | 1000 | 280.92 | 280920 |  | 0 | 8.17% | 22964.53 | 8.17% | 22964.53 | 0 | 81.75 | 81.75
3.5 | Lift Core Construction | m3 | 1000 | 220.47 | 220470 |  | 0 | 6.06% | 13360.73 | 6.06% | 13360.73 | 0 | 60.6 | 60.6
3.6 | Roof Slab and Parapets | m3 | 360 | 259.57 | 93445.2 |  | 0 | 30.17% | 28191.08 | 30.17% | 28191.08 | 0 | 108.61 | 108.61
4 | Masonry and Partitioning | LS | LS | - | 13892077.94 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 185.75 | 6501250 |  | 0 | 9.58% | 622771.33 | 9.58% | 622771.33 | 0 | 3352.74 | 3352.74
4.2 | Internal Blockwork | m2 | 35000 | 217.08 | 7597800 |  | 0 | 15.30% | 1162814.2 | 15.30% | 1162814.2 | 0 | 5356.62 | 5356.62
4.3 | Drywall Partitioning | m3 | 1000 | 232.51 | 232510 |  | 0 | 8.57% | 19923.91 | 8.57% | 19923.91 | 0 | 85.69 | 85.69
5 | MEP Works | LS | LS | - | 211450.94 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 45252.04 | 45252.04 |  | 0 | 13.32% | 6026.58 | 13.32% | 6026.58 | 0 | 0.13 | 0.13
5.2 | Plumbing & Drainage | LS | 1 | 49292.7 | 49292.7 |  | 0 | 14.44% | 7118.88 | 14.44% | 7118.88 | 0 | 0.14 | 0.14
5.3 | Firefighting Piping | LS | 1 | 49723.32 | 49723.32 |  | 0 | 24.97% | 12415.35 | 24.97% | 12415.35 | 0 | 0.25 | 0.25
5.4 | HVAC Ducting | No. | 40 | 547.73 | 21909.2 |  | 0 | 29.30% | 6420.4 | 29.30% | 6420.4 | 0 | 11.72 | 11.72
5.5 | Low Current Systems | LS | 1 | 47808.06 | 47808.06 |  | 0 | 13.54% | 6473.86 | 13.54% | 6473.86 | 0 | 0.14 | 0.14
6 | Finishing Works | LS | LS | - | 16182156.24 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 57.48 | 1896840 |  | 0 | 22.58% | 428221.91 | 22.58% | 428221.91 | 0 | 7449.93 | 7449.93
6.2 | Waterproofing | m2 | 5000 | 220.89 | 1104450 |  | 0 | 20.96% | 231524.31 | 20.96% | 231524.31 | 0 | 1048.14 | 1048.14
6.3 | Tiling | m2 | 15000 | 249.24 | 3738600 |  | 0 | 28.93% | 1081490.2 | 28.93% | 1081490.2 | 0 | 4339.15 | 4339.15
6.4 | Painting | m2 | 40000 | 82.75 | 3310000 |  | 0 | 11.94% | 395269.34 | 11.94% | 395269.34 | 0 | 4776.67 | 4776.67
6.5 | Ceiling Works | m2 | 18000 | 130.91 | 2356380 |  | 0 | 30.67% | 722730.45 | 30.67% | 722730.45 | 0 | 5520.82 | 5520.82
6.6 | Joinery Installation | No. | 400 | 765.2 | 306080 |  | 0 | 9.03% | 27631.71 | 9.03% | 27631.71 | 0 | 36.11 | 36.11
6.7 | Door & Window Installation | No. | 800 | 1560.51 | 1248408 |  | 0 | 10.35% | 129266.59 | 10.35% | 129266.59 | 0 | 82.84 | 82.84
6.8 | Glazing | m2 | 12000 | 76.35 | 916200 |  | 0 | 27.00% | 247396.59 | 27.00% | 247396.59 | 0 | 3240.3 | 3240.3
7 | External Works & Landscaping | LS | LS | - | 3087538.84 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 848.7 | 84870 |  | 0 | 18.86% | 16006.23 | 18.86% | 16006.23 | 0 | 18.86 | 18.86
7.2 | Roadworks and Paving | m2 | 8000 | 207.49 | 1659920 |  | 0 | 9.89% | 164120.7 | 9.89% | 164120.7 | 0 | 790.98 | 790.98
7.3 | Kerbstone and Interlock | m2 | 7000 | 108.8 | 761600 |  | 0 | 11.21% | 85400.02 | 11.21% | 85400.02 | 0 | 784.93 | 784.93
7.4 | Landscaping | m3 | 1000 | 347.29 | 347290 |  | 0 | 20.21% | 70178.16 | 20.21% | 70178.16 | 0 | 202.07 | 202.07
7.5 | Boundary Wall | m3 | 1000 | 289.77 | 289770 |  | 0 | 10.25% | 29700.45 | 10.25% | 29700.45 | 0 | 102.5 | 102.5
8 | Final Works | LS | LS | - | 581819.9 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 217018.92 | 217018.92 |  | 0 | 30.64% | 66493.61 | 30.64% | 66493.61 | 0 | 0.31 | 0.31
8.2 | Snagging & De-snagging | LS | 1 | 106817.65 | 106817.65 |  | 0 | 17.96% | 19189.72 | 17.96% | 19189.72 | 0 | 0.18 | 0.18
8.3 | Cleaning | LS | 1 | 92580.91 | 92580.91 |  | 0 | 12.47% | 11548.25 | 12.47% | 11548.25 | 0 | 0.12 | 0.12
8.4 | Handover | LS | 1 | 157621.21 | 157621.21 |  | 0 | 25.16% | 39656.54 | 25.16% | 39656.54 | 0 | 0.25 | 0.25

## IPC_May_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 808004.52 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 48060.65 | 48060.65 |  | 0 | 30.42% | 14619.51 | 30.42% | 14619.51 | 0 | 0.3 | 0.3
1.2 | Site Fencing and Hoarding | LS | 1 | 53820.25 | 53820.25 | 12.64% | 6800.26 | 24.85% | 13373.86 | 37.48% | 20174.12 | 0.13 | 0.25 | 0.38
1.3 | Temporary Facilities Setup | LS | 1 | 402985.99 | 402985.99 | 23.88% | 96251.73 | 24.40% | 98339.42 | 48.29% | 194591.15 | 0.24 | 0.24 | 0.48
1.4 | Soil Testing and Survey | LS | 1 | 187383.43 | 187383.43 | 22.77% | 42675.18 | 10.58% | 19830.86 | 33.36% | 62506.04 | 0.23 | 0.11 | 0.34
1.5 | Excavation | LS | 1 | 49430.22 | 49430.22 | 38.09% | 18829.49 | 18.82% | 9302.7 | 56.91% | 28132.19 | 0.38 | 0.19 | 0.57
1.6 | Dewatering | LS | 1 | 48227.75 | 48227.75 | 7.90% | 3807.93 | 26.47% | 12766.16 | 34.37% | 16574.09 | 0.08 | 0.26 | 0.34
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4371274.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 312.92 | 1564600 | 45.04% | 704640.27 | 6.54% | 102368.3 | 51.58% | 807008.57 | 2251.82 | 327.14 | 2578.96
2.2 | Raft Foundation | m3 | 3500 | 261.76 | 916160 | 22.77% | 208638.13 | 34.83% | 319138.12 | 57.61% | 527776.25 | 797.06 | 1219.2 | 2016.26
2.3 | Basement Slab and Walls | m3 | 4000 | 361.53 | 1446120 | 8.93% | 129198.11 | 20.40% | 294969.69 | 29.33% | 424167.8 | 357.36 | 815.89 | 1173.25
3 | Superstructure | LS | LS | - | 3171601.29 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 364.6 | 175008 | 46.62% | 81588.48 | 9.60% | 16800.43 | 56.22% | 98388.91 | 223.78 | 46.08 | 269.86
3.2 | Vertical Elements | m3 | 3600 | 201.81 | 726516 | 23.67% | 171980.78 | 13.65% | 99198.58 | 37.33% | 271179.36 | 852.19 | 491.54 | 1343.73
3.3 | Floor Slabs | m3 | 6000 | 257.35 | 1544100 | 44.89% | 693201.05 | 13.12% | 202528.73 | 58.01% | 895729.78 | 2693.61 | 786.98 | 3480.59
3.4 | Staircase Construction | m3 | 1000 | 267.21 | 267210 | 38.46% | 102767.75 | 17.08% | 45644.46 | 55.54% | 148412.21 | 384.6 | 170.82 | 555.42
3.5 | Lift Core Construction | m3 | 1000 | 207.89 | 207890 | 25.77% | 53573.89 | 17.64% | 36674.09 | 43.41% | 90247.98 | 257.7 | 176.41 | 434.11
3.6 | Roof Slab and Parapets | m3 | 360 | 242.12 | 87163.2 | 37.09% | 32326.11 | 16.37% | 14265.14 | 53.45% | 46591.25 | 133.51 | 58.92 | 192.43
4 | Masonry and Partitioning | LS | LS | - | 14750711.07 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 165.53 | 5793550 |  | 0 | 31.56% | 1828666.58 | 31.56% | 1828666.58 | 0 | 11047.34 | 11047.34
4.2 | Internal Blockwork | m2 | 35000 | 251.38 | 8798300 | 32.85% | 2889958.92 | 17.38% | 1529533.76 | 50.23% | 4419492.68 | 11496.38 | 6084.55 | 17580.93
4.3 | Drywall Partitioning | m3 | 1000 | 259.1 | 259100 | 7.97% | 20662.27 | 28.36% | 73482.29 | 36.34% | 94144.56 | 79.75 | 283.61 | 363.36
5 | MEP Works | LS | LS | - | 212989.85 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 51699.09 | 51699.09 | 35.46% | 18334.45 | 22.07% | 11409.01 | 57.53% | 29743.46 | 0.35 | 0.22 | 0.57
5.2 | Plumbing & Drainage | LS | 1 | 52641.81 | 52641.81 | 42.00% | 22111.92 | 7.28% | 3833.72 | 49.29% | 25945.64 | 0.42 | 0.07 | 0.49
5.3 | Firefighting Piping | LS | 1 | 46151.83 | 46151.83 | 29.19% | 13470.86 | 23.56% | 10872.59 | 52.75% | 24343.45 | 0.29 | 0.24 | 0.53
5.4 | HVAC Ducting | No. | 40 | 619.49 | 24779.6 | 36.32% | 9000.52 | 6.78% | 1680.26 | 43.10% | 10680.78 | 14.53 | 2.71 | 17.24
5.5 | Low Current Systems | LS | 1 | 53373.98 | 53373.98 | 15.26% | 8143.22 | 27.36% | 14604.59 | 42.62% | 22747.81 | 0.15 | 0.27 | 0.42
6 | Finishing Works | LS | LS | - | 13518989.35 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 56.48 | 1863840 | 13.98% | 260654.17 | 25.69% | 478757.98 | 39.67% | 739412.15 | 4614.98 | 8476.59 | 13091.57
6.2 | Waterproofing | m2 | 5000 | 245.71 | 1228550 | 10.28% | 126334.38 | 33.24% | 408371.54 | 43.52% | 534705.92 | 514.16 | 1662.01 | 2176.17
6.3 | Tiling | m2 | 15000 | 253.96 | 3809400 | 25.21% | 960220.24 | 14.48% | 551512.26 | 39.68% | 1511732.5 | 3780.99 | 2171.65 | 5952.64
6.4 | Painting | m2 | 40000 | 87.3 | 3492000 | 26.96% | 941331.48 | 31.30% | 1093090.5 | 58.26% | 2034421.98 | 10782.72 | 12521.08 | 23303.8
6.5 | Ceiling Works | m2 | 18000 | 140.22 | 2523960 | 5.66% | 142801.95 | 30.14% | 760801.9 | 35.80% | 903603.85 | 1018.41 | 5425.77 | 6444.18
6.6 | Joinery Installation | No. | 400 | 787.6 | 315040 | 32.22% | 101491.1 | 23.08% | 72711.18 | 55.30% | 174202.28 | 128.86 | 92.32 | 221.18
6.7 | Door & Window Installation | No. | 800 | 1440.36 | 1152288 | 16.67% | 192057.93 | 12.43% | 143183.55 | 29.09% | 335241.48 | 133.34 | 99.41 | 232.75
6.8 | Glazing | m2 | 12000 | 86.77 | 1041240 | 8.49% | 88384.96 | 28.48% | 296519.96 | 36.97% | 384904.92 | 1018.61 | 3417.31 | 4435.92
7 | External Works & Landscaping | LS | LS | - | 3091758.42 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 823.42 | 82342 | 21.41% | 17627.59 | 25.61% | 21084.57 | 47.01% | 38712.16 | 21.41 | 25.61 | 47.02
7.2 | Roadworks and Paving | m2 | 8000 | 195.49 | 1563920 | 10.62% | 166032.87 | 18.60% | 290866.73 | 29.22% | 456899.6 | 849.32 | 1487.89 | 2337.21
7.3 | Kerbstone and Interlock | m2 | 7000 | 111 | 777000 | 32.15% | 249773.42 | 19.64% | 152594.18 | 51.78% | 402367.6 | 2250.21 | 1374.72 | 3624.93
7.4 | Landscaping | m3 | 1000 | 410.4 | 410400 | 29.66% | 121720.25 | 21.01% | 86227.69 | 50.67% | 207947.94 | 296.59 | 210.11 | 506.7
7.5 | Boundary Wall | m3 | 1000 | 284.48 | 284480 | 24.45% | 69557.67 | 10.68% | 30390 | 35.13% | 99947.67 | 244.51 | 106.83 | 351.34
8 | Final Works | LS | LS | - | 496284.83 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 213143.89 | 213143.89 | 18.07% | 38517.91 | 12.28% | 26169.13 | 30.35% | 64687.04 | 0.18 | 0.12 | 0.3
8.2 | Snagging & De-snagging | LS | 1 | 109274.01 | 109274.01 | 32.40% | 35409.27 | 13.72% | 14988.9 | 46.12% | 50398.17 | 0.32 | 0.14 | 0.46
8.3 | Cleaning | LS | 1 | 106832.64 | 106832.64 | 22.77% | 24325.5 | 24.01% | 25651.83 | 46.78% | 49977.33 | 0.23 | 0.24 | 0.47
8.4 | Handover | LS | 1 | 156043.4 | 156043.4 | 10.57% | 16493.02 | 17.84% | 27841.52 | 28.41% | 44334.54 | 0.11 | 0.18 | 0.29

## IPC_Jun_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 785811.7 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50329.14 | 50329.14 | 85.26% | 42909.51 | 14.74% | 7419.63 | 100.00% | 50329.14 | 0.85 | 0.15 | 1
1.2 | Site Fencing and Hoarding | LS | 1 | 50603.09 | 50603.09 | 93.33% | 47228.21 | 5.44% | 2754.84 | 98.77% | 49983.05 | 0.93 | 0.05 | 0.98
1.3 | Temporary Facilities Setup | LS | 1 | 404056.17 | 404056.17 | 87.31% | 352779.43 | 12.69% | 51276.74 | 100.00% | 404056.17 | 0.87 | 0.13 | 1
1.4 | Soil Testing and Survey | LS | 1 | 193879.31 | 193879.31 | 64.69% | 125425.42 | 23.63% | 45814.41 | 88.32% | 171239.83 | 0.65 | 0.24 | 0.89
1.5 | Excavation | LS | 1 | 54691.35 | 54691.35 | 55.33% | 30261.52 | 21.86% | 11954.45 | 77.19% | 42215.97 | 0.55 | 0.22 | 0.77
1.6 | Dewatering | LS | 1 | 48745.67 | 48745.67 | 67.25% | 32783.58 | 20.21% | 9849.92 | 87.46% | 42633.5 | 0.67 | 0.2 | 0.87
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4058080.02 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 373.5 | 1867500 | 52.80% | 986014.05 | 33.96% | 634123.91 | 86.75% | 1620137.96 | 2639.93 | 1697.79 | 4337.72
2.2 | Raft Foundation | m3 | 3500 | 250.65 | 877275 | 79.58% | 698174.31 | 8.40% | 73734.59 | 87.99% | 771908.9 | 2785.46 | 294.17 | 3079.63
2.3 | Basement Slab and Walls | m3 | 4000 | 395.98 | 1583920 | 88.88% | 1407727.26 | 11.12% | 176192.74 | 100.00% | 1583920 | 3555.05 | 444.95 | 4000
3 | Superstructure | LS | LS | - | 3407768.47 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 387.29 | 185899.2 | 82.82% | 153958.24 | 10.53% | 19576.32 | 93.35% | 173534.56 | 397.53 | 50.55 | 448.08
3.2 | Vertical Elements | m3 | 3600 | 205.73 | 740628 | 86.41% | 639967.17 | 9.33% | 69104.17 | 95.74% | 709071.34 | 3110.71 | 335.9 | 3446.61
3.3 | Floor Slabs | m3 | 6000 | 285.43 | 1712580 | 69.78% | 1194988.47 | 30.22% | 517591.53 | 100.00% | 1712580 | 4186.63 | 1813.37 | 6000
3.4 | Staircase Construction | m3 | 1000 | 315.57 | 315570 | 80.72% | 254730.95 | 11.33% | 35743.56 | 92.05% | 290474.51 | 807.21 | 113.27 | 920.48
3.5 | Lift Core Construction | m3 | 1000 | 220.79 | 220790 | 67.47% | 148968.12 | 25.98% | 57363.3 | 93.45% | 206331.42 | 674.71 | 259.81 | 934.52
3.6 | Roof Slab and Parapets | m3 | 360 | 237 | 85320 | 88.73% | 75702.21 | 6.51% | 5557.08 | 95.24% | 81259.29 | 319.42 | 23.45 | 342.87
4 | Masonry and Partitioning | LS | LS | - | 13125843.02 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 154.46 | 5406100 | 67.04% | 3624244.43 | 17.97% | 971267.45 | 85.01% | 4595511.88 | 23463.97 | 6288.15 | 29752.12
4.2 | Internal Blockwork | m2 | 35000 | 216.79 | 7587650 | 92.77% | 7039276.92 | 7.23% | 548373.08 | 100.00% | 7587650 | 32470.49 | 2529.51 | 35000
4.3 | Drywall Partitioning | m3 | 1000 | 255.94 | 255940 | 75.65% | 193619.01 | 5.94% | 15212.6 | 81.59% | 208831.61 | 756.5 | 59.44 | 815.94
5 | MEP Works | LS | LS | - | 215299.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 46897.31 | 46897.31 | 81.30% | 38125.53 | 5.56% | 2607.62 | 86.86% | 40733.15 | 0.81 | 0.06 | 0.87
5.2 | Plumbing & Drainage | LS | 1 | 49801.45 | 49801.45 | 58.68% | 29223.74 | 28.78% | 14333.36 | 87.46% | 43557.1 | 0.59 | 0.29 | 0.88
5.3 | Firefighting Piping | LS | 1 | 53390.33 | 53390.33 | 50.46% | 26938.96 | 33.70% | 17991.21 | 84.15% | 44930.17 | 0.5 | 0.34 | 0.84
5.4 | HVAC Ducting | No. | 40 | 584.4 | 23376 | 59.55% | 13919.7 | 28.58% | 6680.14 | 88.12% | 20599.84 | 23.82 | 11.43 | 35.25
5.5 | Low Current Systems | LS | 1 | 48399.72 | 48399.72 | 84.40% | 40847.6 | 15.60% | 7552.12 | 100.00% | 48399.72 | 0.84 | 0.16 | 1
6 | Finishing Works | LS | LS | - | 15917611.04 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 51.79 | 1709070 | 59.12% | 1010377.9 | 34.35% | 587099.52 | 93.47% | 1597477.42 | 19509.13 | 11336.16 | 30845.29
6.2 | Waterproofing | m2 | 5000 | 233.79 | 1168950 | 65.54% | 766173.77 | 28.41% | 332142.69 | 93.96% | 1098316.46 | 3277.19 | 1420.69 | 4697.88
6.3 | Tiling | m2 | 15000 | 227.68 | 3415200 | 86.34% | 2948816.56 | 7.54% | 257389.24 | 93.88% | 3206205.8 | 12951.58 | 1130.49 | 14082.07
6.4 | Painting | m2 | 40000 | 78.54 | 3141600 | 64.29% | 2019664.9 | 12.98% | 407699.76 | 77.27% | 2427364.66 | 25715.11 | 5190.98 | 30906.09
6.5 | Ceiling Works | m2 | 18000 | 132.15 | 2378700 | 70.95% | 1687696.55 | 12.68% | 301640.43 | 83.63% | 1989336.98 | 12771.07 | 2282.56 | 15053.63
6.6 | Joinery Installation | No. | 400 | 856.4 | 342560 | 48.29% | 165412.3 | 28.82% | 98720.43 | 77.11% | 264132.73 | 193.15 | 115.27 | 308.42
6.7 | Door & Window Installation | No. | 800 | 1299.74 | 1039792 | 67.60% | 702884.05 | 10.53% | 109527.76 | 78.13% | 812411.81 | 540.79 | 84.27 | 625.06
6.8 | Glazing | m2 | 12000 | 83.09 | 997080 | 47.73% | 475935.09 | 34.36% | 342632.99 | 82.10% | 818568.08 | 5727.95 | 4123.64 | 9851.59
7 | External Works & Landscaping | LS | LS | - | 3135492.57 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 771.8 | 77180 | 53.84% | 41553.45 | 31.99% | 24691.19 | 85.83% | 66244.64 | 53.84 | 31.99 | 85.83
7.2 | Roadworks and Paving | m2 | 8000 | 198.2 | 1585600 | 58.64% | 929750.26 | 24.14% | 382742.68 | 82.78% | 1312492.94 | 4690.97 | 1931.09 | 6622.06
7.3 | Kerbstone and Interlock | m2 | 7000 | 116.9 | 818300 | 61.92% | 506674.32 | 31.07% | 254236.24 | 92.99% | 760910.56 | 4334.25 | 2174.82 | 6509.07
7.4 | Landscaping | m3 | 1000 | 384.35 | 384350 | 57.77% | 222023.52 | 31.77% | 122090.21 | 89.53% | 344113.73 | 577.66 | 317.65 | 895.31
7.5 | Boundary Wall | m3 | 1000 | 262.06 | 262060 | 54.09% | 141744.33 | 29.23% | 76603.28 | 83.32% | 218347.61 | 540.89 | 292.31 | 833.2
8 | Final Works | LS | LS | - | 501444.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 218132.73 | 218132.73 | 81.92% | 178704.09 | 5.40% | 11783.45 | 87.33% | 190487.54 | 0.82 | 0.05 | 0.87
8.2 | Snagging & De-snagging | LS | 1 | 94603.03 | 94603.03 | 78.52% | 74277.91 | 21.48% | 20325.12 | 100.00% | 94603.03 | 0.79 | 0.21 | 1
8.3 | Cleaning | LS | 1 | 97128.91 | 97128.91 | 82.73% | 80358.99 | 8.85% | 8591.15 | 91.58% | 88950.14 | 0.83 | 0.09 | 0.92
8.4 | Handover | LS | 1 | 158660.57 | 158660.57 | 75.61% | 119961.86 | 24.39% | 38698.71 | 100.00% | 158660.57 | 0.76 | 0.24 | 1

## IPC_Jul_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 799528.66 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50231.24 | 50231.24 | 57.07% | 28668.29 | 28.38% | 14257.96 | 85.46% | 42926.25 | 0.57 | 0.28 | 0.85
1.2 | Site Fencing and Hoarding | LS | 1 | 51867.35 | 51867.35 | 61.63% | 31966.31 | 13.31% | 6902.26 | 74.94% | 38868.57 | 0.62 | 0.13 | 0.75
1.3 | Temporary Facilities Setup | LS | 1 | 385686.39 | 385686.39 | 65.17% | 251363.32 | 10.53% | 40626.28 | 75.71% | 291989.6 | 0.65 | 0.11 | 0.76
1.4 | Soil Testing and Survey | LS | 1 | 210746.37 | 210746.37 | 75.57% | 159254.34 | 5.86% | 12349.44 | 81.43% | 171603.78 | 0.76 | 0.06 | 0.82
1.5 | Excavation | LS | 1 | 54447.77 | 54447.77 | 43.41% | 23636.91 | 28.29% | 15405.9 | 71.71% | 39042.81 | 0.43 | 0.28 | 0.71
1.6 | Dewatering | LS | 1 | 46186.95 | 46186.95 | 71.26% | 32913.02 | 9.55% | 4410.35 | 80.81% | 37323.37 | 0.71 | 0.1 | 0.81
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3977882.4 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 353.05 | 1765250 | 48.00% | 847286.69 | 30.56% | 539543.36 | 78.56% | 1386830.05 | 2399.91 | 1528.23 | 3928.14
2.2 | Raft Foundation | m3 | 3500 | 272.49 | 953715 | 80.57% | 768388.89 | 16.22% | 154657.88 | 96.78% | 923046.77 | 2819.88 | 567.57 | 3387.45
2.3 | Basement Slab and Walls | m3 | 4000 | 409.92 | 1639680 | 66.64% | 1092738.72 | 7.50% | 123038.17 | 74.15% | 1215776.89 | 2665.74 | 300.15 | 2965.89
3 | Superstructure | LS | LS | - | 3165269.14 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 404.5 | 194160 | 41.66% | 80882.41 | 27.59% | 53564.75 | 69.25% | 134447.16 | 199.96 | 132.42 | 332.38
3.2 | Vertical Elements | m3 | 3600 | 216.36 | 778896 | 75.08% | 584806.64 | 9.12% | 71068.53 | 84.21% | 655875.17 | 2702.93 | 328.47 | 3031.4
3.3 | Floor Slabs | m3 | 6000 | 287.77 | 1726620 | 80.75% | 1394211.47 | 6.25% | 107970.35 | 87.00% | 1502181.82 | 4844.88 | 375.2 | 5220.08
3.4 | Staircase Construction | m3 | 1000 | 293.67 | 293670 | 54.04% | 158710.42 | 20.58% | 60426.96 | 74.62% | 219137.38 | 540.44 | 205.76 | 746.2
3.5 | Lift Core Construction | m3 | 1000 | 203 | 203000 | 63.82% | 129548.54 | 27.16% | 55143.76 | 90.98% | 184692.3 | 638.17 | 271.64 | 909.81
3.6 | Roof Slab and Parapets | m3 | 360 | 255.02 | 91807.2 | 47.54% | 43646.84 | 32.05% | 29419.7 | 79.59% | 73066.54 | 171.15 | 115.36 | 286.51
4 | Masonry and Partitioning | LS | LS | - | 13601624.21 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 161.8 | 5663000 | 76.09% | 4309177.42 | 18.42% | 1043319.85 | 94.52% | 5352497.27 | 26632.74 | 6448.21 | 33080.95
4.2 | Internal Blockwork | m2 | 35000 | 249.88 | 8745800 | 49.08% | 4292850.16 | 34.37% | 3006291.86 | 83.46% | 7299142.02 | 17179.65 | 12030.94 | 29210.59
4.3 | Drywall Partitioning | m3 | 1000 | 262.35 | 262350 | 63.89% | 167624.73 | 14.24% | 37367.5 | 78.14% | 204992.23 | 638.94 | 142.43 | 781.37
5 | MEP Works | LS | LS | - | 209868.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 48787.02 | 48787.02 | 73.10% | 35664.59 | 8.26% | 4030.6 | 81.36% | 39695.19 | 0.73 | 0.08 | 0.81
5.2 | Plumbing & Drainage | LS | 1 | 50601.39 | 50601.39 | 42.83% | 21671.78 | 30.41% | 15386.29 | 73.24% | 37058.07 | 0.43 | 0.3 | 0.73
5.3 | Firefighting Piping | LS | 1 | 48327.84 | 48327.84 | 53.81% | 26002.97 | 14.18% | 6854.98 | 67.99% | 32857.95 | 0.54 | 0.14 | 0.68
5.4 | HVAC Ducting | No. | 40 | 607.92 | 24316.8 | 50.01% | 12160.73 | 21.18% | 5149.95 | 71.19% | 17310.68 | 20 | 8.47 | 28.47
5.5 | Low Current Systems | LS | 1 | 45719.44 | 45719.44 | 48.29% | 22076.02 | 24.04% | 10992 | 72.33% | 33068.02 | 0.48 | 0.24 | 0.72
6 | Finishing Works | LS | LS | - | 13577220.37 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 58.9 | 1943700 | 58.93% | 1145346.78 | 26.34% | 511980.83 | 85.27% | 1657327.61 | 19445.62 | 8692.37 | 28137.99
6.2 | Waterproofing | m2 | 5000 | 264.6 | 1323000 | 82.61% | 1092935.42 | 9.94% | 131529.81 | 92.55% | 1224465.23 | 4130.52 | 497.09 | 4627.61
6.3 | Tiling | m2 | 15000 | 227.48 | 3412200 | 86.71% | 2958871.12 | 5.39% | 183832.9 | 92.10% | 3142704.02 | 13007.17 | 808.13 | 13815.3
6.4 | Painting | m2 | 40000 | 85.67 | 3426800 | 50.34% | 1725091.24 | 22.27% | 763189.22 | 72.61% | 2488280.46 | 20136.47 | 8908.48 | 29044.95
6.5 | Ceiling Works | m2 | 18000 | 139.38 | 2508840 | 79.81% | 2002280.06 | 14.74% | 369798.94 | 94.55% | 2372079 | 14365.62 | 2653.17 | 17018.79
6.6 | Joinery Installation | No. | 400 | 794.15 | 317660 | 63.50% | 201723.85 | 9.87% | 31358.08 | 73.37% | 233081.93 | 254.01 | 39.49 | 293.5
6.7 | Door & Window Installation | No. | 800 | 1390.08 | 1112064 | 69.36% | 771344.28 | 16.31% | 181429.82 | 85.68% | 952774.1 | 554.89 | 130.52 | 685.41
6.8 | Glazing | m2 | 12000 | 78.22 | 938640 | 75.26% | 706405.19 | 18.36% | 172369.82 | 93.62% | 878775.01 | 9031 | 2203.65 | 11234.65
7 | External Works & Landscaping | LS | LS | - | 2931387.42 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 797.08 | 79708 | 56.15% | 44754.35 | 30.60% | 24394.4 | 86.75% | 69148.75 | 56.15 | 30.6 | 86.75
7.2 | Roadworks and Paving | m2 | 8000 | 190.12 | 1520960 | 75.03% | 1141103.29 | 18.71% | 284564.47 | 93.73% | 1425667.76 | 6002.02 | 1496.76 | 7498.78
7.3 | Kerbstone and Interlock | m2 | 7000 | 121.56 | 850920 | 62.47% | 531572.62 | 30.04% | 255611.19 | 92.51% | 787183.81 | 4372.92 | 2102.76 | 6475.68
7.4 | Landscaping | m3 | 1000 | 374.49 | 374490 | 62.16% | 232786.98 | 28.59% | 107077.64 | 90.75% | 339864.62 | 621.61 | 285.93 | 907.54
7.5 | Boundary Wall | m3 | 1000 | 254.54 | 254540 | 55.85% | 142148.46 | 30.68% | 78092.66 | 86.53% | 220241.12 | 558.45 | 306.8 | 865.25
8 | Final Works | LS | LS | - | 573469.22 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 206636.98 | 206636.98 | 72.13% | 149049.02 | 6.76% | 13961.63 | 78.89% | 163010.65 | 0.72 | 0.07 | 0.79
8.2 | Snagging & De-snagging | LS | 1 | 105853.42 | 105853.42 | 44.73% | 47343.71 | 33.64% | 35604.21 | 78.36% | 82947.92 | 0.45 | 0.34 | 0.79
8.3 | Cleaning | LS | 1 | 104902.4 | 104902.4 | 55.55% | 58274.69 | 18.38% | 19280.9 | 73.93% | 77555.59 | 0.56 | 0.18 | 0.74
8.4 | Handover | LS | 1 | 160987.91 | 160987.91 | 57.42% | 92436.72 | 31.15% | 50147.9 | 88.57% | 142584.62 | 0.57 | 0.31 | 0.88