## IPC_Jul_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 770099.89 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 45320.38 | 45320.38 |  | 0 | 12.01% | 5441.35 | 12.01% | 5441.35 | 0 | 0.12 | 0.12
1.2 | Site Fencing and Hoarding | LS | 1 | 48619.3 | 48619.3 |  | 0 | 23.03% | 11198.75 | 23.03% | 11198.75 | 0 | 0.23 | 0.23
1.3 | Temporary Facilities Setup | LS | 1 | 365810.37 | 365810.37 |  | 0 | 16.04% | 58683.55 | 16.04% | 58683.55 | 0 | 0.16 | 0.16
1.4 | Soil Testing and Survey | LS | 1 | 201674.65 | 201674.65 |  | 0 | 19.27% | 38863.76 | 19.27% | 38863.76 | 0 | 0.19 | 0.19
1.5 | Excavation | LS | 1 | 51757.19 | 51757.19 |  | 0 | 14.24% | 7370.26 | 14.24% | 7370.26 | 0 | 0.14 | 0.14
1.6 | Dewatering | LS | 1 | 47525.94 | 47525.94 |  | 0 | 24.43% | 11609.55 | 24.43% | 11609.55 | 0 | 0.24 | 0.24
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3836202.74 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 374.55 | 1872750 |  | 0 | 27.19% | 509129.27 | 27.19% | 509129.27 | 0 | 1359.31 | 1359.31
2.2 | Raft Foundation | m3 | 3500 | 273.86 | 958510 |  | 0 | 27.26% | 261286.04 | 27.26% | 261286.04 | 0 | 954.09 | 954.09
2.3 | Basement Slab and Walls | m3 | 4000 | 351.12 | 1404480 |  | 0 | 17.36% | 243755.45 | 17.36% | 243755.45 | 0 | 694.22 | 694.22
3 | Superstructure | LS | LS | - | 3546843.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 389.67 | 187041.6 |  | 0 | 28.17% | 52698.09 | 28.17% | 52698.09 | 0 | 135.24 | 135.24
3.2 | Vertical Elements | m3 | 3600 | 223.01 | 802836 |  | 0 | 30.86% | 247756.57 | 30.86% | 247756.57 | 0 | 1110.97 | 1110.97
3.3 | Floor Slabs | m3 | 6000 | 266.8 | 1600800 |  | 0 | 25.04% | 400865.3 | 25.04% | 400865.3 | 0 | 1502.49 | 1502.49
3.4 | Staircase Construction | m3 | 1000 | 268.23 | 268230 |  | 0 | 8.95% | 24016.27 | 8.95% | 24016.27 | 0 | 89.54 | 89.54
3.5 | Lift Core Construction | m3 | 1000 | 229.09 | 229090 |  | 0 | 27.22% | 62349.69 | 27.22% | 62349.69 | 0 | 272.16 | 272.16
3.6 | Roof Slab and Parapets | m3 | 360 | 228.31 | 82191.6 |  | 0 | 30.52% | 25081.33 | 30.52% | 25081.33 | 0 | 109.86 | 109.86
4 | Masonry and Partitioning | LS | LS | - | 13821238.02 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 155.84 | 5454400 |  | 0 | 32.18% | 1755025.48 | 32.18% | 1755025.48 | 0 | 11261.71 | 11261.71
4.2 | Internal Blockwork | m2 | 35000 | 226.91 | 7941850 |  | 0 | 18.87% | 1498913.92 | 18.87% | 1498913.92 | 0 | 6605.76 | 6605.76
4.3 | Drywall Partitioning | m3 | 1000 | 247.7 | 247700 |  | 0 | 31.54% | 78112.69 | 31.54% | 78112.69 | 0 | 315.35 | 315.35
5 | MEP Works | LS | LS | - | 220544.47 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 46671.71 | 46671.71 |  | 0 | 34.12% | 15926.19 | 34.12% | 15926.19 | 0 | 0.34 | 0.34
5.2 | Plumbing & Drainage | LS | 1 | 50454.19 | 50454.19 |  | 0 | 25.30% | 12762.94 | 25.30% | 12762.94 | 0 | 0.25 | 0.25
5.3 | Firefighting Piping | LS | 1 | 52978.17 | 52978.17 |  | 0 | 16.08% | 8519.16 | 16.08% | 8519.16 | 0 | 0.16 | 0.16
5.4 | HVAC Ducting | No. | 40 | 639.12 | 25564.8 |  | 0 | 8.61% | 2200.92 | 8.61% | 2200.92 | 0 | 3.44 | 3.44
5.5 | Low Current Systems | LS | 1 | 54384.91 | 54384.91 |  | 0 | 21.81% | 11860.93 | 21.81% | 11860.93 | 0 | 0.22 | 0.22
6 | Finishing Works | LS | LS | - | 15614366.37 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 55.97 | 1847010 |  | 0 | 29.29% | 540949.63 | 29.29% | 540949.63 | 0 | 9664.99 | 9664.99
6.2 | Waterproofing | m2 | 5000 | 258.35 | 1291750 |  | 0 | 14.26% | 184174.35 | 14.26% | 184174.35 | 0 | 712.89 | 712.89
6.3 | Tiling | m2 | 15000 | 223.2 | 3348000 |  | 0 | 12.99% | 435009.15 | 12.99% | 435009.15 | 0 | 1948.97 | 1948.97
6.4 | Painting | m2 | 40000 | 89.71 | 3588400 |  | 0 | 15.83% | 568005.24 | 15.83% | 568005.24 | 0 | 6331.57 | 6331.57
6.5 | Ceiling Works | m2 | 18000 | 139.98 | 2519640 |  | 0 | 28.49% | 717789.8 | 28.49% | 717789.8 | 0 | 5127.8 | 5127.8
6.6 | Joinery Installation | No. | 400 | 828.68 | 331472 |  | 0 | 13.85% | 45907.2 | 13.85% | 45907.2 | 0 | 55.4 | 55.4
6.7 | Door & Window Installation | No. | 800 | 1312.28 | 1049824 |  | 0 | 34.25% | 359536.84 | 34.25% | 359536.84 | 0 | 273.98 | 273.98
6.8 | Glazing | m2 | 12000 | 80.77 | 969240 |  | 0 | 27.42% | 265744.27 | 27.42% | 265744.27 | 0 | 3290.14 | 3290.14
7 | External Works & Landscaping | LS | LS | - | 3333727.21 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 833.09 | 83309 |  | 0 | 27.86% | 23212.35 | 27.86% | 23212.35 | 0 | 27.86 | 27.86
7.2 | Roadworks and Paving | m2 | 8000 | 206.29 | 1650320 |  | 0 | 21.08% | 347879.79 | 21.08% | 347879.79 | 0 | 1686.36 | 1686.36
7.3 | Kerbstone and Interlock | m2 | 7000 | 104.8 | 733600 |  | 0 | 34.29% | 251554.9 | 34.29% | 251554.9 | 0 | 2400.33 | 2400.33
7.4 | Landscaping | m3 | 1000 | 351.57 | 351570 |  | 0 | 30.39% | 106831.33 | 30.39% | 106831.33 | 0 | 303.87 | 303.87
7.5 | Boundary Wall | m3 | 1000 | 291.92 | 291920 |  | 0 | 24.32% | 71003.92 | 24.32% | 71003.92 | 0 | 243.23 | 243.23
8 | Final Works | LS | LS | - | 571878.36 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 215228.82 | 215228.82 |  | 0 | 36.72% | 79030.51 | 36.72% | 79030.51 | 0 | 0.37 | 0.37
8.2 | Snagging & De-snagging | LS | 1 | 106316.34 | 106316.34 |  | 0 | 11.50% | 12223.58 | 11.50% | 12223.58 | 0 | 0.11 | 0.11
8.3 | Cleaning | LS | 1 | 98319.44 | 98319.44 |  | 0 | 11.36% | 11170.22 | 11.36% | 11170.22 | 0 | 0.11 | 0.11
8.4 | Handover | LS | 1 | 146087.08 | 146087.08 |  | 0 | 15.62% | 22815.94 | 15.62% | 22815.94 | 0 | 0.16 | 0.16

## IPC_Aug_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 855722.09 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 48740.33 | 48740.33 | 68.53% | 33402.07 | 7.38% | 3597.32 | 75.91% | 36999.39 | 0.69 | 0.07 | 0.76
1.2 | Site Fencing and Hoarding | LS | 1 | 48965.64 | 48965.64 | 22.54% | 11034.98 | 34.49% | 16888.53 | 57.03% | 27923.51 | 0.23 | 0.34 | 0.57
1.3 | Temporary Facilities Setup | LS | 1 | 389730.65 | 389730.65 | 45.87% | 178779.2 | 28.69% | 111812.75 | 74.56% | 290591.95 | 0.46 | 0.29 | 0.75
1.4 | Soil Testing and Survey | LS | 1 | 198648.01 | 198648.01 | 45.32% | 90032.17 | 22.03% | 43767.34 | 67.36% | 133799.51 | 0.45 | 0.22 | 0.67
1.5 | Excavation | LS | 1 | 51640.79 | 51640.79 | 62.86% | 32459.78 | 11.21% | 5787.33 | 74.06% | 38247.11 | 0.63 | 0.11 | 0.74
1.6 | Dewatering | LS | 1 | 47749.62 | 47749.62 | 51.15% | 24424.44 | 6.23% | 2976.73 | 57.39% | 27401.17 | 0.51 | 0.06 | 0.57
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4069363.53 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 338.73 | 1693650 | 49.90% | 845066.92 | 10.75% | 182111.39 | 60.65% | 1027178.31 | 2494.81 | 537.63 | 3032.44
2.2 | Raft Foundation | m3 | 3500 | 239.79 | 839265 | 59.86% | 502395.08 | 7.35% | 61662.14 | 67.21% | 564057.22 | 2095.15 | 257.15 | 2352.3
2.3 | Basement Slab and Walls | m3 | 4000 | 375.43 | 1501720 | 24.82% | 372734.25 | 27.80% | 417525.14 | 52.62% | 790259.39 | 992.82 | 1112.13 | 2104.95
3 | Superstructure | LS | LS | - | 3173408.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 355.2 | 170496 | 63.28% | 107887.7 | 5.92% | 10088.06 | 69.20% | 117975.76 | 303.74 | 28.4 | 332.14
3.2 | Vertical Elements | m3 | 3600 | 215.49 | 775764 | 36.99% | 286988.16 | 16.84% | 130677.07 | 53.84% | 417665.23 | 1331.79 | 606.42 | 1938.21
3.3 | Floor Slabs | m3 | 6000 | 300.61 | 1803660 | 53.59% | 966668.97 | 17.46% | 314967.69 | 71.06% | 1281636.66 | 3215.69 | 1047.76 | 4263.45
3.4 | Staircase Construction | m3 | 1000 | 264.95 | 264950 | 66.27% | 175579.26 | 8.81% | 23350.62 | 75.08% | 198929.88 | 662.69 | 88.13 | 750.82
3.5 | Lift Core Construction | m3 | 1000 | 190.87 | 190870 | 28.37% | 54148.13 | 33.58% | 64096.69 | 61.95% | 118244.82 | 283.69 | 335.81 | 619.5
3.6 | Roof Slab and Parapets | m3 | 360 | 228.44 | 82238.4 | 28.94% | 23797.62 | 33.51% | 27557.82 | 62.45% | 51355.44 | 104.17 | 120.63 | 224.8
4 | Masonry and Partitioning | LS | LS | - | 14344005 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 154.25 | 5398750 | 38.11% | 2057668.37 | 31.07% | 1677483.65 | 69.19% | 3735152.02 | 13339.83 | 10875.1 | 24214.93
4.2 | Internal Blockwork | m2 | 35000 | 225.32 | 7886200 | 58.14% | 4584887.2 | 12.48% | 984534.1 | 70.62% | 5569421.3 | 20348.34 | 4369.49 | 24717.83
4.3 | Drywall Partitioning | m3 | 1000 | 269 | 269000 | 63.21% | 170023.94 | 10.89% | 29283.31 | 74.09% | 199307.25 | 632.06 | 108.86 | 740.92
5 | MEP Works | LS | LS | - | 224958.54 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 49350.15 | 49350.15 | 60.70% | 29953.99 | 14.28% | 7047.38 | 74.98% | 37001.37 | 0.61 | 0.14 | 0.75
5.2 | Plumbing & Drainage | LS | 1 | 53046.45 | 53046.45 | 20.72% | 10990.53 | 28.47% | 15104.33 | 49.19% | 26094.86 | 0.21 | 0.28 | 0.49
5.3 | Firefighting Piping | LS | 1 | 48918.51 | 48918.51 | 31.49% | 15405.59 | 32.76% | 16023.9 | 64.25% | 31429.49 | 0.31 | 0.33 | 0.64
5.4 | HVAC Ducting | No. | 40 | 564.76 | 22590.4 | 41.33% | 9336.87 | 30.87% | 6974.72 | 72.21% | 16311.59 | 16.53 | 12.35 | 28.88
5.5 | Low Current Systems | LS | 1 | 54565.71 | 54565.71 | 29.95% | 16340.69 | 34.21% | 18665.08 | 64.15% | 35005.77 | 0.3 | 0.34 | 0.64
6 | Finishing Works | LS | LS | - | 15783997.29 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 57.97 | 1913010 | 21.03% | 402285.82 | 27.92% | 534138.75 | 48.95% | 936424.57 | 6939.55 | 9214.05 | 16153.6
6.2 | Waterproofing | m2 | 5000 | 261.9 | 1309500 | 26.21% | 343156.81 | 23.98% | 314010.45 | 50.18% | 657167.26 | 1310.26 | 1198.97 | 2509.23
6.3 | Tiling | m2 | 15000 | 262.22 | 3933300 | 34.91% | 1373015.27 | 25.54% | 1004471.83 | 60.45% | 2377487.1 | 5236.12 | 3830.65 | 9066.77
6.4 | Painting | m2 | 40000 | 83.66 | 3346400 | 43.42% | 1452945.11 | 21.00% | 702823.24 | 64.42% | 2155768.35 | 17367.26 | 8400.95 | 25768.21
6.5 | Ceiling Works | m2 | 18000 | 127.1 | 2287800 | 28.34% | 648340.29 | 23.34% | 533979.58 | 51.68% | 1182319.87 | 5101.03 | 4201.26 | 9302.29
6.6 | Joinery Installation | No. | 400 | 838.88 | 335552 | 58.42% | 196029.45 | 14.45% | 48481.05 | 72.87% | 244510.5 | 233.68 | 57.79 | 291.47
6.7 | Door & Window Installation | No. | 800 | 1552.57 | 1242056 | 35.68% | 443198.86 | 27.26% | 338539.19 | 62.94% | 781738.05 | 285.46 | 218.05 | 503.51
6.8 | Glazing | m2 | 12000 | 82.11 | 985320 | 26.08% | 257005.94 | 23.81% | 234563.95 | 49.89% | 491569.89 | 3130.02 | 2856.7 | 5986.72
7 | External Works & Landscaping | LS | LS | - | 3153770.96 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 877.62 | 87762 | 15.41% | 13520.68 | 33.62% | 29502.34 | 49.02% | 43023.02 | 15.41 | 33.62 | 49.03
7.2 | Roadworks and Paving | m2 | 8000 | 209.51 | 1676080 | 45.52% | 762889.19 | 5.40% | 90588.24 | 50.92% | 853477.43 | 3641.3 | 432.38 | 4073.68
7.3 | Kerbstone and Interlock | m2 | 7000 | 120.58 | 844060 | 22.54% | 190225.39 | 31.81% | 268474.59 | 54.34% | 458699.98 | 1577.59 | 2226.53 | 3804.12
7.4 | Landscaping | m3 | 1000 | 370.32 | 370320 | 42.21% | 156307.18 | 9.79% | 36238.08 | 51.99% | 192545.26 | 422.09 | 97.86 | 519.95
7.5 | Boundary Wall | m3 | 1000 | 293.27 | 293270 | 15.15% | 44433.29 | 32.46% | 95201.4 | 47.61% | 139634.69 | 151.51 | 324.62 | 476.13
8 | Final Works | LS | LS | - | 521616.84 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 194622.93 | 194622.93 | 52.52% | 102214.23 | 11.70% | 22777.83 | 64.22% | 124992.06 | 0.53 | 0.12 | 0.65
8.2 | Snagging & De-snagging | LS | 1 | 99203.66 | 99203.66 | 27.22% | 27002.75 | 22.52% | 22340.39 | 49.74% | 49343.14 | 0.27 | 0.23 | 0.5
8.3 | Cleaning | LS | 1 | 98787.3 | 98787.3 | 58.39% | 57677.2 | 10.50% | 10374.77 | 68.89% | 68051.97 | 0.58 | 0.11 | 0.69
8.4 | Handover | LS | 1 | 147497.8 | 147497.8 | 45.83% | 67595.65 | 20.40% | 30084.16 | 66.22% | 97679.81 | 0.46 | 0.2 | 0.66

## IPC_Sep_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 850001.05 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 52711.12 | 52711.12 | 69.69% | 36733.58 | 10.43% | 5496.55 | 80.12% | 42230.13 | 0.7 | 0.1 | 0.8
1.2 | Site Fencing and Hoarding | LS | 1 | 48646.19 | 48646.19 | 55.20% | 26850.32 | 18.27% | 8888.72 | 73.47% | 35739.04 | 0.55 | 0.18 | 0.73
1.3 | Temporary Facilities Setup | LS | 1 | 411085.13 | 411085.13 | 62.90% | 258590.49 | 18.15% | 74627.67 | 81.06% | 333218.16 | 0.63 | 0.18 | 0.81
1.4 | Soil Testing and Survey | LS | 1 | 214057.39 | 214057.39 | 62.11% | 132941.19 | 13.69% | 29302.55 | 75.79% | 162243.74 | 0.62 | 0.14 | 0.76
1.5 | Excavation | LS | 1 | 48945.44 | 48945.44 | 33.88% | 16582.64 | 34.67% | 16967.55 | 68.55% | 33550.19 | 0.34 | 0.35 | 0.69
1.6 | Dewatering | LS | 1 | 49773.46 | 49773.46 | 49.83% | 24800.39 | 9.85% | 4903.01 | 59.68% | 29703.4 | 0.5 | 0.1 | 0.6
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4516604.48 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 360.55 | 1802750 | 46.42% | 836871.45 | 19.49% | 351299.02 | 65.91% | 1188170.47 | 2321.1 | 974.34 | 3295.44
2.2 | Raft Foundation | m3 | 3500 | 262 | 917000 | 39.42% | 361519.67 | 22.80% | 209077.84 | 62.22% | 570597.51 | 1379.85 | 798.01 | 2177.86
2.3 | Basement Slab and Walls | m3 | 4000 | 391.47 | 1565880 | 32.02% | 501326.69 | 31.01% | 485655.17 | 63.03% | 986981.86 | 1280.63 | 1240.59 | 2521.22
3 | Superstructure | LS | LS | - | 3239204.72 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 424.23 | 203630.4 | 66.42% | 135255.33 | 7.57% | 15420.46 | 73.99% | 150675.79 | 318.83 | 36.35 | 355.18
3.2 | Vertical Elements | m3 | 3600 | 233.65 | 841140 | 42.31% | 355856.68 | 19.55% | 164435.37 | 61.86% | 520292.05 | 1523.03 | 703.77 | 2226.8
3.3 | Floor Slabs | m3 | 6000 | 280.14 | 1680840 | 52.54% | 883035.9 | 17.85% | 300041.51 | 70.39% | 1183077.41 | 3152.12 | 1071.04 | 4223.16
3.4 | Staircase Construction | m3 | 1000 | 307.07 | 307070 | 35.60% | 109329.98 | 17.62% | 54107.09 | 53.22% | 163437.07 | 356.04 | 176.2 | 532.24
3.5 | Lift Core Construction | m3 | 1000 | 209.06 | 209060 | 45.02% | 94124.26 | 22.14% | 46279.87 | 67.16% | 140404.13 | 450.23 | 221.37 | 671.6
3.6 | Roof Slab and Parapets | m3 | 360 | 247.24 | 89006.4 | 42.81% | 38099.77 | 28.47% | 25342.7 | 71.28% | 63442.47 | 154.1 | 102.5 | 256.6
4 | Masonry and Partitioning | LS | LS | - | 13945907.84 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 180.99 | 6334650 | 47.11% | 2984071.54 | 9.68% | 613163.42 | 56.79% | 3597234.96 | 16487.49 | 3387.83 | 19875.32
4.2 | Internal Blockwork | m2 | 35000 | 228.18 | 7986300 | 53.78% | 4294884.19 | 16.49% | 1316638.27 | 70.26% | 5611522.46 | 18822.35 | 5770.17 | 24592.52
4.3 | Drywall Partitioning | m3 | 1000 | 251.1 | 251100 | 30.20% | 75841.89 | 28.93% | 72632.91 | 59.13% | 148474.8 | 302.04 | 289.26 | 591.3
5 | MEP Works | LS | LS | - | 240865.4 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 54240.64 | 54240.64 | 34.07% | 18480.62 | 24.21% | 13130.88 | 58.28% | 31611.5 | 0.34 | 0.24 | 0.58
5.2 | Plumbing & Drainage | LS | 1 | 52384.41 | 52384.41 | 69.28% | 36289.33 | 9.46% | 4954.02 | 78.73% | 41243.35 | 0.69 | 0.09 | 0.78
5.3 | Firefighting Piping | LS | 1 | 53302.6 | 53302.6 | 52.89% | 28190.11 | 5.26% | 2804.92 | 58.15% | 30995.03 | 0.53 | 0.05 | 0.58
5.4 | HVAC Ducting | No. | 40 | 611.01 | 24440.4 | 58.38% | 14268.27 | 21.38% | 5224.86 | 79.76% | 19493.13 | 23.35 | 8.55 | 31.9
5.5 | Low Current Systems | LS | 1 | 46911.66 | 46911.66 | 58.29% | 27346.94 | 17.72% | 8311.8 | 76.01% | 35658.74 | 0.58 | 0.18 | 0.76
6 | Finishing Works | LS | LS | - | 14191608.89 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 50.86 | 1678380 | 47.42% | 795851.65 | 24.16% | 405416.79 | 71.57% | 1201268.44 | 15647.89 | 7971.23 | 23619.12
6.2 | Waterproofing | m2 | 5000 | 258.7 | 1293500 | 63.52% | 821601.86 | 10.77% | 139281.75 | 74.29% | 960883.61 | 3175.89 | 538.39 | 3714.28
6.3 | Tiling | m2 | 15000 | 252.76 | 3791400 | 64.28% | 2437024.28 | 9.54% | 361796.76 | 73.82% | 2798821.04 | 9641.65 | 1431.38 | 11073.03
6.4 | Painting | m2 | 40000 | 92.35 | 3694000 | 53.47% | 1975243.52 | 25.62% | 946291.54 | 79.09% | 2921535.06 | 21388.67 | 10246.8 | 31635.47
6.5 | Ceiling Works | m2 | 18000 | 129.47 | 2330460 | 40.38% | 941024.96 | 26.83% | 625252.12 | 67.21% | 1566277.08 | 7268.29 | 4829.32 | 12097.61
6.6 | Joinery Installation | No. | 400 | 777.72 | 311088 | 41.37% | 128706.83 | 27.19% | 84589.88 | 68.56% | 213296.71 | 165.49 | 108.77 | 274.26
6.7 | Door & Window Installation | No. | 800 | 1536.3 | 1229040 | 51.91% | 638037.7 | 11.53% | 141732.2 | 63.45% | 779769.9 | 415.31 | 92.26 | 507.57
6.8 | Glazing | m2 | 12000 | 80.35 | 964200 | 43.94% | 423705.43 | 8.79% | 84760.49 | 52.73% | 508465.92 | 5273.25 | 1054.89 | 6328.14
7 | External Works & Landscaping | LS | LS | - | 3242801.85 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 773.39 | 77339 | 45.02% | 34815.06 | 34.43% | 26631.54 | 79.45% | 61446.6 | 45.02 | 34.43 | 79.45
7.2 | Roadworks and Paving | m2 | 8000 | 191.05 | 1528400 | 53.99% | 825214 | 26.48% | 404686.33 | 80.47% | 1229900.33 | 4319.36 | 2118.22 | 6437.58
7.3 | Kerbstone and Interlock | m2 | 7000 | 101.84 | 712880 | 62.74% | 447272.41 | 11.88% | 84690.6 | 74.62% | 531963.01 | 4391.91 | 831.6 | 5223.51
7.4 | Landscaping | m3 | 1000 | 402.69 | 402690 | 61.16% | 246292.57 | 5.55% | 22365.81 | 66.72% | 268658.38 | 611.62 | 55.54 | 667.16
7.5 | Boundary Wall | m3 | 1000 | 300.09 | 300090 | 41.27% | 123859.55 | 24.85% | 74586.72 | 66.13% | 198446.27 | 412.74 | 248.55 | 661.29
8 | Final Works | LS | LS | - | 575635.59 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 198605.95 | 198605.95 | 55.82% | 110857.33 | 25.06% | 49771.66 | 80.88% | 160628.99 | 0.56 | 0.25 | 0.81
8.2 | Snagging & De-snagging | LS | 1 | 107195.83 | 107195.83 | 33.57% | 35990.63 | 26.75% | 28677.22 | 60.33% | 64667.85 | 0.34 | 0.27 | 0.61
8.3 | Cleaning | LS | 1 | 103463.14 | 103463.14 | 37.59% | 38896.41 | 31.47% | 32557.18 | 69.06% | 71453.59 | 0.38 | 0.31 | 0.69
8.4 | Handover | LS | 1 | 147742.02 | 147742.02 | 53.39% | 78886.63 | 26.55% | 39220.67 | 79.94% | 118107.3 | 0.53 | 0.27 | 0.8

## IPC_Oct_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 864198.54 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 49431.03 | 49431.03 | 79.33% | 39214.46 | 20.67% | 10216.57 | 100.00% | 49431.03 | 0.79 | 0.21 | 1
1.2 | Site Fencing and Hoarding | LS | 1 | 46849.04 | 46849.04 | 64.60% | 30266.52 | 32.99% | 15454.15 | 97.59% | 45720.67 | 0.65 | 0.33 | 0.98
1.3 | Temporary Facilities Setup | LS | 1 | 436061.52 | 436061.52 | 61.07% | 266290.51 | 26.02% | 113460.05 | 87.09% | 379750.56 | 0.61 | 0.26 | 0.87
1.4 | Soil Testing and Survey | LS | 1 | 211823.59 | 211823.59 | 76.07% | 161132.82 | 23.93% | 50690.77 | 100.00% | 211823.59 | 0.76 | 0.24 | 1
1.5 | Excavation | LS | 1 | 54877.62 | 54877.62 | 73.10% | 40116.25 | 26.90% | 14761.37 | 100.00% | 54877.62 | 0.73 | 0.27 | 1
1.6 | Dewatering | LS | 1 | 47854.76 | 47854.76 | 87.02% | 41641.28 | 10.87% | 5201.03 | 97.88% | 46842.31 | 0.87 | 0.11 | 0.98
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3942029.43 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 342.24 | 1711200 | 78.81% | 1348615.96 | 21.19% | 362584.04 | 100.00% | 1711200 | 3940.56 | 1059.44 | 5000
2.2 | Raft Foundation | m3 | 3500 | 235.23 | 823305 | 74.59% | 614135.55 | 25.41% | 209169.45 | 100.00% | 823305 | 2610.79 | 889.21 | 3500
2.3 | Basement Slab and Walls | m3 | 4000 | 403.63 | 1614520 | 83.51% | 1348331.08 | 9.03% | 145818.92 | 92.54% | 1494150 | 3340.51 | 361.27 | 3701.78
3 | Superstructure | LS | LS | - | 3491002.23 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 421.48 | 202310.4 | 90.53% | 183152.38 | 9.47% | 19158.02 | 100.00% | 202310.4 | 434.55 | 45.45 | 480
3.2 | Vertical Elements | m3 | 3600 | 206.86 | 744696 | 94.00% | 700023.4 | 6.00% | 44672.6 | 100.00% | 744696 | 3384.04 | 215.96 | 3600
3.3 | Floor Slabs | m3 | 6000 | 268.62 | 1611720 | 66.07% | 1064916.49 | 33.93% | 546803.51 | 100.00% | 1611720 | 3964.4 | 2035.6 | 6000
3.4 | Staircase Construction | m3 | 1000 | 276.44 | 276440 | 67.75% | 187279.29 | 32.25% | 89160.71 | 100.00% | 276440 | 677.47 | 322.53 | 1000
3.5 | Lift Core Construction | m3 | 1000 | 223.67 | 223670 | 74.36% | 166313.07 | 25.64% | 57356.93 | 100.00% | 223670 | 743.56 | 256.44 | 1000
3.6 | Roof Slab and Parapets | m3 | 360 | 241.3 | 86868 | 88.48% | 76858.22 | 11.52% | 10009.78 | 100.00% | 86868 | 318.52 | 41.48 | 360
4 | Masonry and Partitioning | LS | LS | - | 13620018.31 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 169.64 | 5937400 | 52.73% | 3130602.92 | 34.88% | 2070746.31 | 87.60% | 5201349.23 | 18454.39 | 12206.71 | 30661.1
4.2 | Internal Blockwork | m2 | 35000 | 213.43 | 7470050 | 90.31% | 6746357.59 | 9.69% | 723692.41 | 100.00% | 7470050 | 31609.23 | 3390.77 | 35000
4.3 | Drywall Partitioning | m3 | 1000 | 253.49 | 253490 | 86.80% | 220037.86 | 13.20% | 33452.14 | 100.00% | 253490 | 868.03 | 131.97 | 1000
5 | MEP Works | LS | LS | - | 210458.03 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 51370.66 | 51370.66 | 93.16% | 47858.74 | 6.84% | 3511.92 | 100.00% | 51370.66 | 0.93 | 0.07 | 1
5.2 | Plumbing & Drainage | LS | 1 | 49278.59 | 49278.59 | 72.41% | 35684.03 | 16.88% | 8319.47 | 89.30% | 44003.5 | 0.72 | 0.17 | 0.89
5.3 | Firefighting Piping | LS | 1 | 46579.34 | 46579.34 | 79.66% | 37105.97 | 18.53% | 8632.23 | 98.19% | 45738.2 | 0.8 | 0.19 | 0.99
5.4 | HVAC Ducting | No. | 40 | 545.1 | 21804 | 80.49% | 17549.4 | 11.49% | 2504.55 | 91.97% | 20053.95 | 32.19 | 4.59 | 36.78
5.5 | Low Current Systems | LS | 1 | 53350.08 | 53350.08 | 86.31% | 46045.42 | 13.69% | 7304.66 | 100.00% | 53350.08 | 0.86 | 0.14 | 1
6 | Finishing Works | LS | LS | - | 15763336.4 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 50.05 | 1651650 | 78.11% | 1290171.08 | 21.28% | 351406.77 | 99.39% | 1641577.85 | 25777.64 | 7021.11 | 32798.75
6.2 | Waterproofing | m2 | 5000 | 250.78 | 1253900 | 65.16% | 817094.58 | 34.84% | 436805.42 | 100.00% | 1253900 | 3258.21 | 1741.79 | 5000
6.3 | Tiling | m2 | 15000 | 262.71 | 3940650 | 89.69% | 3534172.16 | 10.31% | 406477.84 | 100.00% | 3940650 | 13452.75 | 1547.25 | 15000
6.4 | Painting | m2 | 40000 | 78.84 | 3153600 | 81.69% | 2576258.53 | 10.10% | 318406.68 | 91.79% | 2894665.21 | 32677.05 | 4038.64 | 36715.69
6.5 | Ceiling Works | m2 | 18000 | 125 | 2250000 | 82.02% | 1845552.66 | 17.98% | 404447.34 | 100.00% | 2250000 | 14764.42 | 3235.58 | 18000
6.6 | Joinery Installation | No. | 400 | 778.76 | 311504 | 73.35% | 228492.05 | 26.65% | 83011.95 | 100.00% | 311504 | 293.4 | 106.6 | 400
6.7 | Door & Window Installation | No. | 800 | 1367.37 | 1093896 | 90.47% | 989621.55 | 9.53% | 104274.45 | 100.00% | 1093896 | 723.74 | 76.26 | 800
6.8 | Glazing | m2 | 12000 | 75.35 | 904200 | 90.12% | 814836.47 | 9.88% | 89363.53 | 100.00% | 904200 | 10814.02 | 1185.98 | 12000
7 | External Works & Landscaping | LS | LS | - | 3246236.39 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 887.93 | 88793 | 57.86% | 51374.76 | 33.90% | 30104 | 91.76% | 81478.76 | 57.86 | 33.9 | 91.76
7.2 | Roadworks and Paving | m2 | 8000 | 215.78 | 1726240 | 69.65% | 1202385.2 | 30.35% | 523854.8 | 100.00% | 1726240 | 5572.27 | 2427.73 | 8000
7.3 | Kerbstone and Interlock | m2 | 7000 | 105.29 | 737030 | 70.38% | 518702.01 | 26.51% | 195351.51 | 96.88% | 714053.52 | 4926.41 | 1855.37 | 6781.78
7.4 | Landscaping | m3 | 1000 | 388.34 | 388340 | 62.25% | 241744.79 | 25.57% | 99286.82 | 87.82% | 341031.61 | 622.51 | 255.67 | 878.18
7.5 | Boundary Wall | m3 | 1000 | 259.39 | 259390 | 75.63% | 196187.69 | 11.55% | 29968.16 | 87.19% | 226155.85 | 756.34 | 115.53 | 871.87
8 | Final Works | LS | LS | - | 586033.51 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 219492.38 | 219492.38 | 78.45% | 172181.65 | 21.55% | 47310.73 | 100.00% | 219492.38 | 0.78 | 0.22 | 1
8.2 | Snagging & De-snagging | LS | 1 | 104148.66 | 104148.66 | 75.45% | 78581.91 | 24.55% | 25566.75 | 100.00% | 104148.66 | 0.75 | 0.25 | 1
8.3 | Cleaning | LS | 1 | 108828.63 | 108828.63 | 60.88% | 66249.6 | 29.82% | 32448.16 | 90.69% | 98697.76 | 0.61 | 0.3 | 0.91
8.4 | Handover | LS | 1 | 141997.52 | 141997.52 | 66.78% | 94825.32 | 31.58% | 44848.48 | 98.36% | 139673.8 | 0.67 | 0.32 | 0.99