## IPC_Apr_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 867393.65 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 51500.27 | 51500.27 |  | 0 | 24.41% | 12569.26 | 24.41% | 12569.26 | 0 | 0.24 | 0.24
1.2 | Site Fencing and Hoarding | LS | 1 | 48838.48 | 48838.48 |  | 0 | 44.67% | 21814.17 | 44.67% | 21814.17 | 0 | 0.45 | 0.45
1.3 | Temporary Facilities Setup | LS | 1 | 424985.21 | 424985.21 |  | 0 | 37.85% | 160868.14 | 37.85% | 160868.14 | 0 | 0.38 | 0.38
1.4 | Soil Testing and Survey | LS | 1 | 182397.8 | 182397.8 |  | 0 | 18.88% | 34430.64 | 18.88% | 34430.64 | 0 | 0.19 | 0.19
1.5 | Excavation | LS | 1 | 48754.51 | 48754.51 |  | 0 | 40.21% | 19601.84 | 40.21% | 19601.84 | 0 | 0.4 | 0.4
1.6 | Dewatering | LS | 1 | 49499.98 | 49499.98 |  | 0 | 43.21% | 21389.58 | 43.21% | 21389.58 | 0 | 0.43 | 0.43
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4547595.31 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 377.51 | 1887550 |  | 0 | 43.64% | 823819.77 | 43.64% | 823819.77 | 0 | 2182.25 | 2182.25
2.2 | Raft Foundation | m3 | 3500 | 268.46 | 939610 |  | 0 | 31.85% | 299294.05 | 31.85% | 299294.05 | 0 | 1114.86 | 1114.86
2.3 | Basement Slab and Walls | m3 | 4000 | 416.49 | 1665960 |  | 0 | 17.45% | 290673.29 | 17.45% | 290673.29 | 0 | 697.91 | 697.91
3 | Superstructure | LS | LS | - | 3117437.88 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 407.34 | 195523.2 |  | 0 | 42.67% | 83426.1 | 42.67% | 83426.1 | 0 | 204.81 | 204.81
3.2 | Vertical Elements | m3 | 3600 | 198.71 | 715356 |  | 0 | 19.20% | 137316.1 | 19.20% | 137316.1 | 0 | 691.04 | 691.04
3.3 | Floor Slabs | m3 | 6000 | 283.45 | 1700700 |  | 0 | 39.55% | 672678.85 | 39.55% | 672678.85 | 0 | 2373.18 | 2373.18
3.4 | Staircase Construction | m3 | 1000 | 265.95 | 265950 |  | 0 | 23.25% | 61829.35 | 23.25% | 61829.35 | 0 | 232.48 | 232.48
3.5 | Lift Core Construction | m3 | 1000 | 218.31 | 218310 |  | 0 | 20.55% | 44857.58 | 20.55% | 44857.58 | 0 | 205.48 | 205.48
3.6 | Roof Slab and Parapets | m3 | 360 | 246.96 | 88905.6 |  | 0 | 41.76% | 37129.14 | 41.76% | 37129.14 | 0 | 150.34 | 150.34
4 | Masonry and Partitioning | LS | LS | - | 13691323.93 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 174.24 | 6098400 |  | 0 | 44.84% | 2734755.08 | 44.84% | 2734755.08 | 0 | 15695.33 | 15695.33
4.2 | Internal Blockwork | m2 | 35000 | 251.1 | 8788500 |  | 0 | 29.55% | 2597249.96 | 29.55% | 2597249.96 | 0 | 10343.49 | 10343.49
4.3 | Drywall Partitioning | m3 | 1000 | 224.13 | 224130 |  | 0 | 36.94% | 82798.44 | 36.94% | 82798.44 | 0 | 369.42 | 369.42
5 | MEP Works | LS | LS | - | 207979.63 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 47415.63 | 47415.63 |  | 0 | 39.55% | 18752.94 | 39.55% | 18752.94 | 0 | 0.4 | 0.4
5.2 | Plumbing & Drainage | LS | 1 | 51959.7 | 51959.7 |  | 0 | 16.81% | 8733.12 | 16.81% | 8733.12 | 0 | 0.17 | 0.17
5.3 | Firefighting Piping | LS | 1 | 46731.71 | 46731.71 |  | 0 | 24.65% | 11519.12 | 24.65% | 11519.12 | 0 | 0.25 | 0.25
5.4 | HVAC Ducting | No. | 40 | 619.59 | 24783.6 |  | 0 | 21.83% | 5409.05 | 21.83% | 5409.05 | 0 | 8.73 | 8.73
5.5 | Low Current Systems | LS | 1 | 52177.27 | 52177.27 |  | 0 | 16.85% | 8794.13 | 16.85% | 8794.13 | 0 | 0.17 | 0.17
6 | Finishing Works | LS | LS | - | 15055818.77 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 53.1 | 1752300 |  | 0 | 45.64% | 799716.21 | 45.64% | 799716.21 | 0 | 15060.57 | 15060.57
6.2 | Waterproofing | m2 | 5000 | 232.71 | 1163550 |  | 0 | 23.67% | 275430.64 | 23.67% | 275430.64 | 0 | 1183.58 | 1183.58
6.3 | Tiling | m2 | 15000 | 241.7 | 3625500 |  | 0 | 23.65% | 857417.51 | 23.65% | 857417.51 | 0 | 3547.45 | 3547.45
6.4 | Painting | m2 | 40000 | 87.39 | 3495600 |  | 0 | 32.41% | 1132928.09 | 32.41% | 1132928.09 | 0 | 12964.05 | 12964.05
6.5 | Ceiling Works | m2 | 18000 | 136.27 | 2452860 |  | 0 | 40.91% | 1003491.67 | 40.91% | 1003491.67 | 0 | 7364 | 7364
6.6 | Joinery Installation | No. | 400 | 758.4 | 303360 |  | 0 | 45.04% | 136621.8 | 45.04% | 136621.8 | 0 | 180.14 | 180.14
6.7 | Door & Window Installation | No. | 800 | 1329.75 | 1063800 |  | 0 | 33.31% | 354392.17 | 33.31% | 354392.17 | 0 | 266.51 | 266.51
6.8 | Glazing | m2 | 12000 | 74.91 | 898920 |  | 0 | 32.15% | 288996.45 | 32.15% | 288996.45 | 0 | 3857.92 | 3857.92
7 | External Works & Landscaping | LS | LS | - | 2959822.94 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 869.65 | 86965 |  | 0 | 44.98% | 39115.85 | 44.98% | 39115.85 | 0 | 44.98 | 44.98
7.2 | Roadworks and Paving | m2 | 8000 | 202.95 | 1623600 |  | 0 | 45.04% | 731242.06 | 45.04% | 731242.06 | 0 | 3603.07 | 3603.07
7.3 | Kerbstone and Interlock | m2 | 7000 | 121.03 | 847210 |  | 0 | 23.11% | 195781.77 | 23.11% | 195781.77 | 0 | 1617.63 | 1617.63
7.4 | Landscaping | m3 | 1000 | 411.27 | 411270 |  | 0 | 43.61% | 179360.13 | 43.61% | 179360.13 | 0 | 436.11 | 436.11
7.5 | Boundary Wall | m3 | 1000 | 283.63 | 283630 |  | 0 | 38.55% | 109335.86 | 38.55% | 109335.86 | 0 | 385.49 | 385.49
8 | Final Works | LS | LS | - | 600578.25 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 213717.14 | 213717.14 |  | 0 | 33.07% | 70686.75 | 33.07% | 70686.75 | 0 | 0.33 | 0.33
8.2 | Snagging & De-snagging | LS | 1 | 97841.63 | 97841.63 |  | 0 | 24.10% | 23584.02 | 24.10% | 23584.02 | 0 | 0.24 | 0.24
8.3 | Cleaning | LS | 1 | 101502.83 | 101502.83 |  | 0 | 43.64% | 44299.64 | 43.64% | 44299.64 | 0 | 0.44 | 0.44
8.4 | Handover | LS | 1 | 136122.78 | 136122.78 |  | 0 | 17.66% | 24043.49 | 17.66% | 24043.49 | 0 | 0.18 | 0.18

## IPC_May_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 773417.84 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 54843.16 | 54843.16 | 42.19% | 23139.06 | 28.76% | 15773.07 | 70.95% | 38912.13 | 0.42 | 0.29 | 0.71
1.2 | Site Fencing and Hoarding | LS | 1 | 53695.36 | 53695.36 | 34.11% | 18317.51 | 12.49% | 6706.53 | 46.60% | 25024.04 | 0.34 | 0.12 | 0.46
1.3 | Temporary Facilities Setup | LS | 1 | 377370.59 | 377370.59 | 51.33% | 193689.78 | 11.05% | 41685.72 | 62.37% | 235375.5 | 0.51 | 0.11 | 0.62
1.4 | Soil Testing and Survey | LS | 1 | 183127.34 | 183127.34 | 12.42% | 22742.98 | 34.47% | 63119.6 | 46.89% | 85862.58 | 0.12 | 0.34 | 0.46
1.5 | Excavation | LS | 1 | 46731.03 | 46731.03 | 61.00% | 28508.05 | 9.32% | 4356.25 | 70.33% | 32864.3 | 0.61 | 0.09 | 0.7
1.6 | Dewatering | LS | 1 | 47993.57 | 47993.57 | 30.32% | 14551.63 | 19.37% | 9293.97 | 49.68% | 23845.6 | 0.3 | 0.19 | 0.49
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4476095.87 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 331.19 | 1655950 | 35.19% | 582804.65 | 23.90% | 395808.62 | 59.10% | 978613.27 | 1759.73 | 1195.11 | 2954.84
2.2 | Raft Foundation | m3 | 3500 | 264.93 | 927255 | 46.37% | 429978.14 | 21.13% | 195964.45 | 67.50% | 625942.59 | 1622.99 | 739.68 | 2362.67
2.3 | Basement Slab and Walls | m3 | 4000 | 354.15 | 1416600 | 37.49% | 531047.52 | 23.74% | 336299.78 | 61.23% | 867347.3 | 1499.5 | 949.6 | 2449.1
3 | Superstructure | LS | LS | - | 3330601.55 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 377.07 | 180993.6 | 26.34% | 47682.39 | 22.00% | 39814.79 | 48.34% | 87497.18 | 126.46 | 105.59 | 232.05
3.2 | Vertical Elements | m3 | 3600 | 213.55 | 768780 | 47.44% | 364679.36 | 11.62% | 89339.02 | 59.06% | 454018.38 | 1707.7 | 418.35 | 2126.05
3.3 | Floor Slabs | m3 | 6000 | 258.84 | 1553040 | 32.32% | 501865.47 | 19.30% | 299772.17 | 51.62% | 801637.64 | 1938.9 | 1158.14 | 3097.04
3.4 | Staircase Construction | m3 | 1000 | 287.58 | 287580 | 31.30% | 89999.67 | 14.86% | 42744.86 | 46.16% | 132744.53 | 312.96 | 148.64 | 461.6
3.5 | Lift Core Construction | m3 | 1000 | 211.96 | 211960 | 41.53% | 88017.96 | 25.43% | 53899.03 | 66.95% | 141916.99 | 415.26 | 254.29 | 669.55
3.6 | Roof Slab and Parapets | m3 | 360 | 245.47 | 88369.2 | 58.67% | 51843.24 | 10.39% | 9185.45 | 69.06% | 61028.69 | 211.2 | 37.42 | 248.62
4 | Masonry and Partitioning | LS | LS | - | 15187326 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 177.3 | 6205500 | 44.00% | 2730188.65 | 14.23% | 883022.05 | 58.23% | 3613210.7 | 15398.7 | 4980.38 | 20379.08
4.2 | Internal Blockwork | m2 | 35000 | 252.05 | 8821750 | 44.94% | 3964624.02 | 29.87% | 2635127.34 | 74.81% | 6599751.36 | 15729.51 | 10454.78 | 26184.29
4.3 | Drywall Partitioning | m3 | 1000 | 226.02 | 226020 | 53.67% | 121314.18 | 9.01% | 20361.22 | 62.68% | 141675.4 | 536.74 | 90.09 | 626.83
5 | MEP Works | LS | LS | - | 212003.41 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 49105.05 | 49105.05 | 25.26% | 12405.3 | 30.01% | 14737.43 | 55.27% | 27142.73 | 0.25 | 0.3 | 0.55
5.2 | Plumbing & Drainage | LS | 1 | 49195.06 | 49195.06 | 41.70% | 20515.8 | 13.07% | 6428.98 | 54.77% | 26944.78 | 0.42 | 0.13 | 0.55
5.3 | Firefighting Piping | LS | 1 | 49953.34 | 49953.34 | 42.83% | 21395.67 | 14.45% | 7220.51 | 57.29% | 28616.18 | 0.43 | 0.14 | 0.57
5.4 | HVAC Ducting | No. | 40 | 615.6 | 24624 | 40.97% | 10088.18 | 30.48% | 7504.5 | 71.45% | 17592.68 | 16.39 | 12.19 | 28.58
5.5 | Low Current Systems | LS | 1 | 45428.79 | 45428.79 | 42.77% | 19429.92 | 22.06% | 10022.6 | 64.83% | 29452.52 | 0.43 | 0.22 | 0.65
6 | Finishing Works | LS | LS | - | 16263061.82 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 54.66 | 1803780 | 49.14% | 886460.22 | 22.20% | 400515.4 | 71.35% | 1286975.62 | 16217.71 | 7327.39 | 23545.1
6.2 | Waterproofing | m2 | 5000 | 233.77 | 1168850 | 42.79% | 500099.42 | 7.89% | 92228.17 | 50.68% | 592327.59 | 2139.28 | 394.53 | 2533.81
6.3 | Tiling | m2 | 15000 | 238.93 | 3583950 | 41.91% | 1501889.2 | 23.80% | 853001.18 | 65.71% | 2354890.38 | 6285.9 | 3570.09 | 9855.99
6.4 | Painting | m2 | 40000 | 86.12 | 3444800 | 51.18% | 1763057.17 | 5.88% | 202441.49 | 57.06% | 1965498.66 | 20472.1 | 2350.69 | 22822.79
6.5 | Ceiling Works | m2 | 18000 | 151.22 | 2721960 | 30.51% | 830518.51 | 19.25% | 524075.32 | 49.77% | 1354593.83 | 5492.12 | 3465.65 | 8957.77
6.6 | Joinery Installation | No. | 400 | 757.15 | 302860 | 44.30% | 134170.06 | 18.65% | 56485.79 | 62.95% | 190655.85 | 177.2 | 74.6 | 251.8
6.7 | Door & Window Installation | No. | 800 | 1382.53 | 1106024 | 42.41% | 469081.06 | 16.42% | 181658.73 | 58.84% | 650739.79 | 339.29 | 131.4 | 470.69
6.8 | Glazing | m2 | 12000 | 80.65 | 967800 | 31.78% | 307520.05 | 16.94% | 163937.67 | 48.71% | 471457.72 | 3813.02 | 2032.71 | 5845.73
7 | External Works & Landscaping | LS | LS | - | 2974562.25 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 758.47 | 75847 | 31.20% | 23665.37 | 17.39% | 13189.06 | 48.59% | 36854.43 | 31.2 | 17.39 | 48.59
7.2 | Roadworks and Paving | m2 | 8000 | 208.23 | 1665840 | 21.11% | 351652.73 | 26.68% | 444430.31 | 47.79% | 796083.04 | 1688.77 | 2134.32 | 3823.09
7.3 | Kerbstone and Interlock | m2 | 7000 | 109.94 | 769580 | 21.89% | 168460.61 | 30.74% | 236606.2 | 52.63% | 405066.81 | 1532.3 | 2152.14 | 3684.44
7.4 | Landscaping | m3 | 1000 | 354.28 | 354280 | 28.33% | 100369.25 | 27.02% | 95732.13 | 55.35% | 196101.38 | 283.3 | 270.22 | 553.52
7.5 | Boundary Wall | m3 | 1000 | 256.49 | 256490 | 19.70% | 50519.75 | 26.36% | 67614.09 | 46.06% | 118133.84 | 196.97 | 263.61 | 460.58
8 | Final Works | LS | LS | - | 528525.26 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 185791.92 | 185791.92 | 38.90% | 72277.05 | 21.03% | 39076.29 | 59.93% | 111353.34 | 0.39 | 0.21 | 0.6
8.2 | Snagging & De-snagging | LS | 1 | 93499.6 | 93499.6 | 40.65% | 38004.9 | 16.80% | 15712.61 | 57.45% | 53717.51 | 0.41 | 0.17 | 0.58
8.3 | Cleaning | LS | 1 | 92697.59 | 92697.59 | 20.29% | 18806.27 | 32.75% | 30357.15 | 53.04% | 49163.42 | 0.2 | 0.33 | 0.53
8.4 | Handover | LS | 1 | 136381.26 | 136381.26 | 26.84% | 36604.14 | 31.63% | 43138.57 | 58.47% | 79742.71 | 0.27 | 0.32 | 0.59

## IPC_Jun_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 750499.46 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 46351.57 | 46351.57 | 34.57% | 16023.1 | 29.28% | 13571.65 | 63.85% | 29594.75 | 0.35 | 0.29 | 0.64
1.2 | Site Fencing and Hoarding | LS | 1 | 50634.01 | 50634.01 | 58.62% | 29682.95 | 5.12% | 2593.46 | 63.74% | 32276.41 | 0.59 | 0.05 | 0.64
1.3 | Temporary Facilities Setup | LS | 1 | 422349.54 | 422349.54 | 44.51% | 187969.01 | 32.67% | 138000 | 77.18% | 325969.01 | 0.45 | 0.33 | 0.78
1.4 | Soil Testing and Survey | LS | 1 | 203729.63 | 203729.63 | 56.39% | 114876.34 | 22.23% | 45294.96 | 78.62% | 160171.3 | 0.56 | 0.22 | 0.78
1.5 | Excavation | LS | 1 | 47359.54 | 47359.54 | 48.39% | 22919.32 | 12.23% | 5791.51 | 60.62% | 28710.83 | 0.48 | 0.12 | 0.6
1.6 | Dewatering | LS | 1 | 49532.47 | 49532.47 | 42.62% | 21113.2 | 24.53% | 12148.51 | 67.15% | 33261.71 | 0.43 | 0.25 | 0.68
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4236165.81 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 375.73 | 1878650 | 43.62% | 819549.18 | 10.78% | 202591.52 | 54.41% | 1022140.7 | 2181.22 | 539.19 | 2720.41
2.2 | Raft Foundation | m3 | 3500 | 264.92 | 927220 | 30.40% | 281846.89 | 29.08% | 269671.81 | 59.48% | 551518.7 | 1063.89 | 1017.94 | 2081.83
2.3 | Basement Slab and Walls | m3 | 4000 | 374.81 | 1499240 | 32.78% | 491413.78 | 27.95% | 419036.13 | 60.73% | 910449.91 | 1311.1 | 1118 | 2429.1
3 | Superstructure | LS | LS | - | 3499141.12 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 377.05 | 180984 | 64.37% | 116499.64 | 8.62% | 15609.05 | 72.99% | 132108.69 | 308.98 | 41.4 | 350.38
3.2 | Vertical Elements | m3 | 3600 | 222.48 | 800928 | 51.65% | 413669.91 | 11.67% | 93468.14 | 63.32% | 507138.05 | 1859.36 | 420.12 | 2279.48
3.3 | Floor Slabs | m3 | 6000 | 289.19 | 1735140 | 37.14% | 644415.95 | 31.07% | 539101.46 | 68.21% | 1183517.41 | 2228.35 | 1864.18 | 4092.53
3.4 | Staircase Construction | m3 | 1000 | 277.25 | 277250 | 43.92% | 121773.32 | 34.33% | 95181.17 | 78.25% | 216954.49 | 439.22 | 343.3 | 782.52
3.5 | Lift Core Construction | m3 | 1000 | 197.02 | 197020 | 47.00% | 92597.34 | 12.14% | 23927.65 | 59.14% | 116524.99 | 469.99 | 121.45 | 591.44
3.6 | Roof Slab and Parapets | m3 | 360 | 235.82 | 84895.2 | 48.41% | 41098.98 | 33.98% | 28848.01 | 82.39% | 69946.99 | 174.28 | 122.33 | 296.61
4 | Masonry and Partitioning | LS | LS | - | 13540963.52 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 177.97 | 6228950 | 45.57% | 2838283.44 | 9.64% | 600532.9 | 55.21% | 3438816.34 | 15948.1 | 3374.35 | 19322.45
4.2 | Internal Blockwork | m2 | 35000 | 238.66 | 8353100 | 56.48% | 4717887.51 | 20.69% | 1728019.14 | 77.17% | 6445906.65 | 19768.24 | 7240.51 | 27008.75
4.3 | Drywall Partitioning | m3 | 1000 | 246.49 | 246490 | 53.92% | 132919.57 | 8.45% | 20821.02 | 62.37% | 153740.59 | 539.25 | 84.47 | 623.72
5 | MEP Works | LS | LS | - | 232825.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 47492.32 | 47492.32 | 49.55% | 23533.11 | 20.15% | 9569.15 | 69.70% | 33102.26 | 0.5 | 0.2 | 0.7
5.2 | Plumbing & Drainage | LS | 1 | 48700.33 | 48700.33 | 42.66% | 20777.59 | 10.76% | 5242.12 | 53.43% | 26019.71 | 0.43 | 0.11 | 0.54
5.3 | Firefighting Piping | LS | 1 | 50206.63 | 50206.63 | 59.84% | 30043.87 | 17.73% | 8903.91 | 77.57% | 38947.78 | 0.6 | 0.18 | 0.78
5.4 | HVAC Ducting | No. | 40 | 629.58 | 25183.2 | 44.99% | 11331 | 24.16% | 6084.91 | 69.16% | 17415.91 | 18 | 9.67 | 27.67
5.5 | Low Current Systems | LS | 1 | 47676.97 | 47676.97 | 32.97% | 15720.39 | 27.33% | 13030.51 | 60.30% | 28750.9 | 0.33 | 0.27 | 0.6
6 | Finishing Works | LS | LS | - | 14075147.8 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 59.7 | 1970100 | 61.14% | 1204449.33 | 14.16% | 279062.3 | 75.30% | 1483511.63 | 20175.03 | 4674.41 | 24849.44
6.2 | Waterproofing | m2 | 5000 | 241.09 | 1205450 | 47.38% | 571194.93 | 22.49% | 271102.72 | 69.87% | 842297.65 | 2369.22 | 1124.49 | 3493.71
6.3 | Tiling | m2 | 15000 | 251.69 | 3775350 | 55.21% | 2084218.47 | 11.20% | 422908.32 | 66.41% | 2507126.79 | 8280.9 | 1680.27 | 9961.17
6.4 | Painting | m2 | 40000 | 79.7 | 3188000 | 45.12% | 1438573.74 | 10.81% | 344606.57 | 55.93% | 1783180.31 | 18049.86 | 4323.8 | 22373.66
6.5 | Ceiling Works | m2 | 18000 | 139.35 | 2508300 | 41.43% | 1039291.3 | 13.05% | 327364.51 | 54.49% | 1366655.81 | 7458.14 | 2349.23 | 9807.37
6.6 | Joinery Installation | No. | 400 | 828.09 | 331236 | 36.78% | 121837.48 | 33.24% | 110087.94 | 70.02% | 231925.42 | 147.13 | 132.94 | 280.07
6.7 | Door & Window Installation | No. | 800 | 1397.4 | 1117920 | 39.48% | 441368.76 | 24.73% | 276407.32 | 64.21% | 717776.08 | 315.85 | 197.8 | 513.65
6.8 | Glazing | m2 | 12000 | 83.42 | 1001040 | 46.94% | 469838.16 | 30.28% | 303065.73 | 77.21% | 772903.89 | 5632.2 | 3633.01 | 9265.21
7 | External Works & Landscaping | LS | LS | - | 3454898.49 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 823.73 | 82373 | 48.52% | 39970.56 | 16.17% | 13321.5 | 64.70% | 53292.06 | 48.52 | 16.17 | 64.69
7.2 | Roadworks and Paving | m2 | 8000 | 199.94 | 1599520 | 62.71% | 1003135.29 | 19.73% | 315514.44 | 82.44% | 1318649.73 | 5017.18 | 1578.05 | 6595.23
7.3 | Kerbstone and Interlock | m2 | 7000 | 108.75 | 761250 | 66.36% | 505169.6 | 10.33% | 78599.84 | 76.69% | 583769.44 | 4645.24 | 722.76 | 5368
7.4 | Landscaping | m3 | 1000 | 405.1 | 405100 | 54.86% | 222247.97 | 6.66% | 26979.38 | 61.52% | 249227.35 | 548.62 | 66.6 | 615.22
7.5 | Boundary Wall | m3 | 1000 | 282.89 | 282890 | 49.33% | 139550.6 | 32.75% | 92645.13 | 82.08% | 232195.73 | 493.3 | 327.5 | 820.8
8 | Final Works | LS | LS | - | 586606.7 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 184659.98 | 184659.98 | 47.00% | 86793.8 | 15.79% | 29153.97 | 62.79% | 115947.77 | 0.47 | 0.16 | 0.63
8.2 | Snagging & De-snagging | LS | 1 | 90904.98 | 90904.98 | 38.11% | 34648.18 | 29.56% | 26870.3 | 67.67% | 61518.48 | 0.38 | 0.3 | 0.68
8.3 | Cleaning | LS | 1 | 100424.88 | 100424.88 | 33.48% | 33617.68 | 32.64% | 32781 | 66.12% | 66398.68 | 0.33 | 0.33 | 0.66
8.4 | Handover | LS | 1 | 161196.05 | 161196.05 | 60.01% | 96727.67 | 15.51% | 25009.28 | 75.52% | 121736.95 | 0.6 | 0.16 | 0.76

## IPC_Jul_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 771978.47 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 53986.1 | 53986.1 | 69.44% | 37490.33 | 10.32% | 5573.05 | 79.77% | 43063.38 | 0.69 | 0.1 | 0.79
1.2 | Site Fencing and Hoarding | LS | 1 | 54035.43 | 54035.43 | 60.04% | 32444.88 | 6.81% | 3678.89 | 66.85% | 36123.77 | 0.6 | 0.07 | 0.67
1.3 | Temporary Facilities Setup | LS | 1 | 416939.88 | 416939.88 | 34.86% | 145330.11 | 28.81% | 120128.61 | 63.67% | 265458.72 | 0.35 | 0.29 | 0.64
1.4 | Soil Testing and Survey | LS | 1 | 193631.53 | 193631.53 | 56.00% | 108429.82 | 19.22% | 37223.08 | 75.22% | 145652.9 | 0.56 | 0.19 | 0.75
1.5 | Excavation | LS | 1 | 48611.84 | 48611.84 | 79.81% | 38795.48 | 5.25% | 2552.71 | 85.06% | 41348.19 | 0.8 | 0.05 | 0.85
1.6 | Dewatering | LS | 1 | 53281.35 | 53281.35 | 34.48% | 18373.96 | 29.85% | 15903.53 | 64.33% | 34277.49 | 0.34 | 0.3 | 0.64
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4297773.44 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 373.94 | 1869700 | 79.70% | 1490187.46 | 8.42% | 157444.85 | 88.12% | 1647632.31 | 3985.1 | 421.04 | 4406.14
2.2 | Raft Foundation | m3 | 3500 | 264.72 | 926520 | 37.41% | 346605.19 | 28.54% | 264453.26 | 65.95% | 611058.45 | 1309.33 | 998.99 | 2308.32
2.3 | Basement Slab and Walls | m3 | 4000 | 404.71 | 1618840 | 52.46% | 849184.02 | 25.61% | 414567.55 | 78.07% | 1263751.57 | 2098.25 | 1024.36 | 3122.61
3 | Superstructure | LS | LS | - | 3551188.21 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 394.59 | 189403.2 | 70.17% | 132910.79 | 9.44% | 17880.48 | 79.61% | 150791.27 | 336.83 | 45.31 | 382.14
3.2 | Vertical Elements | m3 | 3600 | 206.09 | 741924 | 39.29% | 291486.14 | 26.00% | 192869.21 | 65.28% | 484355.35 | 1414.36 | 935.85 | 2350.21
3.3 | Floor Slabs | m3 | 6000 | 282.44 | 1694640 | 36.14% | 612474.02 | 31.84% | 539596.09 | 67.98% | 1152070.11 | 2168.51 | 1910.48 | 4078.99
3.4 | Staircase Construction | m3 | 1000 | 288.77 | 288770 | 57.20% | 165176.34 | 12.73% | 36749.56 | 69.93% | 201925.9 | 572 | 127.26 | 699.26
3.5 | Lift Core Construction | m3 | 1000 | 194.79 | 194790 | 62.96% | 122649.25 | 14.92% | 29070.16 | 77.89% | 151719.41 | 629.65 | 149.24 | 778.89
3.6 | Roof Slab and Parapets | m3 | 360 | 264.98 | 95392.8 | 36.13% | 34469.53 | 32.80% | 31293.35 | 68.94% | 65762.88 | 130.08 | 118.1 | 248.18
4 | Masonry and Partitioning | LS | LS | - | 15563807.82 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 158.99 | 5564650 | 43.41% | 2415355.9 | 34.64% | 1927407.39 | 78.04% | 4342763.29 | 15191.87 | 12122.82 | 27314.69
4.2 | Internal Blockwork | m2 | 35000 | 225.05 | 7876750 | 45.24% | 3563471.76 | 26.11% | 2056842.28 | 71.35% | 5620314.04 | 15834.13 | 9139.49 | 24973.62
4.3 | Drywall Partitioning | m3 | 1000 | 250.25 | 250250 | 65.30% | 163419.22 | 12.48% | 31236.08 | 77.78% | 194655.3 | 653.02 | 124.82 | 777.84
5 | MEP Works | LS | LS | - | 220632.13 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 49091.76 | 49091.76 | 44.02% | 21610.16 | 29.17% | 14318.78 | 73.19% | 35928.94 | 0.44 | 0.29 | 0.73
5.2 | Plumbing & Drainage | LS | 1 | 45443.86 | 45443.86 | 55.50% | 25221.03 | 15.87% | 7211.36 | 71.37% | 32432.39 | 0.55 | 0.16 | 0.71
5.3 | Firefighting Piping | LS | 1 | 47123.04 | 47123.04 | 43.63% | 20558.57 | 20.24% | 9539.11 | 63.87% | 30097.68 | 0.44 | 0.2 | 0.64
5.4 | HVAC Ducting | No. | 40 | 617.31 | 24692.4 | 28.27% | 6979.73 | 32.83% | 8106.95 | 61.10% | 15086.68 | 11.31 | 13.13 | 24.44
5.5 | Low Current Systems | LS | 1 | 50029.71 | 50029.71 | 67.16% | 33598.6 | 17.38% | 8697.02 | 84.54% | 42295.62 | 0.67 | 0.17 | 0.84
6 | Finishing Works | LS | LS | - | 15939645.26 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 59.15 | 1951950 | 65.92% | 1286800.24 | 9.83% | 191841.34 | 75.75% | 1478641.58 | 21754.86 | 3243.3 | 24998.16
6.2 | Waterproofing | m2 | 5000 | 243.56 | 1217800 | 43.66% | 531669.59 | 25.43% | 309664.32 | 69.09% | 841333.91 | 2182.91 | 1271.41 | 3454.32
6.3 | Tiling | m2 | 15000 | 237.88 | 3568200 | 53.68% | 1915430.59 | 32.30% | 1152689.53 | 85.99% | 3068120.12 | 8052.09 | 4845.68 | 12897.77
6.4 | Painting | m2 | 40000 | 85.64 | 3425600 | 57.58% | 1972335.31 | 12.86% | 440488.56 | 70.44% | 2412823.87 | 23030.54 | 5143.49 | 28174.03
6.5 | Ceiling Works | m2 | 18000 | 148.04 | 2664720 | 33.45% | 891433.56 | 32.34% | 861838.7 | 65.80% | 1753272.26 | 6021.57 | 5821.66 | 11843.23
6.6 | Joinery Installation | No. | 400 | 765.89 | 306356 | 49.93% | 152949.24 | 17.89% | 54808.32 | 67.82% | 207757.56 | 199.7 | 71.56 | 271.26
6.7 | Door & Window Installation | No. | 800 | 1532.72 | 1226176 | 51.05% | 625970.19 | 15.19% | 186238.91 | 66.24% | 812209.1 | 408.4 | 121.51 | 529.91
6.8 | Glazing | m2 | 12000 | 85.06 | 1020720 | 48.93% | 499419.31 | 12.30% | 125548.69 | 61.23% | 624968 | 5871.38 | 1476 | 7347.38
7 | External Works & Landscaping | LS | LS | - | 3189507.07 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 793.77 | 79377 | 44.61% | 35406.49 | 27.83% | 22093.37 | 72.44% | 57499.86 | 44.61 | 27.83 | 72.44
7.2 | Roadworks and Paving | m2 | 8000 | 215.95 | 1727600 | 56.68% | 979203.67 | 7.24% | 125112.2 | 63.92% | 1104315.87 | 4534.4 | 579.36 | 5113.76
7.3 | Kerbstone and Interlock | m2 | 7000 | 103.03 | 721210 | 53.50% | 385835.69 | 18.74% | 135119.28 | 72.23% | 520954.97 | 3744.89 | 1311.46 | 5056.35
7.4 | Landscaping | m3 | 1000 | 387.59 | 387590 | 34.44% | 133470.6 | 29.68% | 115049.54 | 64.12% | 248520.14 | 344.36 | 296.83 | 641.19
7.5 | Boundary Wall | m3 | 1000 | 298.2 | 298200 | 53.56% | 159709.31 | 23.64% | 70483.35 | 77.19% | 230192.66 | 535.58 | 236.36 | 771.94
8 | Final Works | LS | LS | - | 523024.52 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 183441.55 | 183441.55 | 55.23% | 101309.96 | 5.21% | 9548.54 | 60.43% | 110858.5 | 0.55 | 0.05 | 0.6
8.2 | Snagging & De-snagging | LS | 1 | 93657.74 | 93657.74 | 43.79% | 41009.89 | 23.56% | 22069.08 | 67.35% | 63078.97 | 0.44 | 0.24 | 0.68
8.3 | Cleaning | LS | 1 | 102037.83 | 102037.83 | 62.84% | 64120.33 | 27.20% | 27755.04 | 90.04% | 91875.37 | 0.63 | 0.27 | 0.9
8.4 | Handover | LS | 1 | 140081.74 | 140081.74 | 56.03% | 78483.7 | 14.99% | 20999.09 | 71.02% | 99482.79 | 0.56 | 0.15 | 0.71