## IPC_Jul_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 867472.57 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 45305.14 | 45305.14 |  | 0 | 26.75% | 12117.59 | 26.75% | 12117.59 | 0 | 0.27 | 0.27
1.2 | Site Fencing and Hoarding | LS | 1 | 50773.56 | 50773.56 |  | 0 | 28.13% | 14280.46 | 28.13% | 14280.46 | 0 | 0.28 | 0.28
1.3 | Temporary Facilities Setup | LS | 1 | 435408.53 | 435408.53 |  | 0 | 27.65% | 120384.73 | 27.65% | 120384.73 | 0 | 0.28 | 0.28
1.4 | Soil Testing and Survey | LS | 1 | 192135.32 | 192135.32 |  | 0 | 28.36% | 54487.77 | 28.36% | 54487.77 | 0 | 0.28 | 0.28
1.5 | Excavation | LS | 1 | 48314.21 | 48314.21 |  | 0 | 29.51% | 14255.22 | 29.51% | 14255.22 | 0 | 0.3 | 0.3
1.6 | Dewatering | LS | 1 | 46768.57 | 46768.57 |  | 0 | 40.22% | 18810.65 | 40.22% | 18810.65 | 0 | 0.4 | 0.4
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4172212.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 335.42 | 1677100 |  | 0 | 29.40% | 493075.27 | 29.40% | 493075.27 | 0 | 1470.02 | 1470.02
2.2 | Raft Foundation | m3 | 3500 | 237.77 | 832195 |  | 0 | 29.99% | 249567.17 | 29.99% | 249567.17 | 0 | 1049.62 | 1049.62
2.3 | Basement Slab and Walls | m3 | 4000 | 379.59 | 1518360 |  | 0 | 24.12% | 366212.03 | 24.12% | 366212.03 | 0 | 964.76 | 964.76
3 | Superstructure | LS | LS | - | 2973327.91 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 356.18 | 170966.4 |  | 0 | 15.03% | 25690.17 | 15.03% | 25690.17 | 0 | 72.13 | 72.13
3.2 | Vertical Elements | m3 | 3600 | 211.06 | 759816 |  | 0 | 22.87% | 173740.4 | 22.87% | 173740.4 | 0 | 823.18 | 823.18
3.3 | Floor Slabs | m3 | 6000 | 301.55 | 1809300 |  | 0 | 21.11% | 381919.77 | 21.11% | 381919.77 | 0 | 1266.52 | 1266.52
3.4 | Staircase Construction | m3 | 1000 | 307.46 | 307460 |  | 0 | 16.54% | 50868.4 | 16.54% | 50868.4 | 0 | 165.45 | 165.45
3.5 | Lift Core Construction | m3 | 1000 | 230.82 | 230820 |  | 0 | 19.39% | 44750.12 | 19.39% | 44750.12 | 0 | 193.87 | 193.87
3.6 | Roof Slab and Parapets | m3 | 360 | 243.52 | 87667.2 |  | 0 | 16.51% | 14477.28 | 16.51% | 14477.28 | 0 | 59.45 | 59.45
4 | Masonry and Partitioning | LS | LS | - | 15384123.87 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 160.92 | 5632200 |  | 0 | 15.85% | 892645.57 | 15.85% | 892645.57 | 0 | 5547.14 | 5547.14
4.2 | Internal Blockwork | m2 | 35000 | 240.66 | 8423100 |  | 0 | 37.53% | 3161361.91 | 37.53% | 3161361.91 | 0 | 13136.22 | 13136.22
4.3 | Drywall Partitioning | m3 | 1000 | 248.75 | 248750 |  | 0 | 27.14% | 67514.41 | 27.14% | 67514.41 | 0 | 271.41 | 271.41
5 | MEP Works | LS | LS | - | 216144.92 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 45030.11 | 45030.11 |  | 0 | 40.17% | 18089.62 | 40.17% | 18089.62 | 0 | 0.4 | 0.4
5.2 | Plumbing & Drainage | LS | 1 | 45672.82 | 45672.82 |  | 0 | 13.69% | 6250.99 | 13.69% | 6250.99 | 0 | 0.14 | 0.14
5.3 | Firefighting Piping | LS | 1 | 52026.79 | 52026.79 |  | 0 | 24.90% | 12956.09 | 24.90% | 12956.09 | 0 | 0.25 | 0.25
5.4 | HVAC Ducting | No. | 40 | 641.32 | 25652.8 |  | 0 | 24.15% | 6194.78 | 24.15% | 6194.78 | 0 | 9.66 | 9.66
5.5 | Low Current Systems | LS | 1 | 50859.79 | 50859.79 |  | 0 | 32.70% | 16630.73 | 32.70% | 16630.73 | 0 | 0.33 | 0.33
6 | Finishing Works | LS | LS | - | 15516910.23 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 57.86 | 1909380 |  | 0 | 15.08% | 287976.8 | 15.08% | 287976.8 | 0 | 4977.13 | 4977.13
6.2 | Waterproofing | m2 | 5000 | 220.45 | 1102250 |  | 0 | 14.08% | 155233.34 | 14.08% | 155233.34 | 0 | 704.17 | 704.17
6.3 | Tiling | m2 | 15000 | 242.05 | 3630750 |  | 0 | 13.18% | 478397.41 | 13.18% | 478397.41 | 0 | 1976.44 | 1976.44
6.4 | Painting | m2 | 40000 | 82.23 | 3289200 |  | 0 | 15.03% | 494333.11 | 15.03% | 494333.11 | 0 | 6011.59 | 6011.59
6.5 | Ceiling Works | m2 | 18000 | 149.44 | 2689920 |  | 0 | 37.52% | 1009285.08 | 37.52% | 1009285.08 | 0 | 6753.78 | 6753.78
6.6 | Joinery Installation | No. | 400 | 740.94 | 296376 |  | 0 | 36.77% | 108989.44 | 36.77% | 108989.44 | 0 | 147.1 | 147.1
6.7 | Door & Window Installation | No. | 800 | 1429.51 | 1143608 |  | 0 | 33.42% | 382197.95 | 33.42% | 382197.95 | 0 | 267.36 | 267.36
6.8 | Glazing | m2 | 12000 | 74.07 | 888840 |  | 0 | 36.23% | 322017.61 | 36.23% | 322017.61 | 0 | 4347.48 | 4347.48
7 | External Works & Landscaping | LS | LS | - | 2932876.21 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 904.58 | 90458 |  | 0 | 38.25% | 34602.77 | 38.25% | 34602.77 | 0 | 38.25 | 38.25
7.2 | Roadworks and Paving | m2 | 8000 | 193.43 | 1547440 |  | 0 | 40.73% | 630292.25 | 40.73% | 630292.25 | 0 | 3258.5 | 3258.5
7.3 | Kerbstone and Interlock | m2 | 7000 | 122.28 | 855960 |  | 0 | 20.36% | 174271.17 | 20.36% | 174271.17 | 0 | 1425.18 | 1425.18
7.4 | Landscaping | m3 | 1000 | 362.47 | 362470 |  | 0 | 23.05% | 83553.08 | 23.05% | 83553.08 | 0 | 230.51 | 230.51
7.5 | Boundary Wall | m3 | 1000 | 256.32 | 256320 |  | 0 | 36.78% | 94268.25 | 36.78% | 94268.25 | 0 | 367.78 | 367.78
8 | Final Works | LS | LS | - | 596672.59 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 215213.55 | 215213.55 |  | 0 | 37.24% | 80148.44 | 37.24% | 80148.44 | 0 | 0.37 | 0.37
8.2 | Snagging & De-snagging | LS | 1 | 93040.75 | 93040.75 |  | 0 | 16.36% | 15220.49 | 16.36% | 15220.49 | 0 | 0.16 | 0.16
8.3 | Cleaning | LS | 1 | 90888.78 | 90888.78 |  | 0 | 12.86% | 11691.41 | 12.86% | 11691.41 | 0 | 0.13 | 0.13
8.4 | Handover | LS | 1 | 163435.91 | 163435.91 |  | 0 | 35.14% | 57437.98 | 35.14% | 57437.98 | 0 | 0.35 | 0.35

## IPC_Aug_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 795121.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 52141.6 | 52141.6 | 25.71% | 13407.14 | 9.79% | 5106.86 | 35.51% | 18514 | 0.26 | 0.1 | 0.36
1.2 | Site Fencing and Hoarding | LS | 1 | 46393.47 | 46393.47 | 11.67% | 5412.71 | 24.21% | 11230.23 | 35.87% | 16642.94 | 0.12 | 0.24 | 0.36
1.3 | Temporary Facilities Setup | LS | 1 | 428690.35 | 428690.35 | 10.96% | 46995.76 | 30.04% | 128772.59 | 41.00% | 175768.35 | 0.11 | 0.3 | 0.41
1.4 | Soil Testing and Survey | LS | 1 | 181422.25 | 181422.25 | 32.08% | 58207.3 | 8.18% | 14833.54 | 40.26% | 73040.84 | 0.32 | 0.08 | 0.4
1.5 | Excavation | LS | 1 | 54545.27 | 54545.27 | 18.46% | 10068.63 | 13.51% | 7370.5 | 31.97% | 17439.13 | 0.18 | 0.14 | 0.32
1.6 | Dewatering | LS | 1 | 48087.5 | 48087.5 | 7.23% | 3476.79 | 14.31% | 6881.09 | 21.54% | 10357.88 | 0.07 | 0.14 | 0.21
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3983590.51 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 373.88 | 1869400 | 25.52% | 477006.02 | 12.50% | 233586.95 | 38.01% | 710592.97 | 1275.83 | 624.76 | 1900.59
2.2 | Raft Foundation | m3 | 3500 | 244.28 | 854980 | 27.58% | 235839.81 | 8.67% | 74157.64 | 36.26% | 309997.45 | 965.45 | 303.58 | 1269.03
2.3 | Basement Slab and Walls | m3 | 4000 | 392.8 | 1571200 |  | 0 | 21.12% | 331886.6 | 21.12% | 331886.6 | 0 | 844.93 | 844.93
3 | Superstructure | LS | LS | - | 2972002.62 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 407.51 | 195604.8 | 24.77% | 48449.56 | 10.39% | 20326.92 | 35.16% | 68776.48 | 118.89 | 49.88 | 168.77
3.2 | Vertical Elements | m3 | 3600 | 211.31 | 760716 | 36.88% | 280562.08 | 11.52% | 87657.61 | 48.40% | 368219.69 | 1327.73 | 414.83 | 1742.56
3.3 | Floor Slabs | m3 | 6000 | 297.3 | 1783800 |  | 0 | 22.18% | 395612.46 | 22.18% | 395612.46 | 0 | 1330.68 | 1330.68
3.4 | Staircase Construction | m3 | 1000 | 304.79 | 304790 | 30.68% | 93514.23 | 13.52% | 41203.83 | 44.20% | 134718.06 | 306.82 | 135.19 | 442.01
3.5 | Lift Core Construction | m3 | 1000 | 203.5 | 203500 | 12.66% | 25764.39 | 10.10% | 20547.64 | 22.76% | 46312.03 | 126.61 | 100.97 | 227.58
3.6 | Roof Slab and Parapets | m3 | 360 | 261.59 | 94172.4 | 31.83% | 29978.28 | 7.68% | 7229.73 | 39.51% | 37208.01 | 114.6 | 27.64 | 142.24
4 | Masonry and Partitioning | LS | LS | - | 14153704.56 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 178.91 | 6261850 | 23.55% | 1474686.83 | 20.56% | 1287239.33 | 44.11% | 2761926.16 | 8242.62 | 7194.9 | 15437.52
4.2 | Internal Blockwork | m2 | 35000 | 213.76 | 7481600 | 35.69% | 2670024.73 | 10.84% | 811142.4 | 46.53% | 3481167.13 | 12490.76 | 3794.64 | 16285.4
4.3 | Drywall Partitioning | m3 | 1000 | 230.86 | 230860 | 24.85% | 57361.23 | 24.07% | 55557.9 | 48.91% | 112919.13 | 248.47 | 240.66 | 489.13
5 | MEP Works | LS | LS | - | 222315.22 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 45501.01 | 45501.01 |  | 0 | 23.62% | 10749.24 | 23.62% | 10749.24 | 0 | 0.24 | 0.24
5.2 | Plumbing & Drainage | LS | 1 | 54144.34 | 54144.34 | 34.29% | 18568.06 | 8.10% | 4387.23 | 42.40% | 22955.29 | 0.34 | 0.08 | 0.42
5.3 | Firefighting Piping | LS | 1 | 52102.77 | 52102.77 | 25.80% | 13442.59 | 18.55% | 9666.98 | 44.35% | 23109.57 | 0.26 | 0.19 | 0.45
5.4 | HVAC Ducting | No. | 40 | 601.97 | 24078.8 | 7.57% | 1822.93 | 12.97% | 3124.17 | 20.55% | 4947.1 | 3.03 | 5.19 | 8.22
5.5 | Low Current Systems | LS | 1 | 46942.61 | 46942.61 | 25.99% | 12201.78 | 5.77% | 2710.82 | 31.77% | 14912.6 | 0.26 | 0.06 | 0.32
6 | Finishing Works | LS | LS | - | 16386450.68 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 50.08 | 1652640 | 19.60% | 323995.57 | 27.78% | 459155.9 | 47.39% | 783151.47 | 6469.56 | 9168.45 | 15638.01
6.2 | Waterproofing | m2 | 5000 | 236.42 | 1182100 | 43.04% | 508787.5 | 5.41% | 64009.27 | 48.46% | 572796.77 | 2152.05 | 270.74 | 2422.79
6.3 | Tiling | m2 | 15000 | 229.69 | 3445350 | 8.21% | 282986.82 | 25.83% | 889940.7 | 34.04% | 1172927.52 | 1232.04 | 3874.53 | 5106.57
6.4 | Painting | m2 | 40000 | 93.26 | 3730400 | 22.79% | 850108.63 | 5.23% | 194932.65 | 28.01% | 1045041.28 | 9115.47 | 2090.21 | 11205.68
6.5 | Ceiling Works | m2 | 18000 | 149.23 | 2686140 | 1.50% | 40238.38 | 27.91% | 749693.47 | 29.41% | 789931.85 | 269.64 | 5023.75 | 5293.39
6.6 | Joinery Installation | No. | 400 | 882.04 | 352816 | 20.01% | 70613.66 | 12.81% | 45186.71 | 32.82% | 115800.37 | 80.06 | 51.23 | 131.29
6.7 | Door & Window Installation | No. | 800 | 1526.37 | 1221096 | 2.98% | 36350.08 | 25.91% | 316360.86 | 28.88% | 352710.94 | 23.81 | 207.26 | 231.07
6.8 | Glazing | m2 | 12000 | 80.4 | 964800 |  | 0 | 26.13% | 252120.8 | 26.13% | 252120.8 | 0 | 3135.83 | 3135.83
7 | External Works & Landscaping | LS | LS | - | 3512449.24 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 771.06 | 77106 | 20.17% | 15553.13 | 25.41% | 19590.67 | 45.58% | 35143.8 | 20.17 | 25.41 | 45.58
7.2 | Roadworks and Paving | m2 | 8000 | 195.26 | 1562080 | 13.98% | 218340.61 | 30.53% | 476879.42 | 44.51% | 695220.03 | 1118.2 | 2442.28 | 3560.48
7.3 | Kerbstone and Interlock | m2 | 7000 | 109.5 | 766500 | 36.21% | 277577.04 | 12.40% | 95076.49 | 48.62% | 372653.53 | 2534.95 | 868.28 | 3403.23
7.4 | Landscaping | m3 | 1000 | 358.99 | 358990 | 18.14% | 65116.25 | 26.53% | 95224.17 | 44.66% | 160340.42 | 181.39 | 265.26 | 446.65
7.5 | Boundary Wall | m3 | 1000 | 285.14 | 285140 | 24.96% | 71175.79 | 11.16% | 31821.42 | 36.12% | 102997.21 | 249.62 | 111.6 | 361.22
8 | Final Works | LS | LS | - | 520496.55 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 207391.84 | 207391.84 | 11.57% | 23987.89 | 19.53% | 40510.56 | 31.10% | 64498.45 | 0.12 | 0.2 | 0.32
8.2 | Snagging & De-snagging | LS | 1 | 93697.02 | 93697.02 | 41.29% | 38690.92 | 5.71% | 5348.44 | 47.00% | 44039.36 | 0.41 | 0.06 | 0.47
8.3 | Cleaning | LS | 1 | 104859.6 | 104859.6 | 13.00% | 13628.52 | 26.25% | 27521.42 | 39.24% | 41149.94 | 0.13 | 0.26 | 0.39
8.4 | Handover | LS | 1 | 142874.42 | 142874.42 | 0.08% | 112.98 | 23.18% | 33118.43 | 23.26% | 33231.41 | 0 | 0.23 | 0.23

## IPC_Sep_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 762752.71 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 54747.49 | 54747.49 | 39.41% | 21578.27 | 19.88% | 10882.22 | 59.29% | 32460.49 | 0.39 | 0.2 | 0.59
1.2 | Site Fencing and Hoarding | LS | 1 | 51527.95 | 51527.95 | 42.30% | 21795.37 | 17.55% | 9043.17 | 59.85% | 30838.54 | 0.42 | 0.18 | 0.6
1.3 | Temporary Facilities Setup | LS | 1 | 418639.95 | 418639.95 | 47.18% | 197503.77 | 26.88% | 112527.17 | 74.06% | 310030.94 | 0.47 | 0.27 | 0.74
1.4 | Soil Testing and Survey | LS | 1 | 195519.09 | 195519.09 | 45.89% | 89723.52 | 16.65% | 32551.19 | 62.54% | 122274.71 | 0.46 | 0.17 | 0.63
1.5 | Excavation | LS | 1 | 52643.74 | 52643.74 | 72.01% | 37906.49 | 5.95% | 3134.83 | 77.96% | 41041.32 | 0.72 | 0.06 | 0.78
1.6 | Dewatering | LS | 1 | 47668.36 | 47668.36 | 58.45% | 27864.16 | 17.37% | 8278.86 | 75.82% | 36143.02 | 0.58 | 0.17 | 0.75
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3812461.4 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 377.05 | 1885250 | 39.52% | 745118.26 | 25.57% | 482088.62 | 65.10% | 1227206.88 | 1976.18 | 1278.58 | 3254.76
2.2 | Raft Foundation | m3 | 3500 | 267.09 | 934815 | 43.74% | 408871.76 | 16.80% | 157073.94 | 60.54% | 565945.7 | 1530.84 | 588.09 | 2118.93
2.3 | Basement Slab and Walls | m3 | 4000 | 397.15 | 1588600 | 52.93% | 840922.18 | 15.32% | 243366.46 | 68.25% | 1084288.64 | 2117.39 | 612.78 | 2730.17
3 | Superstructure | LS | LS | - | 3169462.31 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 393.83 | 189038.4 | 29.07% | 54960.69 | 28.41% | 53711.66 | 57.49% | 108672.35 | 139.55 | 136.38 | 275.93
3.2 | Vertical Elements | m3 | 3600 | 214.97 | 773892 | 46.75% | 361780.39 | 29.07% | 224983.88 | 75.82% | 586764.27 | 1682.93 | 1046.58 | 2729.51
3.3 | Floor Slabs | m3 | 6000 | 264.03 | 1584180 | 37.77% | 598370.6 | 17.38% | 275255.22 | 55.15% | 873625.82 | 2266.3 | 1042.51 | 3308.81
3.4 | Staircase Construction | m3 | 1000 | 284.79 | 284790 | 34.63% | 98625.29 | 19.19% | 54645.91 | 53.82% | 153271.2 | 346.31 | 191.88 | 538.19
3.5 | Lift Core Construction | m3 | 1000 | 227.56 | 227560 | 41.16% | 93652.87 | 16.91% | 38491.03 | 58.07% | 132143.9 | 411.55 | 169.15 | 580.7
3.6 | Roof Slab and Parapets | m3 | 360 | 228.85 | 82386 | 53.81% | 44334.77 | 16.16% | 13309.64 | 69.97% | 57644.41 | 193.73 | 58.16 | 251.89
4 | Masonry and Partitioning | LS | LS | - | 13264055.67 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 155.45 | 5440750 | 45.14% | 2456205.52 | 27.27% | 1483469.13 | 72.41% | 3939674.65 | 15800.61 | 9543.06 | 25343.67
4.2 | Internal Blockwork | m2 | 35000 | 235.5 | 8242500 | 42.74% | 3522778.5 | 8.41% | 692971.95 | 51.15% | 4215750.45 | 14958.72 | 2942.56 | 17901.28
4.3 | Drywall Partitioning | m3 | 1000 | 250.23 | 250230 | 48.47% | 121292.4 | 24.75% | 61943.82 | 73.23% | 183236.22 | 484.72 | 247.55 | 732.27
5 | MEP Works | LS | LS | - | 209825 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 54858.7 | 54858.7 | 48.90% | 26824.28 | 30.31% | 16628.25 | 79.21% | 43452.53 | 0.49 | 0.3 | 0.79
5.2 | Plumbing & Drainage | LS | 1 | 47007.59 | 47007.59 | 56.34% | 26485.31 | 11.64% | 5471.55 | 67.98% | 31956.86 | 0.56 | 0.12 | 0.68
5.3 | Firefighting Piping | LS | 1 | 49991.68 | 49991.68 | 40.57% | 20281.99 | 19.53% | 9763.14 | 60.10% | 30045.13 | 0.41 | 0.2 | 0.61
5.4 | HVAC Ducting | No. | 40 | 658.44 | 26337.6 | 41.73% | 10989.61 | 20.33% | 5353.32 | 62.05% | 16342.93 | 16.69 | 8.13 | 24.82
5.5 | Low Current Systems | LS | 1 | 47152.94 | 47152.94 | 27.67% | 13047.49 | 24.13% | 11376.08 | 51.80% | 24423.57 | 0.28 | 0.24 | 0.52
6 | Finishing Works | LS | LS | - | 14776500.81 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 58.75 | 1938750 | 58.46% | 1133335.79 | 21.41% | 415171.3 | 79.87% | 1548507.09 | 19290.82 | 7066.75 | 26357.57
6.2 | Waterproofing | m2 | 5000 | 233.95 | 1169750 | 60.89% | 712312.48 | 18.15% | 212293.13 | 79.04% | 924605.61 | 3044.72 | 907.43 | 3952.15
6.3 | Tiling | m2 | 15000 | 252.74 | 3791100 | 40.84% | 1548234.5 | 19.24% | 729570.2 | 60.08% | 2277804.7 | 6125.8 | 2886.64 | 9012.44
6.4 | Painting | m2 | 40000 | 86.99 | 3479600 | 40.57% | 1411646.65 | 10.76% | 374406.39 | 51.33% | 1786053.04 | 16227.69 | 4304.02 | 20531.71
6.5 | Ceiling Works | m2 | 18000 | 136.44 | 2455920 | 39.26% | 964257.3 | 13.78% | 338525.28 | 53.05% | 1302782.58 | 7067.26 | 2481.13 | 9548.39
6.6 | Joinery Installation | No. | 400 | 853.19 | 341276 | 43.99% | 150135.84 | 22.24% | 75894.51 | 66.23% | 226030.35 | 175.97 | 88.95 | 264.92
6.7 | Door & Window Installation | No. | 800 | 1355.78 | 1084624 | 45.03% | 488445.37 | 21.11% | 228985.89 | 66.15% | 717431.26 | 360.27 | 168.9 | 529.17
6.8 | Glazing | m2 | 12000 | 80.47 | 965640 | 56.12% | 541943.16 | 13.56% | 130900.99 | 69.68% | 672844.15 | 6734.72 | 1626.71 | 8361.43
7 | External Works & Landscaping | LS | LS | - | 3385331.67 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 789.45 | 78945 | 43.44% | 34292.71 | 16.81% | 13267.68 | 60.24% | 47560.39 | 43.44 | 16.81 | 60.25
7.2 | Roadworks and Paving | m2 | 8000 | 194.27 | 1554160 | 30.81% | 478853.99 | 31.02% | 482104.85 | 61.83% | 960958.84 | 2464.89 | 2481.62 | 4946.51
7.3 | Kerbstone and Interlock | m2 | 7000 | 100.25 | 701750 | 51.44% | 360959.72 | 14.35% | 100699.33 | 65.79% | 461659.05 | 3600.6 | 1004.48 | 4605.08
7.4 | Landscaping | m3 | 1000 | 402.66 | 402660 | 56.47% | 227390.02 | 21.22% | 85437.22 | 77.69% | 312827.24 | 564.72 | 212.18 | 776.9
7.5 | Boundary Wall | m3 | 1000 | 301.48 | 301480 | 38.21% | 115202.29 | 33.43% | 100782.45 | 71.64% | 215984.74 | 382.12 | 334.29 | 716.41
8 | Final Works | LS | LS | - | 531674.4 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 213440.33 | 213440.33 | 28.56% | 60957.32 | 29.76% | 63529.12 | 58.32% | 124486.44 | 0.29 | 0.3 | 0.59
8.2 | Snagging & De-snagging | LS | 1 | 96158.43 | 96158.43 | 21.95% | 21108.06 | 34.70% | 33371.58 | 56.66% | 54479.64 | 0.22 | 0.35 | 0.57
8.3 | Cleaning | LS | 1 | 93483.13 | 93483.13 | 39.62% | 37040.36 | 26.54% | 24808.56 | 66.16% | 61848.92 | 0.4 | 0.27 | 0.67
8.4 | Handover | LS | 1 | 159527.07 | 159527.07 | 29.98% | 47821.84 | 27.48% | 43836.36 | 57.46% | 91658.2 | 0.3 | 0.27 | 0.57

## IPC_Oct_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 841115.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 45360.55 | 45360.55 | 36.38% | 16503.29 | 34.63% | 15707.47 | 71.01% | 32210.76 | 0.36 | 0.35 | 0.71
1.2 | Site Fencing and Hoarding | LS | 1 | 47447.33 | 47447.33 | 65.30% | 30981.92 | 7.36% | 3489.76 | 72.65% | 34471.68 | 0.65 | 0.07 | 0.72
1.3 | Temporary Facilities Setup | LS | 1 | 371705.35 | 371705.35 | 59.54% | 221300.6 | 9.05% | 33656.52 | 68.59% | 254957.12 | 0.6 | 0.09 | 0.69
1.4 | Soil Testing and Survey | LS | 1 | 186797.73 | 186797.73 | 58.67% | 109597.46 | 23.33% | 43585.45 | 82.00% | 153182.91 | 0.59 | 0.23 | 0.82
1.5 | Excavation | LS | 1 | 51281.28 | 51281.28 | 62.03% | 31811.98 | 13.97% | 7163.08 | 76.00% | 38975.06 | 0.62 | 0.14 | 0.76
1.6 | Dewatering | LS | 1 | 48979.29 | 48979.29 | 43.32% | 21217.63 | 32.53% | 15931.35 | 75.85% | 37148.98 | 0.43 | 0.33 | 0.76
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4470279.07 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 360.82 | 1804100 | 57.38% | 1035214.74 | 15.68% | 282825.08 | 73.06% | 1318039.82 | 2869.06 | 783.84 | 3652.9
2.2 | Raft Foundation | m3 | 3500 | 253.63 | 887705 | 31.86% | 282851.41 | 33.69% | 299045.31 | 65.55% | 581896.72 | 1115.21 | 1179.06 | 2294.27
2.3 | Basement Slab and Walls | m3 | 4000 | 412.11 | 1648440 | 48.83% | 804864.28 | 19.57% | 322653.06 | 68.40% | 1127517.34 | 1953.03 | 782.93 | 2735.96
3 | Superstructure | LS | LS | - | 3171373.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 358.45 | 172056 | 33.29% | 57280.5 | 24.56% | 42259.11 | 57.85% | 99539.61 | 159.8 | 117.89 | 277.69
3.2 | Vertical Elements | m3 | 3600 | 231.87 | 834732 | 67.47% | 563223.88 | 7.37% | 61510.32 | 74.84% | 624734.2 | 2429.05 | 265.28 | 2694.33
3.3 | Floor Slabs | m3 | 6000 | 290.61 | 1743660 | 70.15% | 1223117.55 | 7.36% | 128381.62 | 77.51% | 1351499.17 | 4208.79 | 441.77 | 4650.56
3.4 | Staircase Construction | m3 | 1000 | 304.2 | 304200 | 59.36% | 180559.88 | 15.73% | 47861.85 | 75.09% | 228421.73 | 593.56 | 157.34 | 750.9
3.5 | Lift Core Construction | m3 | 1000 | 200.94 | 200940 | 49.59% | 99643.66 | 23.14% | 46503.06 | 72.73% | 146146.72 | 495.89 | 231.43 | 727.32
3.6 | Roof Slab and Parapets | m3 | 360 | 245.87 | 88513.2 | 65.30% | 57802.15 | 19.90% | 17613.22 | 85.20% | 75415.37 | 235.09 | 71.64 | 306.73
4 | Masonry and Partitioning | LS | LS | - | 13513273.66 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 162.04 | 5671400 | 40.29% | 2285184.77 | 21.01% | 1191752.14 | 61.31% | 3476936.91 | 14102.6 | 7354.68 | 21457.28
4.2 | Internal Blockwork | m2 | 35000 | 249.02 | 8715700 | 44.26% | 3857558.62 | 13.87% | 1209217.96 | 58.13% | 5066776.58 | 15490.96 | 4855.91 | 20346.87
4.3 | Drywall Partitioning | m3 | 1000 | 255.17 | 255170 | 24.91% | 63571.08 | 34.43% | 87855.65 | 59.34% | 151426.73 | 249.13 | 344.3 | 593.43
5 | MEP Works | LS | LS | - | 207724.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 47559.42 | 47559.42 | 57.45% | 27323.11 | 12.27% | 5835.48 | 69.72% | 33158.59 | 0.57 | 0.12 | 0.69
5.2 | Plumbing & Drainage | LS | 1 | 50126.09 | 50126.09 | 32.79% | 16434.16 | 29.00% | 14538.97 | 61.79% | 30973.13 | 0.33 | 0.29 | 0.62
5.3 | Firefighting Piping | LS | 1 | 45682.71 | 45682.71 | 35.46% | 16197.77 | 26.91% | 12292.34 | 62.37% | 28490.11 | 0.35 | 0.27 | 0.62
5.4 | HVAC Ducting | No. | 40 | 628.36 | 25134.4 | 57.46% | 14441.28 | 16.83% | 4230.7 | 74.29% | 18671.98 | 22.98 | 6.73 | 29.71
5.5 | Low Current Systems | LS | 1 | 50947.22 | 50947.22 | 24.03% | 12241.93 | 34.10% | 17372.74 | 58.13% | 29614.67 | 0.24 | 0.34 | 0.58
6 | Finishing Works | LS | LS | - | 13686008.54 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 59.81 | 1973730 | 46.80% | 923800.58 | 23.58% | 465431.38 | 70.39% | 1389231.96 | 15445.59 | 7781.83 | 23227.42
6.2 | Waterproofing | m2 | 5000 | 249.9 | 1249500 | 43.45% | 542880.4 | 18.02% | 225150.28 | 61.47% | 768030.68 | 2172.39 | 900.96 | 3073.35
6.3 | Tiling | m2 | 15000 | 224.39 | 3365850 | 45.85% | 1543353.13 | 16.20% | 545222.09 | 62.05% | 2088575.22 | 6877.99 | 2429.8 | 9307.79
6.4 | Painting | m2 | 40000 | 76.68 | 3067200 | 66.55% | 2041203.89 | 16.26% | 498599.6 | 82.81% | 2539803.49 | 26619.77 | 6502.34 | 33122.11
6.5 | Ceiling Works | m2 | 18000 | 137.27 | 2470860 | 69.30% | 1712413.64 | 6.43% | 158951.37 | 75.74% | 1871365.01 | 12474.78 | 1157.95 | 13632.73
6.6 | Joinery Installation | No. | 400 | 739.68 | 295872 | 58.89% | 174230.59 | 16.89% | 49958.85 | 75.77% | 224189.44 | 235.55 | 67.54 | 303.09
6.7 | Door & Window Installation | No. | 800 | 1349.69 | 1079752 | 50.78% | 548292.66 | 8.48% | 91608.69 | 59.26% | 639901.35 | 406.24 | 67.87 | 474.11
6.8 | Glazing | m2 | 12000 | 71.75 | 861000 | 31.34% | 269857.11 | 29.94% | 257747.84 | 61.28% | 527604.95 | 3761.07 | 3592.3 | 7353.37
7 | External Works & Landscaping | LS | LS | - | 3161446.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 872.88 | 87288 | 65.13% | 56853.2 | 9.03% | 7884.06 | 74.17% | 64737.26 | 65.13 | 9.03 | 74.16
7.2 | Roadworks and Paving | m2 | 8000 | 199.49 | 1595920 | 45.25% | 722196.75 | 31.07% | 495866.85 | 76.32% | 1218063.6 | 3620.22 | 2485.67 | 6105.89
7.3 | Kerbstone and Interlock | m2 | 7000 | 110.95 | 776650 | 38.32% | 297639.66 | 26.80% | 208163.49 | 65.13% | 505803.15 | 2682.65 | 1876.19 | 4558.84
7.4 | Landscaping | m3 | 1000 | 372.94 | 372940 | 55.70% | 207733.24 | 29.77% | 111035.57 | 85.47% | 318768.81 | 557.02 | 297.73 | 854.75
7.5 | Boundary Wall | m3 | 1000 | 266.8 | 266800 | 64.24% | 171397.3 | 17.97% | 47948.52 | 82.21% | 219345.82 | 642.42 | 179.72 | 822.14
8 | Final Works | LS | LS | - | 552800.67 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 206248.62 | 206248.62 | 50.30% | 103733.88 | 11.10% | 22897.41 | 61.40% | 126631.29 | 0.5 | 0.11 | 0.61
8.2 | Snagging & De-snagging | LS | 1 | 104275 | 104275 | 62.71% | 65391.09 | 12.56% | 13097.71 | 75.27% | 78488.8 | 0.63 | 0.13 | 0.76
8.3 | Cleaning | LS | 1 | 94527.6 | 94527.6 | 38.93% | 36803.53 | 30.84% | 29147.85 | 69.77% | 65951.38 | 0.39 | 0.31 | 0.7
8.4 | Handover | LS | 1 | 155797.86 | 155797.86 | 49.91% | 77758.4 | 28.89% | 45004.42 | 78.80% | 122762.82 | 0.5 | 0.29 | 0.79