## IPC_Oct_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 808832.53 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50766.91 | 50766.91 |  | 0 | 28.32% | 14378.9 | 28.32% | 14378.9 | 0 | 0.28 | 0.28
1.2 | Site Fencing and Hoarding | LS | 1 | 52945.06 | 52945.06 |  | 0 | 38.54% | 20404.1 | 38.54% | 20404.1 | 0 | 0.39 | 0.39
1.3 | Temporary Facilities Setup | LS | 1 | 416195.97 | 416195.97 |  | 0 | 24.94% | 103778.58 | 24.94% | 103778.58 | 0 | 0.25 | 0.25
1.4 | Soil Testing and Survey | LS | 1 | 189543.62 | 189543.62 |  | 0 | 26.97% | 51113.08 | 26.97% | 51113.08 | 0 | 0.27 | 0.27
1.5 | Excavation | LS | 1 | 50555.24 | 50555.24 |  | 0 | 18.13% | 9165.48 | 18.13% | 9165.48 | 0 | 0.18 | 0.18
1.6 | Dewatering | LS | 1 | 54156.13 | 54156.13 |  | 0 | 12.88% | 6975.09 | 12.88% | 6975.09 | 0 | 0.13 | 0.13
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4552208.76 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 379.73 | 1898650 |  | 0 | 17.56% | 333388.64 | 17.56% | 333388.64 | 0 | 877.96 | 877.96
2.2 | Raft Foundation | m3 | 3500 | 270.11 | 945385 |  | 0 | 24.72% | 233654.63 | 24.72% | 233654.63 | 0 | 865.04 | 865.04
2.3 | Basement Slab and Walls | m3 | 4000 | 356.27 | 1425080 |  | 0 | 24.97% | 355901.49 | 24.97% | 355901.49 | 0 | 998.97 | 998.97
3 | Superstructure | LS | LS | - | 3007815.55 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 370.53 | 177854.4 |  | 0 | 13.22% | 23509.45 | 13.22% | 23509.45 | 0 | 63.45 | 63.45
3.2 | Vertical Elements | m3 | 3600 | 227.75 | 819900 |  | 0 | 11.32% | 92808.6 | 11.32% | 92808.6 | 0 | 407.5 | 407.5
3.3 | Floor Slabs | m3 | 6000 | 286.41 | 1718460 |  | 0 | 19.66% | 337830.39 | 19.66% | 337830.39 | 0 | 1179.53 | 1179.53
3.4 | Staircase Construction | m3 | 1000 | 299.19 | 299190 |  | 0 | 19.35% | 57905.38 | 19.35% | 57905.38 | 0 | 193.54 | 193.54
3.5 | Lift Core Construction | m3 | 1000 | 214.66 | 214660 |  | 0 | 16.98% | 36454.47 | 16.98% | 36454.47 | 0 | 169.82 | 169.82
3.6 | Roof Slab and Parapets | m3 | 360 | 249.05 | 89658 |  | 0 | 34.02% | 30503.3 | 34.02% | 30503.3 | 0 | 122.48 | 122.48
4 | Masonry and Partitioning | LS | LS | - | 13353502.54 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 176.64 | 6182400 |  | 0 | 12.23% | 756254.88 | 12.23% | 756254.88 | 0 | 4281.33 | 4281.33
4.2 | Internal Blockwork | m2 | 35000 | 244.83 | 8569050 |  | 0 | 13.66% | 1170842.35 | 13.66% | 1170842.35 | 0 | 4782.27 | 4782.27
4.3 | Drywall Partitioning | m3 | 1000 | 235.25 | 235250 |  | 0 | 16.84% | 39623.4 | 16.84% | 39623.4 | 0 | 168.43 | 168.43
5 | MEP Works | LS | LS | - | 221214.6 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 53689.03 | 53689.03 |  | 0 | 16.49% | 8855.07 | 16.49% | 8855.07 | 0 | 0.16 | 0.16
5.2 | Plumbing & Drainage | LS | 1 | 53707.92 | 53707.92 |  | 0 | 22.81% | 12252.34 | 22.81% | 12252.34 | 0 | 0.23 | 0.23
5.3 | Firefighting Piping | LS | 1 | 45563.24 | 45563.24 |  | 0 | 25.52% | 11627.92 | 25.52% | 11627.92 | 0 | 0.26 | 0.26
5.4 | HVAC Ducting | No. | 40 | 622.07 | 24882.8 |  | 0 | 29.74% | 7400.71 | 29.74% | 7400.71 | 0 | 11.9 | 11.9
5.5 | Low Current Systems | LS | 1 | 52578.47 | 52578.47 |  | 0 | 36.45% | 19165.46 | 36.45% | 19165.46 | 0 | 0.36 | 0.36
6 | Finishing Works | LS | LS | - | 15791987.76 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 55.56 | 1833480 |  | 0 | 33.40% | 612365.17 | 33.40% | 612365.17 | 0 | 11021.69 | 11021.69
6.2 | Waterproofing | m2 | 5000 | 249.24 | 1246200 |  | 0 | 11.70% | 145808.22 | 11.70% | 145808.22 | 0 | 585.01 | 585.01
6.3 | Tiling | m2 | 15000 | 228.27 | 3424050 |  | 0 | 24.53% | 839885.52 | 24.53% | 839885.52 | 0 | 3679.35 | 3679.35
6.4 | Painting | m2 | 40000 | 85.7 | 3428000 |  | 0 | 27.79% | 952539.56 | 27.79% | 952539.56 | 0 | 11114.81 | 11114.81
6.5 | Ceiling Works | m2 | 18000 | 139.46 | 2510280 |  | 0 | 32.06% | 804838.15 | 32.06% | 804838.15 | 0 | 5771.1 | 5771.1
6.6 | Joinery Installation | No. | 400 | 819.79 | 327916 |  | 0 | 18.09% | 59331.89 | 18.09% | 59331.89 | 0 | 72.37 | 72.37
6.7 | Door & Window Installation | No. | 800 | 1315.51 | 1052408 |  | 0 | 10.42% | 109683.96 | 10.42% | 109683.96 | 0 | 83.38 | 83.38
6.8 | Glazing | m2 | 12000 | 82.84 | 994080 |  | 0 | 38.04% | 378174.62 | 38.04% | 378174.62 | 0 | 4565.12 | 4565.12
7 | External Works & Landscaping | LS | LS | - | 3253342.24 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 826.09 | 82609 |  | 0 | 28.95% | 23917.71 | 28.95% | 23917.71 | 0 | 28.95 | 28.95
7.2 | Roadworks and Paving | m2 | 8000 | 210.52 | 1684160 |  | 0 | 21.80% | 367078.36 | 21.80% | 367078.36 | 0 | 1743.67 | 1743.67
7.3 | Kerbstone and Interlock | m2 | 7000 | 117.36 | 821520 |  | 0 | 31.78% | 261100.29 | 31.78% | 261100.29 | 0 | 2224.78 | 2224.78
7.4 | Landscaping | m3 | 1000 | 364.99 | 364990 |  | 0 | 36.03% | 131513.43 | 36.03% | 131513.43 | 0 | 360.32 | 360.32
7.5 | Boundary Wall | m3 | 1000 | 306.74 | 306740 |  | 0 | 12.82% | 39327.03 | 12.82% | 39327.03 | 0 | 128.21 | 128.21
8 | Final Works | LS | LS | - | 537504.99 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 210474.49 | 210474.49 |  | 0 | 15.99% | 33657.62 | 15.99% | 33657.62 | 0 | 0.16 | 0.16
8.2 | Snagging & De-snagging | LS | 1 | 105902.48 | 105902.48 |  | 0 | 35.67% | 37771.7 | 35.67% | 37771.7 | 0 | 0.36 | 0.36
8.3 | Cleaning | LS | 1 | 90617.45 | 90617.45 |  | 0 | 35.03% | 31746.19 | 35.03% | 31746.19 | 0 | 0.35 | 0.35
8.4 | Handover | LS | 1 | 151935.74 | 151935.74 |  | 0 | 13.53% | 20556.15 | 13.53% | 20556.15 | 0 | 0.14 | 0.14

## IPC_Nov_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 745445.46 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 45598.19 | 45598.19 | 33.27% | 15170.08 | 21.16% | 9650.44 | 54.43% | 24820.52 | 0.33 | 0.21 | 0.54
1.2 | Site Fencing and Hoarding | LS | 1 | 48481.32 | 48481.32 | 55.67% | 26990 | 12.08% | 5856.28 | 67.75% | 32846.28 | 0.56 | 0.12 | 0.68
1.3 | Temporary Facilities Setup | LS | 1 | 405196.29 | 405196.29 | 56.35% | 228343.07 | 10.17% | 41197.54 | 66.52% | 269540.61 | 0.56 | 0.1 | 0.66
1.4 | Soil Testing and Survey | LS | 1 | 218208.64 | 218208.64 | 17.75% | 38733.48 | 32.01% | 69841.52 | 49.76% | 108575 | 0.18 | 0.32 | 0.5
1.5 | Excavation | LS | 1 | 48143.46 | 48143.46 | 37.41% | 18008.33 | 16.97% | 8170.84 | 54.38% | 26179.17 | 0.37 | 0.17 | 0.54
1.6 | Dewatering | LS | 1 | 54414.15 | 54414.15 | 34.04% | 18523.23 | 30.03% | 16339.42 | 64.07% | 34862.65 | 0.34 | 0.3 | 0.64
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3851777.32 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 361.19 | 1805950 | 39.48% | 712915.92 | 16.66% | 300851.44 | 56.13% | 1013767.36 | 1973.8 | 832.95 | 2806.75
2.2 | Raft Foundation | m3 | 3500 | 250.95 | 878325 | 68.30% | 599855.96 | 9.17% | 80500.03 | 77.46% | 680355.99 | 2390.34 | 320.78 | 2711.12
2.3 | Basement Slab and Walls | m3 | 4000 | 379.01 | 1516040 | 49.84% | 755562.4 | 14.33% | 217191.07 | 64.16% | 972753.47 | 1993.52 | 573.05 | 2566.57
3 | Superstructure | LS | LS | - | 3090361.67 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 421.08 | 202118.4 | 40.76% | 82375.8 | 15.86% | 32050.79 | 56.61% | 114426.59 | 195.63 | 76.12 | 271.75
3.2 | Vertical Elements | m3 | 3600 | 224.87 | 809532 | 23.40% | 189461.32 | 34.56% | 279751.23 | 57.96% | 469212.55 | 842.54 | 1244.06 | 2086.6
3.3 | Floor Slabs | m3 | 6000 | 277.9 | 1667400 | 64.22% | 1070832.49 | 8.78% | 146372.5 | 73.00% | 1217204.99 | 3853.3 | 526.71 | 4380.01
3.4 | Staircase Construction | m3 | 1000 | 260.13 | 260130 | 34.50% | 89744.62 | 30.17% | 78479.37 | 64.67% | 168223.99 | 345 | 301.69 | 646.69
3.5 | Lift Core Construction | m3 | 1000 | 210.64 | 210640 | 46.74% | 98444 | 17.83% | 37553.43 | 64.56% | 135997.43 | 467.36 | 178.28 | 645.64
3.6 | Roof Slab and Parapets | m3 | 360 | 231.44 | 83318.4 | 39.03% | 32517.48 | 10.28% | 8561.1 | 49.30% | 41078.58 | 140.5 | 36.99 | 177.49
4 | Masonry and Partitioning | LS | LS | - | 13357520.36 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 168.11 | 5883850 | 60.03% | 3532342.46 | 12.06% | 709740.37 | 72.10% | 4242082.83 | 21012.09 | 4221.88 | 25233.97
4.2 | Internal Blockwork | m2 | 35000 | 230.92 | 8082200 | 48.38% | 3910525.68 | 24.97% | 2018323.8 | 73.36% | 5928849.48 | 16934.55 | 8740.36 | 25674.91
4.3 | Drywall Partitioning | m3 | 1000 | 255.87 | 255870 | 52.25% | 133701.01 | 20.21% | 51710.59 | 72.46% | 185411.6 | 522.53 | 202.1 | 724.63
5 | MEP Works | LS | LS | - | 219445.63 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 54018.01 | 54018.01 | 21.44% | 11582.49 | 29.72% | 16055.75 | 51.16% | 27638.24 | 0.21 | 0.3 | 0.51
5.2 | Plumbing & Drainage | LS | 1 | 49790.5 | 49790.5 | 24.65% | 12273.86 | 27.88% | 13881.31 | 52.53% | 26155.17 | 0.25 | 0.28 | 0.53
5.3 | Firefighting Piping | LS | 1 | 49413.06 | 49413.06 | 18.82% | 9300.97 | 32.71% | 16161.22 | 51.53% | 25462.19 | 0.19 | 0.33 | 0.52
5.4 | HVAC Ducting | No. | 40 | 629.33 | 25173.2 | 23.55% | 5927.52 | 26.99% | 6793.86 | 50.54% | 12721.38 | 9.42 | 10.8 | 20.22
5.5 | Low Current Systems | LS | 1 | 46504.12 | 46504.12 | 28.27% | 13148.1 | 23.02% | 10704.91 | 51.29% | 23853.01 | 0.28 | 0.23 | 0.51
6 | Finishing Works | LS | LS | - | 14529658.37 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 52.31 | 1726230 | 44.78% | 772935.05 | 24.27% | 418966.61 | 69.05% | 1191901.66 | 14776.05 | 8009.3 | 22785.35
6.2 | Waterproofing | m2 | 5000 | 229.62 | 1148100 | 56.10% | 644047.8 | 10.63% | 122088.82 | 66.73% | 766136.62 | 2804.84 | 531.7 | 3336.54
6.3 | Tiling | m2 | 15000 | 232.08 | 3481200 | 71.74% | 2497539.09 | 7.14% | 248613.28 | 78.89% | 2746152.37 | 10761.54 | 1071.24 | 11832.78
6.4 | Painting | m2 | 40000 | 84.32 | 3372800 | 57.66% | 1944605 | 10.63% | 358447.3 | 68.28% | 2303052.3 | 23062.2 | 4251.04 | 27313.24
6.5 | Ceiling Works | m2 | 18000 | 137.91 | 2482380 | 23.55% | 584481.66 | 26.87% | 667029.57 | 50.42% | 1251511.23 | 4238.14 | 4836.7 | 9074.84
6.6 | Joinery Installation | No. | 400 | 842.72 | 337088 | 40.24% | 135634.21 | 14.16% | 47718.68 | 54.39% | 183352.89 | 160.95 | 56.62 | 217.57
6.7 | Door & Window Installation | No. | 800 | 1526.65 | 1221320 | 28.31% | 345794.03 | 32.37% | 395310.48 | 60.68% | 741104.51 | 226.51 | 258.94 | 485.45
6.8 | Glazing | m2 | 12000 | 77.52 | 930240 | 62.29% | 579414.52 | 11.27% | 104845.43 | 73.56% | 684259.95 | 7474.39 | 1352.5 | 8826.89
7 | External Works & Landscaping | LS | LS | - | 3326653.13 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 836.04 | 83604 | 42.21% | 35291.37 | 20.85% | 17431.61 | 63.06% | 52722.98 | 42.21 | 20.85 | 63.06
7.2 | Roadworks and Paving | m2 | 8000 | 228.05 | 1824400 | 46.03% | 839748.49 | 8.71% | 158882.64 | 54.74% | 998631.13 | 3682.3 | 696.7 | 4379
7.3 | Kerbstone and Interlock | m2 | 7000 | 116.53 | 815710 | 34.59% | 282149.14 | 34.47% | 281169.77 | 69.06% | 563318.91 | 2421.26 | 2412.85 | 4834.11
7.4 | Landscaping | m3 | 1000 | 382.09 | 382090 | 40.97% | 156533.38 | 19.93% | 76138.14 | 60.89% | 232671.52 | 409.68 | 199.27 | 608.95
7.5 | Boundary Wall | m3 | 1000 | 273.53 | 273530 | 30.64% | 83801.18 | 31.69% | 86686.38 | 62.33% | 170487.56 | 306.37 | 316.92 | 623.29
8 | Final Works | LS | LS | - | 546345.64 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 181295.2 | 181295.2 | 46.43% | 84166.53 | 11.86% | 21500.82 | 58.28% | 105667.35 | 0.46 | 0.12 | 0.58
8.2 | Snagging & De-snagging | LS | 1 | 91421.01 | 91421.01 | 62.98% | 57573.91 | 15.84% | 14483.14 | 78.82% | 72057.05 | 0.63 | 0.16 | 0.79
8.3 | Cleaning | LS | 1 | 105861.21 | 105861.21 | 46.48% | 49208.41 | 20.42% | 21621.58 | 66.91% | 70829.99 | 0.46 | 0.2 | 0.66
8.4 | Handover | LS | 1 | 160944.63 | 160944.63 | 16.90% | 27201.56 | 32.77% | 52743.94 | 49.67% | 79945.5 | 0.17 | 0.33 | 0.5

## IPC_Dec_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 876423.8 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 51796.05 | 51796.05 | 58.49% | 30296.13 | 21.87% | 11326.47 | 80.36% | 41622.6 | 0.58 | 0.22 | 0.8
1.2 | Site Fencing and Hoarding | LS | 1 | 45143.59 | 45143.59 | 66.34% | 29947.7 | 16.85% | 7608.42 | 83.19% | 37556.12 | 0.66 | 0.17 | 0.83
1.3 | Temporary Facilities Setup | LS | 1 | 370701.43 | 370701.43 | 58.58% | 217150.52 | 12.97% | 48062.11 | 71.54% | 265212.63 | 0.59 | 0.13 | 0.72
1.4 | Soil Testing and Survey | LS | 1 | 191721.83 | 191721.83 | 58.21% | 111594.12 | 19.52% | 37430.45 | 77.73% | 149024.57 | 0.58 | 0.2 | 0.78
1.5 | Excavation | LS | 1 | 47731.51 | 47731.51 | 67.37% | 32155.41 | 22.19% | 10592.07 | 89.56% | 42747.48 | 0.67 | 0.22 | 0.89
1.6 | Dewatering | LS | 1 | 46383.71 | 46383.71 | 54.09% | 25086.98 | 18.29% | 8481.91 | 72.37% | 33568.89 | 0.54 | 0.18 | 0.72
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4300355.45 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 349.89 | 1749450 | 45.70% | 799422.54 | 32.80% | 573775.63 | 78.49% | 1373198.17 | 2284.78 | 1639.87 | 3924.65
2.2 | Raft Foundation | m3 | 3500 | 248.75 | 870625 | 45.28% | 394232.23 | 29.29% | 254968.64 | 74.57% | 649200.87 | 1584.85 | 1025 | 2609.85
2.3 | Basement Slab and Walls | m3 | 4000 | 421.43 | 1685720 | 65.24% | 1099764.37 | 12.03% | 202784.37 | 77.27% | 1302548.74 | 2609.6 | 481.18 | 3090.78
3 | Superstructure | LS | LS | - | 3564236.23 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 352.11 | 169012.8 | 54.56% | 92215.72 | 27.68% | 46778.25 | 82.24% | 138993.97 | 261.89 | 132.85 | 394.74
3.2 | Vertical Elements | m3 | 3600 | 210.72 | 758592 | 55.24% | 419034.04 | 23.72% | 179937.15 | 78.96% | 598971.19 | 1988.58 | 853.92 | 2842.5
3.3 | Floor Slabs | m3 | 6000 | 276.37 | 1658220 | 76.17% | 1263049.32 | 13.67% | 226617.55 | 89.84% | 1489666.87 | 4570.14 | 819.98 | 5390.12
3.4 | Staircase Construction | m3 | 1000 | 297.23 | 297230 | 61.63% | 183197.34 | 27.12% | 80594.61 | 88.75% | 263791.95 | 616.35 | 271.15 | 887.5
3.5 | Lift Core Construction | m3 | 1000 | 206.6 | 206600 | 55.79% | 115262.96 | 32.02% | 66145.84 | 87.81% | 181408.8 | 557.9 | 320.16 | 878.06
3.6 | Roof Slab and Parapets | m3 | 360 | 232.8 | 83808 | 59.15% | 49571.26 | 21.75% | 18228.3 | 80.90% | 67799.56 | 212.93 | 78.3 | 291.23
4 | Masonry and Partitioning | LS | LS | - | 13609522.63 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 182.54 | 6388900 | 49.01% | 3131470.3 | 23.75% | 1517287.4 | 72.76% | 4648757.7 | 17154.98 | 8312.08 | 25467.06
4.2 | Internal Blockwork | m2 | 35000 | 255.86 | 8955100 | 60.66% | 5432097.05 | 34.95% | 3129920.32 | 95.61% | 8562017.37 | 21230.74 | 12232.94 | 33463.68
4.3 | Drywall Partitioning | m3 | 1000 | 242.94 | 242940 | 61.34% | 149023.42 | 14.37% | 34899.85 | 75.71% | 183923.27 | 613.42 | 143.66 | 757.08
5 | MEP Works | LS | LS | - | 237889.77 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 52262.4 | 52262.4 | 55.66% | 29087.78 | 17.06% | 8917.89 | 72.72% | 38005.67 | 0.56 | 0.17 | 0.73
5.2 | Plumbing & Drainage | LS | 1 | 52424.03 | 52424.03 | 36.28% | 19017.23 | 33.88% | 17761.44 | 70.16% | 36778.67 | 0.36 | 0.34 | 0.7
5.3 | Firefighting Piping | LS | 1 | 52601.63 | 52601.63 | 78.07% | 41067.7 | 5.06% | 2660.49 | 83.13% | 43728.19 | 0.78 | 0.05 | 0.83
5.4 | HVAC Ducting | No. | 40 | 621 | 24840 | 62.49% | 15521.7 | 32.49% | 8070.13 | 94.98% | 23591.83 | 24.99 | 13 | 37.99
5.5 | Low Current Systems | LS | 1 | 50822.92 | 50822.92 | 51.07% | 25952.73 | 17.32% | 8802.19 | 68.38% | 34754.92 | 0.51 | 0.17 | 0.68
6 | Finishing Works | LS | LS | - | 13676050.75 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 59.25 | 1955250 | 84.53% | 1652778.4 | 11.08% | 216564.7 | 95.61% | 1869343.1 | 27894.99 | 3655.1 | 31550.09
6.2 | Waterproofing | m2 | 5000 | 255.67 | 1278350 | 56.25% | 719131.19 | 13.36% | 170806.71 | 69.62% | 889937.9 | 2812.73 | 668.07 | 3480.8
6.3 | Tiling | m2 | 15000 | 246.68 | 3700200 | 59.54% | 2203104.65 | 9.69% | 358481.05 | 69.23% | 2561585.7 | 8931.02 | 1453.22 | 10384.24
6.4 | Painting | m2 | 40000 | 81.43 | 3257200 | 74.62% | 2430605.64 | 21.20% | 690541.4 | 95.82% | 3121147.04 | 29849.02 | 8480.18 | 38329.2
6.5 | Ceiling Works | m2 | 18000 | 144.26 | 2596680 | 60.80% | 1578669.46 | 29.53% | 766819.36 | 90.33% | 2345488.82 | 10943.22 | 5315.54 | 16258.76
6.6 | Joinery Installation | No. | 400 | 777.27 | 310908 | 53.56% | 166530.71 | 23.64% | 73498.29 | 77.20% | 240029 | 214.25 | 94.56 | 308.81
6.7 | Door & Window Installation | No. | 800 | 1465.51 | 1172408 | 80.83% | 947652.19 | 7.63% | 89428.02 | 88.46% | 1037080.21 | 646.64 | 61.02 | 707.66
6.8 | Glazing | m2 | 12000 | 75.21 | 902520 | 83.56% | 754176.57 | 7.19% | 64935.96 | 90.76% | 819112.53 | 10027.61 | 863.4 | 10891.01
7 | External Works & Landscaping | LS | LS | - | 3269748.04 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 840.02 | 84002 | 68.43% | 57478.99 | 19.97% | 16771.99 | 88.39% | 74250.98 | 68.43 | 19.97 | 88.4
7.2 | Roadworks and Paving | m2 | 8000 | 227.46 | 1819680 | 70.01% | 1273993.15 | 21.21% | 385885.95 | 91.22% | 1659879.1 | 5600.95 | 1696.5 | 7297.45
7.3 | Kerbstone and Interlock | m2 | 7000 | 101.91 | 713370 | 64.91% | 463039.91 | 26.87% | 191717.07 | 91.78% | 654756.98 | 4543.62 | 1881.24 | 6424.86
7.4 | Landscaping | m3 | 1000 | 346.24 | 346240 | 62.21% | 215407.07 | 9.74% | 33710.28 | 71.95% | 249117.35 | 622.13 | 97.36 | 719.49
7.5 | Boundary Wall | m3 | 1000 | 265.92 | 265920 | 59.45% | 158099.79 | 21.91% | 58268.2 | 81.37% | 216367.99 | 594.54 | 219.12 | 813.66
8 | Final Works | LS | LS | - | 502725.34 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 189806.58 | 189806.58 | 41.81% | 79353.8 | 30.92% | 58697.37 | 72.73% | 138051.17 | 0.42 | 0.31 | 0.73
8.2 | Snagging & De-snagging | LS | 1 | 95426.85 | 95426.85 | 53.70% | 51239.57 | 32.06% | 30590.05 | 85.75% | 81829.62 | 0.54 | 0.32 | 0.86
8.3 | Cleaning | LS | 1 | 105734.2 | 105734.2 | 50.90% | 53821.59 | 32.39% | 34247.67 | 83.29% | 88069.26 | 0.51 | 0.32 | 0.83
8.4 | Handover | LS | 1 | 153457.58 | 153457.58 | 56.16% | 86177.53 | 33.67% | 51669.59 | 89.83% | 137847.12 | 0.56 | 0.34 | 0.9

## IPC_Jan_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 751137.34 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 51085.55 | 51085.55 | 52.60% | 26870.01 | 20.85% | 10649.96 | 73.45% | 37519.97 | 0.53 | 0.21 | 0.74
1.2 | Site Fencing and Hoarding | LS | 1 | 50495.98 | 50495.98 | 53.39% | 26960.59 | 10.79% | 5446.93 | 64.18% | 32407.52 | 0.53 | 0.11 | 0.64
1.3 | Temporary Facilities Setup | LS | 1 | 370088.81 | 370088.81 | 41.25% | 152649.82 | 29.63% | 109653.81 | 70.88% | 262303.63 | 0.41 | 0.3 | 0.71
1.4 | Soil Testing and Survey | LS | 1 | 193963.28 | 193963.28 | 41.01% | 79546.49 | 28.23% | 54763.76 | 69.25% | 134310.25 | 0.41 | 0.28 | 0.69
1.5 | Excavation | LS | 1 | 48430.26 | 48430.26 | 66.42% | 32168.72 | 13.84% | 6700.71 | 80.26% | 38869.43 | 0.66 | 0.14 | 0.8
1.6 | Dewatering | LS | 1 | 50388.87 | 50388.87 | 36.78% | 18530.6 | 31.08% | 15659.68 | 67.85% | 34190.28 | 0.37 | 0.31 | 0.68
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4122652.96 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 314.58 | 1572900 | 45.72% | 719125.38 | 18.63% | 293099.33 | 64.35% | 1012224.71 | 2285.99 | 931.72 | 3217.71
2.2 | Raft Foundation | m3 | 3500 | 234.94 | 822290 | 77.17% | 634589.74 | 11.38% | 93584.92 | 88.55% | 728174.66 | 2701.07 | 398.34 | 3099.41
2.3 | Basement Slab and Walls | m3 | 4000 | 398.82 | 1595280 | 54.34% | 866853.91 | 18.22% | 290590.78 | 72.55% | 1157444.69 | 2173.55 | 728.63 | 2902.18
3 | Superstructure | LS | LS | - | 3520207.24 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 366.02 | 175689.6 | 66.99% | 117702.74 | 25.21% | 44290.22 | 92.20% | 161992.96 | 321.57 | 121 | 442.57
3.2 | Vertical Elements | m3 | 3600 | 240.3 | 865080 | 44.21% | 382464.96 | 23.50% | 203307.02 | 67.71% | 585771.98 | 1591.61 | 846.06 | 2437.67
3.3 | Floor Slabs | m3 | 6000 | 254.96 | 1529760 | 44.29% | 677524.06 | 31.04% | 474834.18 | 75.33% | 1152358.24 | 2657.37 | 1862.39 | 4519.76
3.4 | Staircase Construction | m3 | 1000 | 315.4 | 315400 | 64.39% | 203071.03 | 9.98% | 31464.86 | 74.36% | 234535.89 | 643.85 | 99.76 | 743.61
3.5 | Lift Core Construction | m3 | 1000 | 202.7 | 202700 | 45.45% | 92124.67 | 25.63% | 51945.78 | 71.08% | 144070.45 | 454.49 | 256.27 | 710.76
3.6 | Roof Slab and Parapets | m3 | 360 | 247.49 | 89096.4 | 32.14% | 28633.04 | 30.48% | 27160.71 | 62.62% | 55793.75 | 115.69 | 109.74 | 225.43
4 | Masonry and Partitioning | LS | LS | - | 14580952.83 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 180.05 | 6301750 | 72.95% | 4597428.78 | 12.44% | 783773.62 | 85.39% | 5381202.4 | 25534.18 | 4353.09 | 29887.27
4.2 | Internal Blockwork | m2 | 35000 | 231.03 | 8086050 | 55.71% | 4504366.14 | 23.17% | 1873929.58 | 78.88% | 6378295.72 | 19496.89 | 8111.2 | 27608.09
4.3 | Drywall Partitioning | m3 | 1000 | 249.16 | 249160 | 52.09% | 129781.69 | 26.73% | 66597.4 | 78.82% | 196379.09 | 520.88 | 267.29 | 788.17
5 | MEP Works | LS | LS | - | 204652.11 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 51507.55 | 51507.55 | 40.04% | 20622.85 | 33.45% | 17228.6 | 73.49% | 37851.45 | 0.4 | 0.33 | 0.73
5.2 | Plumbing & Drainage | LS | 1 | 53311.44 | 53311.44 | 66.82% | 35624.43 | 9.01% | 4805.34 | 75.84% | 40429.77 | 0.67 | 0.09 | 0.76
5.3 | Firefighting Piping | LS | 1 | 52175.84 | 52175.84 | 50.89% | 26551.05 | 17.84% | 9310.45 | 68.73% | 35861.5 | 0.51 | 0.18 | 0.69
5.4 | HVAC Ducting | No. | 40 | 607.48 | 24299.2 | 44.18% | 10734.87 | 34.79% | 8454.7 | 78.97% | 19189.57 | 17.67 | 13.92 | 31.59
5.5 | Low Current Systems | LS | 1 | 49117.09 | 49117.09 | 53.45% | 26252.13 | 20.09% | 9867.77 | 73.54% | 36119.9 | 0.53 | 0.2 | 0.73
6 | Finishing Works | LS | LS | - | 15886312.64 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 53.38 | 1761540 | 55.30% | 974140.01 | 13.32% | 234721.15 | 68.63% | 1208861.16 | 18249.16 | 4397.17 | 22646.33
6.2 | Waterproofing | m2 | 5000 | 223.35 | 1116750 | 71.25% | 795720.6 | 9.77% | 109147.09 | 81.03% | 904867.69 | 3562.66 | 488.68 | 4051.34
6.3 | Tiling | m2 | 15000 | 255.8 | 3837000 | 53.07% | 2036458.63 | 26.05% | 999695.83 | 79.13% | 3036154.46 | 7961.14 | 3908.12 | 11869.26
6.4 | Painting | m2 | 40000 | 80.35 | 3214000 | 55.51% | 1784100.68 | 12.44% | 399850.07 | 67.95% | 2183950.75 | 22204.12 | 4976.35 | 27180.47
6.5 | Ceiling Works | m2 | 18000 | 149.27 | 2686860 | 81.93% | 2201441.72 | 9.87% | 265084.31 | 91.80% | 2466526.03 | 14748.05 | 1775.87 | 16523.92
6.6 | Joinery Installation | No. | 400 | 825.99 | 330396 | 71.40% | 235917.46 | 19.35% | 63931.03 | 90.75% | 299848.49 | 285.62 | 77.4 | 363.02
6.7 | Door & Window Installation | No. | 800 | 1426.23 | 1140984 | 65.58% | 748230.52 | 15.82% | 180522.89 | 81.40% | 928753.41 | 524.62 | 126.57 | 651.19
6.8 | Glazing | m2 | 12000 | 82.08 | 984960 | 33.53% | 330265.79 | 32.21% | 317232.37 | 65.74% | 647498.16 | 4023.71 | 3864.92 | 7888.63
7 | External Works & Landscaping | LS | LS | - | 3373721.55 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 860.5 | 86050 | 57.59% | 49551.97 | 22.12% | 19031.25 | 79.70% | 68583.22 | 57.59 | 22.12 | 79.71
7.2 | Roadworks and Paving | m2 | 8000 | 194.21 | 1553680 | 73.05% | 1135020.65 | 14.68% | 228041.48 | 87.73% | 1363062.13 | 5844.3 | 1174.2 | 7018.5
7.3 | Kerbstone and Interlock | m2 | 7000 | 100.45 | 703150 | 53.93% | 379197.63 | 10.28% | 72278.13 | 64.21% | 451475.76 | 3774.99 | 719.54 | 4494.53
7.4 | Landscaping | m3 | 1000 | 369.24 | 369240 | 70.18% | 259122.53 | 20.85% | 76997.77 | 91.03% | 336120.3 | 701.77 | 208.53 | 910.3
7.5 | Boundary Wall | m3 | 1000 | 275.05 | 275050 | 60.68% | 166909.95 | 11.55% | 31764.85 | 72.23% | 198674.8 | 606.83 | 115.49 | 722.32
8 | Final Works | LS | LS | - | 560152.6 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 183665.91 | 183665.91 | 50.13% | 92074.69 | 17.51% | 32161.49 | 67.64% | 124236.18 | 0.5 | 0.18 | 0.68
8.2 | Snagging & De-snagging | LS | 1 | 103844.69 | 103844.69 | 76.49% | 79430.69 | 13.03% | 13530.45 | 89.52% | 92961.14 | 0.76 | 0.13 | 0.89
8.3 | Cleaning | LS | 1 | 98818.57 | 98818.57 | 52.87% | 52249.92 | 24.59% | 24295.41 | 77.46% | 76545.33 | 0.53 | 0.25 | 0.78
8.4 | Handover | LS | 1 | 144606.12 | 144606.12 | 55.70% | 80541.85 | 17.48% | 25283.25 | 73.18% | 105825.1 | 0.56 | 0.17 | 0.73