## IPC_Jan_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 768552.71 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 48081.15 | 48081.15 |  | 0 | 17.39% | 8361.58 | 17.39% | 8361.58 | 0 | 0.17 | 0.17
1.2 | Site Fencing and Hoarding | LS | 1 | 52532.27 | 52532.27 |  | 0 | 35.36% | 18577.89 | 35.36% | 18577.89 | 0 | 0.35 | 0.35
1.3 | Temporary Facilities Setup | LS | 1 | 363571.37 | 363571.37 |  | 0 | 32.43% | 117920.28 | 32.43% | 117920.28 | 0 | 0.32 | 0.32
1.4 | Soil Testing and Survey | LS | 1 | 210409.29 | 210409.29 |  | 0 | 37.04% | 77942.19 | 37.04% | 77942.19 | 0 | 0.37 | 0.37
1.5 | Excavation | LS | 1 | 46981.83 | 46981.83 |  | 0 | 13.71% | 6443.07 | 13.71% | 6443.07 | 0 | 0.14 | 0.14
1.6 | Dewatering | LS | 1 | 50036.16 | 50036.16 |  | 0 | 12.40% | 6202.49 | 12.40% | 6202.49 | 0 | 0.12 | 0.12
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4188472.59 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 348.81 | 1744050 |  | 0 | 30.38% | 529795.85 | 30.38% | 529795.85 | 0 | 1518.87 | 1518.87
2.2 | Raft Foundation | m3 | 3500 | 276.6 | 968100 |  | 0 | 37.88% | 366672.47 | 37.88% | 366672.47 | 0 | 1325.64 | 1325.64
2.3 | Basement Slab and Walls | m3 | 4000 | 364.99 | 1459960 |  | 0 | 14.61% | 213285.27 | 14.61% | 213285.27 | 0 | 584.36 | 584.36
3 | Superstructure | LS | LS | - | 3203807.84 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 412.96 | 198220.8 |  | 0 | 20.27% | 40176.76 | 20.27% | 40176.76 | 0 | 97.29 | 97.29
3.2 | Vertical Elements | m3 | 3600 | 219.36 | 789696 |  | 0 | 39.31% | 310392.35 | 39.31% | 310392.35 | 0 | 1414.99 | 1414.99
3.3 | Floor Slabs | m3 | 6000 | 299.95 | 1799700 |  | 0 | 34.41% | 619348.41 | 34.41% | 619348.41 | 0 | 2064.84 | 2064.84
3.4 | Staircase Construction | m3 | 1000 | 312.35 | 312350 |  | 0 | 33.45% | 104489.14 | 33.45% | 104489.14 | 0 | 334.53 | 334.53
3.5 | Lift Core Construction | m3 | 1000 | 199.92 | 199920 |  | 0 | 24.80% | 49570.32 | 24.80% | 49570.32 | 0 | 247.95 | 247.95
3.6 | Roof Slab and Parapets | m3 | 360 | 248.38 | 89416.8 |  | 0 | 32.31% | 28892.46 | 32.31% | 28892.46 | 0 | 116.32 | 116.32
4 | Masonry and Partitioning | LS | LS | - | 13897459.12 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 171.86 | 6015100 |  | 0 | 24.05% | 1446668.94 | 24.05% | 1446668.94 | 0 | 8417.72 | 8417.72
4.2 | Internal Blockwork | m2 | 35000 | 247.43 | 8660050 |  | 0 | 19.63% | 1700024.35 | 19.63% | 1700024.35 | 0 | 6870.73 | 6870.73
4.3 | Drywall Partitioning | m3 | 1000 | 263.17 | 263170 |  | 0 | 26.04% | 68517.32 | 26.04% | 68517.32 | 0 | 260.35 | 260.35
5 | MEP Works | LS | LS | - | 240644.07 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 45857.9 | 45857.9 |  | 0 | 41.69% | 19120.05 | 41.69% | 19120.05 | 0 | 0.42 | 0.42
5.2 | Plumbing & Drainage | LS | 1 | 46498.34 | 46498.34 |  | 0 | 34.16% | 15882.46 | 34.16% | 15882.46 | 0 | 0.34 | 0.34
5.3 | Firefighting Piping | LS | 1 | 45133.79 | 45133.79 |  | 0 | 33.78% | 15245.89 | 33.78% | 15245.89 | 0 | 0.34 | 0.34
5.4 | HVAC Ducting | No. | 40 | 653.65 | 26146 |  | 0 | 35.81% | 9364.02 | 35.81% | 9364.02 | 0 | 14.33 | 14.33
5.5 | Low Current Systems | LS | 1 | 48560.4 | 48560.4 |  | 0 | 20.29% | 9854.51 | 20.29% | 9854.51 | 0 | 0.2 | 0.2
6 | Finishing Works | LS | LS | - | 15149282.39 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 50 | 1650000 |  | 0 | 38.20% | 630360.24 | 38.20% | 630360.24 | 0 | 12607.2 | 12607.2
6.2 | Waterproofing | m2 | 5000 | 254.56 | 1272800 |  | 0 | 20.25% | 257754.89 | 20.25% | 257754.89 | 0 | 1012.55 | 1012.55
6.3 | Tiling | m2 | 15000 | 229.47 | 3442050 |  | 0 | 33.56% | 1155187.83 | 33.56% | 1155187.83 | 0 | 5034.16 | 5034.16
6.4 | Painting | m2 | 40000 | 78.37 | 3134800 |  | 0 | 27.06% | 848300.26 | 27.06% | 848300.26 | 0 | 10824.3 | 10824.3
6.5 | Ceiling Works | m2 | 18000 | 125.14 | 2252520 |  | 0 | 13.61% | 306619.3 | 13.61% | 306619.3 | 0 | 2450.21 | 2450.21
6.6 | Joinery Installation | No. | 400 | 883.91 | 353564 |  | 0 | 24.42% | 86323.39 | 24.42% | 86323.39 | 0 | 97.66 | 97.66
6.7 | Door & Window Installation | No. | 800 | 1539.78 | 1231824 |  | 0 | 12.05% | 148483.26 | 12.05% | 148483.26 | 0 | 96.43 | 96.43
6.8 | Glazing | m2 | 12000 | 75.81 | 909720 |  | 0 | 13.87% | 126182.1 | 13.87% | 126182.1 | 0 | 1664.45 | 1664.45
7 | External Works & Landscaping | LS | LS | - | 3008160.46 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 761.89 | 76189 |  | 0 | 30.95% | 23579.33 | 30.95% | 23579.33 | 0 | 30.95 | 30.95
7.2 | Roadworks and Paving | m2 | 8000 | 194.05 | 1552400 |  | 0 | 32.12% | 498589.5 | 32.12% | 498589.5 | 0 | 2569.39 | 2569.39
7.3 | Kerbstone and Interlock | m2 | 7000 | 117.64 | 823480 |  | 0 | 22.56% | 185764.08 | 22.56% | 185764.08 | 0 | 1579.09 | 1579.09
7.4 | Landscaping | m3 | 1000 | 391.38 | 391380 |  | 0 | 22.68% | 88781.3 | 22.68% | 88781.3 | 0 | 226.84 | 226.84
7.5 | Boundary Wall | m3 | 1000 | 309.04 | 309040 |  | 0 | 12.97% | 40094.43 | 12.97% | 40094.43 | 0 | 129.74 | 129.74
8 | Final Works | LS | LS | - | 529708.23 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 198942.32 | 198942.32 |  | 0 | 38.89% | 77362.94 | 38.89% | 77362.94 | 0 | 0.39 | 0.39
8.2 | Snagging & De-snagging | LS | 1 | 96225.79 | 96225.79 |  | 0 | 32.24% | 31027.96 | 32.24% | 31027.96 | 0 | 0.32 | 0.32
8.3 | Cleaning | LS | 1 | 93675.28 | 93675.28 |  | 0 | 34.89% | 32681.74 | 34.89% | 32681.74 | 0 | 0.35 | 0.35
8.4 | Handover | LS | 1 | 154110.87 | 154110.87 |  | 0 | 24.64% | 37971.52 | 24.64% | 37971.52 | 0 | 0.25 | 0.25

## IPC_Feb_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 721669.6 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50950.52 | 50950.52 | 20.36% | 10375.35 | 30.01% | 15291.58 | 50.38% | 25666.93 | 0.2 | 0.3 | 0.5
1.2 | Site Fencing and Hoarding | LS | 1 | 47478.96 | 47478.96 | 33.14% | 15735.48 | 17.58% | 8344.75 | 50.72% | 24080.23 | 0.33 | 0.18 | 0.51
1.3 | Temporary Facilities Setup | LS | 1 | 390866.3 | 390866.3 | 22.11% | 86431.59 | 19.21% | 75067.85 | 41.32% | 161499.44 | 0.22 | 0.19 | 0.41
1.4 | Soil Testing and Survey | LS | 1 | 209967 | 209967 | 18.70% | 39272.73 | 8.30% | 17419.44 | 27.00% | 56692.17 | 0.19 | 0.08 | 0.27
1.5 | Excavation | LS | 1 | 53957.62 | 53957.62 | 31.01% | 16733.13 | 15.89% | 8571.58 | 46.90% | 25304.71 | 0.31 | 0.16 | 0.47
1.6 | Dewatering | LS | 1 | 54150.24 | 54150.24 | 27.32% | 14796.51 | 5.09% | 2756.14 | 32.41% | 17552.65 | 0.27 | 0.05 | 0.32
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3783766.63 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 324.01 | 1620050 | 17.50% | 283440.38 | 31.68% | 513290.14 | 49.18% | 796730.52 | 874.79 | 1584.18 | 2458.97
2.2 | Raft Foundation | m3 | 3500 | 260.6 | 912100 | 16.99% | 155003.01 | 24.87% | 226826.12 | 41.86% | 381829.13 | 594.79 | 870.4 | 1465.19
2.3 | Basement Slab and Walls | m3 | 4000 | 403.74 | 1614960 | 31.75% | 512829.66 | 11.64% | 188030.73 | 43.40% | 700860.39 | 1270.2 | 465.72 | 1735.92
3 | Superstructure | LS | LS | - | 2930020.42 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 367.07 | 176193.6 | 22.40% | 39473.25 | 21.63% | 38114.05 | 44.04% | 77587.3 | 107.54 | 103.83 | 211.37
3.2 | Vertical Elements | m3 | 3600 | 215.59 | 776124 | 12.93% | 100348.53 | 12.89% | 100069.21 | 25.82% | 200417.74 | 465.46 | 464.16 | 929.62
3.3 | Floor Slabs | m3 | 6000 | 297.98 | 1787880 | 14.96% | 267539.28 | 34.95% | 624896.14 | 49.92% | 892435.42 | 897.84 | 2097.11 | 2994.95
3.4 | Staircase Construction | m3 | 1000 | 263.64 | 263640 | 6.05% | 15938.86 | 20.49% | 54013.63 | 26.53% | 69952.49 | 60.46 | 204.88 | 265.34
3.5 | Lift Core Construction | m3 | 1000 | 191.99 | 191990 | 19.41% | 37257.16 | 7.61% | 14605.61 | 27.01% | 51862.77 | 194.06 | 76.07 | 270.13
3.6 | Roof Slab and Parapets | m3 | 360 | 264.69 | 95288.4 | 13.55% | 12911.67 | 29.93% | 28517.91 | 43.48% | 41429.58 | 48.78 | 107.74 | 156.52
4 | Masonry and Partitioning | LS | LS | - | 14634847.78 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 159.78 | 5592300 | 16.47% | 921047.05 | 9.21% | 515003.25 | 25.68% | 1436050.3 | 5764.47 | 3223.2 | 8987.67
4.2 | Internal Blockwork | m2 | 35000 | 245.72 | 8600200 | 0.98% | 84690.27 | 31.45% | 2704412.8 | 32.43% | 2789103.07 | 344.66 | 11006.08 | 11350.74
4.3 | Drywall Partitioning | m3 | 1000 | 255.38 | 255380 | 7.25% | 18510.42 | 17.43% | 44517.88 | 24.68% | 63028.3 | 72.48 | 174.32 | 246.8
5 | MEP Works | LS | LS | - | 227841.23 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 49442.17 | 49442.17 | 28.37% | 14027.36 | 14.75% | 7293.46 | 43.12% | 21320.82 | 0.28 | 0.15 | 0.43
5.2 | Plumbing & Drainage | LS | 1 | 48337.92 | 48337.92 | 13.39% | 6473.1 | 34.98% | 16908.25 | 48.37% | 23381.35 | 0.13 | 0.35 | 0.48
5.3 | Firefighting Piping | LS | 1 | 53841.83 | 53841.83 | 10.43% | 5614.48 | 32.41% | 17448.8 | 42.84% | 23063.28 | 0.1 | 0.32 | 0.42
5.4 | HVAC Ducting | No. | 40 | 637.69 | 25507.6 | 45.68% | 11652.45 | 6.86% | 1749.75 | 52.54% | 13402.2 | 18.27 | 2.74 | 21.01
5.5 | Low Current Systems | LS | 1 | 49861.04 | 49861.04 | 18.76% | 9356.05 | 16.40% | 8175.34 | 35.16% | 17531.39 | 0.19 | 0.16 | 0.35
6 | Finishing Works | LS | LS | - | 13884568.77 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 49.55 | 1635150 | 12.29% | 200894.22 | 16.76% | 274016.71 | 29.04% | 474910.93 | 4054.37 | 5530.11 | 9584.48
6.2 | Waterproofing | m2 | 5000 | 251.97 | 1259850 | 30.84% | 388551.17 | 18.19% | 229136.32 | 49.03% | 617687.49 | 1542.05 | 909.38 | 2451.43
6.3 | Tiling | m2 | 15000 | 256.09 | 3841350 |  | 0 | 22.78% | 875010.74 | 22.78% | 875010.74 | 0 | 3416.81 | 3416.81
6.4 | Painting | m2 | 40000 | 82.56 | 3302400 | 19.12% | 631291.5 | 19.89% | 656894.57 | 39.01% | 1288186.07 | 7646.46 | 7956.57 | 15603.03
6.5 | Ceiling Works | m2 | 18000 | 128.11 | 2305980 | 5.57% | 128372.23 | 34.02% | 784560.26 | 39.59% | 912932.49 | 1002.05 | 6124.11 | 7126.16
6.6 | Joinery Installation | No. | 400 | 871.35 | 348540 | 9.32% | 32488.79 | 13.61% | 47451.3 | 22.94% | 79940.09 | 37.29 | 54.46 | 91.75
6.7 | Door & Window Installation | No. | 800 | 1502.15 | 1201720 | 17.50% | 210346.57 | 6.83% | 82080.35 | 24.33% | 292426.92 | 140.03 | 54.64 | 194.67
6.8 | Glazing | m2 | 12000 | 85.55 | 1026600 | 20.41% | 209515.07 | 23.43% | 240509.01 | 43.84% | 450024.08 | 2449.04 | 2811.33 | 5260.37
7 | External Works & Landscaping | LS | LS | - | 3014497.66 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 890.42 | 89042 | 18.88% | 16810.95 | 22.57% | 20100.22 | 41.45% | 36911.17 | 18.88 | 22.57 | 41.45
7.2 | Roadworks and Paving | m2 | 8000 | 230.06 | 1840480 | 26.17% | 481562.05 | 18.17% | 334361.81 | 44.33% | 815923.86 | 2093.2 | 1453.37 | 3546.57
7.3 | Kerbstone and Interlock | m2 | 7000 | 108.3 | 758100 | 27.39% | 207619.91 | 21.74% | 164844.79 | 49.13% | 372464.7 | 1917.08 | 1522.11 | 3439.19
7.4 | Landscaping | m3 | 1000 | 396.33 | 396330 | 6.46% | 25601 | 24.99% | 99042.22 | 31.45% | 124643.22 | 64.6 | 249.9 | 314.5
7.5 | Boundary Wall | m3 | 1000 | 282.13 | 282130 | 34.65% | 97754.52 | 14.59% | 41176.08 | 49.24% | 138930.6 | 346.49 | 145.95 | 492.44
8 | Final Works | LS | LS | - | 601189.58 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 192891.96 | 192891.96 | 19.74% | 38078.9 | 12.11% | 23353.77 | 31.85% | 61432.67 | 0.2 | 0.12 | 0.32
8.2 | Snagging & De-snagging | LS | 1 | 95760.22 | 95760.22 | 30.33% | 29043.05 | 6.57% | 6287.15 | 36.89% | 35330.2 | 0.3 | 0.07 | 0.37
8.3 | Cleaning | LS | 1 | 101476.15 | 101476.15 | 23.33% | 23678.28 | 10.39% | 10544.64 | 33.73% | 34222.92 | 0.23 | 0.1 | 0.33
8.4 | Handover | LS | 1 | 164612.84 | 164612.84 | 40.35% | 66413.28 | 11.04% | 18172.88 | 51.38% | 84586.16 | 0.4 | 0.11 | 0.51

## IPC_Mar_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 787359.63 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 52511.21 | 52511.21 | 51.01% | 26786.95 | 24.26% | 12740.24 | 75.27% | 39527.19 | 0.51 | 0.24 | 0.75
1.2 | Site Fencing and Hoarding | LS | 1 | 47289.74 | 47289.74 | 65.15% | 30807.06 | 31.19% | 14749.73 | 96.34% | 45556.79 | 0.65 | 0.31 | 0.96
1.3 | Temporary Facilities Setup | LS | 1 | 398070.6 | 398070.6 | 59.65% | 237445.11 | 30.62% | 121885.86 | 90.27% | 359330.97 | 0.6 | 0.31 | 0.91
1.4 | Soil Testing and Survey | LS | 1 | 192545.98 | 192545.98 | 64.36% | 123920.74 | 20.82% | 40094.97 | 85.18% | 164015.71 | 0.64 | 0.21 | 0.85
1.5 | Excavation | LS | 1 | 48216.46 | 48216.46 | 53.98% | 26025.57 | 13.83% | 6666.76 | 67.80% | 32692.33 | 0.54 | 0.14 | 0.68
1.6 | Dewatering | LS | 1 | 47772.69 | 47772.69 | 70.37% | 33618.72 | 20.46% | 9775.16 | 90.83% | 43393.88 | 0.7 | 0.2 | 0.9
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3916801.47 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 342.35 | 1711750 | 69.47% | 1189177.02 | 16.94% | 290007.52 | 86.41% | 1479184.54 | 3473.57 | 847.11 | 4320.68
2.2 | Raft Foundation | m3 | 3500 | 281.8 | 986300 | 69.48% | 685246.1 | 20.86% | 205790.71 | 90.34% | 891036.81 | 2431.68 | 730.27 | 3161.95
2.3 | Basement Slab and Walls | m3 | 4000 | 392.21 | 1568840 | 43.27% | 678833.76 | 32.94% | 516739.86 | 76.21% | 1195573.62 | 1730.79 | 1317.51 | 3048.3
3 | Superstructure | LS | LS | - | 3235654.38 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 357.76 | 171724.8 | 57.81% | 99271.53 | 11.70% | 20086.05 | 69.51% | 119357.58 | 277.48 | 56.14 | 333.62
3.2 | Vertical Elements | m3 | 3600 | 241.1 | 867960 | 66.88% | 580459.27 | 5.46% | 47364.34 | 72.33% | 627823.61 | 2407.55 | 196.45 | 2604
3.3 | Floor Slabs | m3 | 6000 | 286.33 | 1717980 | 89.12% | 1531021.25 | 5.16% | 88728.29 | 94.28% | 1619749.54 | 5347.05 | 309.88 | 5656.93
3.4 | Staircase Construction | m3 | 1000 | 264.79 | 264790 | 86.01% | 227734.44 | 5.45% | 14443.23 | 91.46% | 242177.67 | 860.06 | 54.55 | 914.61
3.5 | Lift Core Construction | m3 | 1000 | 203.79 | 203790 | 74.00% | 150804.02 | 11.61% | 23657.24 | 85.61% | 174461.26 | 740 | 116.09 | 856.09
3.6 | Roof Slab and Parapets | m3 | 360 | 245.13 | 88246.8 | 65.39% | 57702.81 | 31.97% | 28215.21 | 97.36% | 85918.02 | 235.4 | 115.1 | 350.5
4 | Masonry and Partitioning | LS | LS | - | 15502832.34 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 165.14 | 5779900 | 64.72% | 3740669.83 | 20.56% | 1188071.96 | 85.27% | 4928741.79 | 22651.51 | 7194.33 | 29845.84
4.2 | Internal Blockwork | m2 | 35000 | 224.65 | 7862750 | 60.98% | 4794962.67 | 33.18% | 2609040.21 | 94.17% | 7404002.88 | 21344.15 | 11613.8 | 32957.95
4.3 | Drywall Partitioning | m3 | 1000 | 252.46 | 252460 | 39.43% | 99534.06 | 30.07% | 75916.64 | 69.50% | 175450.7 | 394.26 | 300.71 | 694.97
5 | MEP Works | LS | LS | - | 227523.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 51192.3 | 51192.3 | 52.77% | 27013.71 | 15.55% | 7962.41 | 68.32% | 34976.12 | 0.53 | 0.16 | 0.69
5.2 | Plumbing & Drainage | LS | 1 | 52008.85 | 52008.85 | 47.88% | 24900.67 | 31.24% | 16247.33 | 79.12% | 41148 | 0.48 | 0.31 | 0.79
5.3 | Firefighting Piping | LS | 1 | 47651 | 47651 | 44.81% | 21352.23 | 34.20% | 16294.34 | 79.00% | 37646.57 | 0.45 | 0.34 | 0.79
5.4 | HVAC Ducting | No. | 40 | 617.29 | 24691.6 | 52.73% | 13019.52 | 33.09% | 8171.12 | 85.82% | 21190.64 | 21.09 | 13.24 | 34.33
5.5 | Low Current Systems | LS | 1 | 54956.99 | 54956.99 | 58.34% | 32059.6 | 19.72% | 10835.48 | 78.05% | 42895.08 | 0.58 | 0.2 | 0.78
6 | Finishing Works | LS | LS | - | 13969923.47 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 59.93 | 1977690 | 73.20% | 1447600.06 | 16.13% | 318989.01 | 89.33% | 1766589.07 | 24154.85 | 5322.69 | 29477.54
6.2 | Waterproofing | m2 | 5000 | 224.45 | 1122250 | 68.29% | 766413.86 | 24.85% | 278915.2 | 93.15% | 1045329.06 | 3414.63 | 1242.66 | 4657.29
6.3 | Tiling | m2 | 15000 | 232.62 | 3489300 | 57.19% | 1995594.14 | 17.56% | 612794.58 | 74.75% | 2608388.72 | 8578.77 | 2634.32 | 11213.09
6.4 | Painting | m2 | 40000 | 92.75 | 3710000 | 47.51% | 1762580.07 | 28.39% | 1053418.9 | 75.90% | 2815998.97 | 19003.56 | 11357.62 | 30361.18
6.5 | Ceiling Works | m2 | 18000 | 128.87 | 2319660 | 68.47% | 1588165.5 | 15.02% | 348355.75 | 83.48% | 1936521.25 | 12323.78 | 2703.16 | 15026.94
6.6 | Joinery Installation | No. | 400 | 800.26 | 320104 | 84.46% | 270371.71 | 12.42% | 39762.99 | 96.89% | 310134.7 | 337.85 | 49.69 | 387.54
6.7 | Door & Window Installation | No. | 800 | 1279.27 | 1023416 | 67.82% | 694071.01 | 8.12% | 83086.95 | 75.94% | 777157.96 | 542.55 | 64.95 | 607.5
6.8 | Glazing | m2 | 12000 | 74.03 | 888360 | 65.28% | 579903.43 | 12.54% | 111400.06 | 77.82% | 691303.49 | 7833.36 | 1504.8 | 9338.16
7 | External Works & Landscaping | LS | LS | - | 2917335.77 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 899.59 | 89959 | 82.88% | 74559.81 | 13.47% | 12117.91 | 96.35% | 86677.72 | 82.88 | 13.47 | 96.35
7.2 | Roadworks and Paving | m2 | 8000 | 210.19 | 1681520 | 88.22% | 1483430.44 | 8.69% | 146067.44 | 96.91% | 1629497.88 | 7057.57 | 694.93 | 7752.5
7.3 | Kerbstone and Interlock | m2 | 7000 | 111.49 | 780430 | 36.00% | 280962.14 | 34.84% | 271917.98 | 70.84% | 552880.12 | 2520.07 | 2438.95 | 4959.02
7.4 | Landscaping | m3 | 1000 | 416.71 | 416710 | 86.26% | 359457.98 | 9.20% | 38317.68 | 95.46% | 397775.66 | 862.61 | 91.95 | 954.56
7.5 | Boundary Wall | m3 | 1000 | 277.7 | 277700 | 55.54% | 154226.25 | 19.42% | 53941.71 | 74.96% | 208167.96 | 555.37 | 194.24 | 749.61
8 | Final Works | LS | LS | - | 546707.54 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 180510.57 | 180510.57 | 65.17% | 117630.95 | 7.78% | 14052.07 | 72.95% | 131683.02 | 0.65 | 0.08 | 0.73
8.2 | Snagging & De-snagging | LS | 1 | 107919.48 | 107919.48 | 44.08% | 47566.69 | 31.71% | 34225.55 | 75.79% | 81792.24 | 0.44 | 0.32 | 0.76
8.3 | Cleaning | LS | 1 | 99909.92 | 99909.92 | 59.53% | 59479.23 | 34.89% | 34863.55 | 94.43% | 94342.78 | 0.6 | 0.35 | 0.95
8.4 | Handover | LS | 1 | 152022.85 | 152022.85 | 60.56% | 92068.47 | 12.03% | 18285.8 | 72.59% | 110354.27 | 0.61 | 0.12 | 0.73

## IPC_Apr_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 768867.01 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 48009.05 | 48009.05 | 67.04% | 32185.18 | 23.08% | 11079.21 | 90.12% | 43264.39 | 0.67 | 0.23 | 0.9
1.2 | Site Fencing and Hoarding | LS | 1 | 50368.83 | 50368.83 | 69.23% | 34870.79 | 24.16% | 12171.43 | 93.40% | 47042.22 | 0.69 | 0.24 | 0.93
1.3 | Temporary Facilities Setup | LS | 1 | 415242.49 | 415242.49 | 93.51% | 388306.75 | 6.49% | 26935.74 | 100.00% | 415242.49 | 0.94 | 0.06 | 1
1.4 | Soil Testing and Survey | LS | 1 | 219469.8 | 219469.8 | 74.58% | 163689.81 | 11.78% | 25860.81 | 86.37% | 189550.62 | 0.75 | 0.12 | 0.87
1.5 | Excavation | LS | 1 | 48106.57 | 48106.57 | 73.46% | 35340.74 | 26.54% | 12765.83 | 100.00% | 48106.57 | 0.73 | 0.27 | 1
1.6 | Dewatering | LS | 1 | 47026.82 | 47026.82 | 86.08% | 40482.39 | 13.92% | 6544.43 | 100.00% | 47026.82 | 0.86 | 0.14 | 1
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3864176.04 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 341.54 | 1707700 | 75.57% | 1290472.14 | 24.43% | 417227.86 | 100.00% | 1707700 | 3778.39 | 1221.61 | 5000
2.2 | Raft Foundation | m3 | 3500 | 261.67 | 915845 | 78.48% | 718779.78 | 21.52% | 197065.22 | 100.00% | 915845 | 2746.89 | 753.11 | 3500
2.3 | Basement Slab and Walls | m3 | 4000 | 381.16 | 1524640 | 82.04% | 1250794.72 | 17.96% | 273845.28 | 100.00% | 1524640 | 3281.55 | 718.45 | 4000
3 | Superstructure | LS | LS | - | 3098049.76 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 383.1 | 183888 | 57.88% | 106431.61 | 30.06% | 55276.27 | 87.94% | 161707.88 | 277.82 | 144.29 | 422.11
3.2 | Vertical Elements | m3 | 3600 | 227.06 | 817416 | 68.09% | 556613.73 | 31.91% | 260802.27 | 100.00% | 817416 | 2451.39 | 1148.61 | 3600
3.3 | Floor Slabs | m3 | 6000 | 293.09 | 1758540 | 70.45% | 1238960.24 | 29.55% | 519579.76 | 100.00% | 1758540 | 4227.23 | 1772.77 | 6000
3.4 | Staircase Construction | m3 | 1000 | 263.31 | 263310 | 68.62% | 180681.78 | 31.38% | 82628.22 | 100.00% | 263310 | 686.19 | 313.81 | 1000
3.5 | Lift Core Construction | m3 | 1000 | 213.72 | 213720 | 79.22% | 169306.59 | 14.94% | 31938.63 | 94.16% | 201245.22 | 792.19 | 149.44 | 941.63
3.6 | Roof Slab and Parapets | m3 | 360 | 248 | 89280 | 70.70% | 63122.69 | 25.10% | 22411.45 | 95.80% | 85534.14 | 254.53 | 90.37 | 344.9
4 | Masonry and Partitioning | LS | LS | - | 14429939.32 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 184.93 | 6472550 | 68.26% | 4418251.08 | 30.02% | 1943176.52 | 98.28% | 6361427.6 | 23891.48 | 10507.63 | 34399.11
4.2 | Internal Blockwork | m2 | 35000 | 254.52 | 8908200 | 63.58% | 5663962.76 | 29.84% | 2658386.49 | 93.42% | 8322349.25 | 22253.51 | 10444.71 | 32698.22
4.3 | Drywall Partitioning | m3 | 1000 | 257.61 | 257610 | 72.94% | 187901.83 | 27.06% | 69708.17 | 100.00% | 257610 | 729.4 | 270.6 | 1000
5 | MEP Works | LS | LS | - | 246341.07 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 49391.57 | 49391.57 | 69.36% | 34259.1 | 30.64% | 15132.47 | 100.00% | 49391.57 | 0.69 | 0.31 | 1
5.2 | Plumbing & Drainage | LS | 1 | 46816.97 | 46816.97 | 91.49% | 42831.76 | 8.51% | 3985.21 | 100.00% | 46816.97 | 0.91 | 0.09 | 1
5.3 | Firefighting Piping | LS | 1 | 49138.43 | 49138.43 | 71.08% | 34925.53 | 28.92% | 14212.9 | 100.00% | 49138.43 | 0.71 | 0.29 | 1
5.4 | HVAC Ducting | No. | 40 | 579.11 | 23164.4 | 63.65% | 14744.4 | 32.95% | 7633.56 | 96.60% | 22377.96 | 25.46 | 13.18 | 38.64
5.5 | Low Current Systems | LS | 1 | 54819.43 | 54819.43 | 81.45% | 44647.93 | 16.41% | 8994.45 | 97.85% | 53642.38 | 0.81 | 0.16 | 0.97
6 | Finishing Works | LS | LS | - | 13937599.68 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 57.85 | 1909050 | 76.91% | 1468291.86 | 23.09% | 440758.14 | 100.00% | 1909050 | 25381.02 | 7618.98 | 33000
6.2 | Waterproofing | m2 | 5000 | 235.03 | 1175150 | 54.79% | 643806.9 | 33.61% | 394946.11 | 88.39% | 1038753.01 | 2739.25 | 1680.41 | 4419.66
6.3 | Tiling | m2 | 15000 | 255.69 | 3835350 | 78.12% | 2996161.93 | 21.88% | 839188.07 | 100.00% | 3835350 | 11717.95 | 3282.05 | 15000
6.4 | Painting | m2 | 40000 | 84.25 | 3370000 | 81.88% | 2759463.12 | 8.24% | 277617.02 | 90.12% | 3037080.14 | 32753.27 | 3295.16 | 36048.43
6.5 | Ceiling Works | m2 | 18000 | 128.39 | 2311020 | 74.28% | 1716565.23 | 18.01% | 416291.97 | 92.29% | 2132857.2 | 13369.93 | 3242.4 | 16612.33
6.6 | Joinery Installation | No. | 400 | 812.59 | 325036 | 70.76% | 230006.25 | 29.24% | 95029.75 | 100.00% | 325036 | 283.05 | 116.95 | 400
6.7 | Door & Window Installation | No. | 800 | 1400.69 | 1120552 | 73.70% | 825842.22 | 18.14% | 203267.49 | 91.84% | 1029109.71 | 589.6 | 145.12 | 734.72
6.8 | Glazing | m2 | 12000 | 75.53 | 906360 | 66.80% | 605447.44 | 33.20% | 300912.56 | 100.00% | 906360 | 8015.99 | 3984.01 | 12000
7 | External Works & Landscaping | LS | LS | - | 2950201.15 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 791.26 | 79126 | 81.73% | 64673.52 | 18.27% | 14452.48 | 100.00% | 79126 | 81.73 | 18.27 | 100
7.2 | Roadworks and Paving | m2 | 8000 | 227.6 | 1820800 | 59.34% | 1080536.7 | 33.19% | 604252.53 | 92.53% | 1684789.23 | 4747.53 | 2654.89 | 7402.42
7.3 | Kerbstone and Interlock | m2 | 7000 | 113.95 | 797650 | 75.00% | 598204.16 | 15.74% | 125588.35 | 90.74% | 723792.51 | 5249.71 | 1102.14 | 6351.85
7.4 | Landscaping | m3 | 1000 | 368.04 | 368040 | 78.66% | 289492.75 | 6.71% | 24705.99 | 85.37% | 314198.74 | 786.58 | 67.13 | 853.71
7.5 | Boundary Wall | m3 | 1000 | 295.55 | 295550 | 88.28% | 260922.8 | 11.72% | 34627.2 | 100.00% | 295550 | 882.84 | 117.16 | 1000
8 | Final Works | LS | LS | - | 495913.9 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 213231.3 | 213231.3 | 60.84% | 129730.13 | 26.25% | 55977.75 | 87.09% | 185707.88 | 0.61 | 0.26 | 0.87
8.2 | Snagging & De-snagging | LS | 1 | 93298.56 | 93298.56 | 82.09% | 76588.72 | 17.91% | 16709.84 | 100.00% | 93298.56 | 0.82 | 0.18 | 1
8.3 | Cleaning | LS | 1 | 93599.16 | 93599.16 | 82.86% | 77557.21 | 17.14% | 16041.95 | 100.00% | 93599.16 | 0.83 | 0.17 | 1
8.4 | Handover | LS | 1 | 151828.5 | 151828.5 | 73.64% | 111808.29 | 26.36% | 40020.21 | 100.00% | 151828.5 | 0.74 | 0.26 | 1