## IPC_Apr_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 831308.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 49060.02 | 49060.02 |  | 0 | 31.13% | 15273.01 | 31.13% | 15273.01 | 0 | 0.31 | 0.31
1.2 | Site Fencing and Hoarding | LS | 1 | 48498.26 | 48498.26 |  | 0 | 29.88% | 14493.19 | 29.88% | 14493.19 | 0 | 0.3 | 0.3
1.3 | Temporary Facilities Setup | LS | 1 | 420488.15 | 420488.15 |  | 0 | 33.72% | 141788.78 | 33.72% | 141788.78 | 0 | 0.34 | 0.34
1.4 | Soil Testing and Survey | LS | 1 | 181986.65 | 181986.65 |  | 0 | 9.64% | 17534.45 | 9.64% | 17534.45 | 0 | 0.1 | 0.1
1.5 | Excavation | LS | 1 | 45540.12 | 45540.12 |  | 0 | 22.50% | 10245.55 | 22.50% | 10245.55 | 0 | 0.22 | 0.22
1.6 | Dewatering | LS | 1 | 46729.96 | 46729.96 |  | 0 | 25.70% | 12008.43 | 25.70% | 12008.43 | 0 | 0.26 | 0.26
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4278700.3 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 361.47 | 1807350 |  | 0 | 19.71% | 356219.81 | 19.71% | 356219.81 | 0 | 985.48 | 985.48
2.2 | Raft Foundation | m3 | 3500 | 261.99 | 916965 |  | 0 | 18.58% | 170412.16 | 18.58% | 170412.16 | 0 | 650.45 | 650.45
2.3 | Basement Slab and Walls | m3 | 4000 | 389.27 | 1557080 |  | 0 | 11.91% | 185493.56 | 11.91% | 185493.56 | 0 | 476.52 | 476.52
3 | Superstructure | LS | LS | - | 3221561.01 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 428.2 | 205536 |  | 0 | 27.91% | 57361.2 | 27.91% | 57361.2 | 0 | 133.96 | 133.96
3.2 | Vertical Elements | m3 | 3600 | 231.43 | 833148 |  | 0 | 18.82% | 156816.93 | 18.82% | 156816.93 | 0 | 677.6 | 677.6
3.3 | Floor Slabs | m3 | 6000 | 303.58 | 1821480 |  | 0 | 19.46% | 354478.87 | 19.46% | 354478.87 | 0 | 1167.66 | 1167.66
3.4 | Staircase Construction | m3 | 1000 | 312.46 | 312460 |  | 0 | 34.55% | 107939.45 | 34.55% | 107939.45 | 0 | 345.45 | 345.45
3.5 | Lift Core Construction | m3 | 1000 | 205.57 | 205570 |  | 0 | 25.03% | 51446.45 | 25.03% | 51446.45 | 0 | 250.26 | 250.26
3.6 | Roof Slab and Parapets | m3 | 360 | 265.07 | 95425.2 |  | 0 | 32.22% | 30750.67 | 32.22% | 30750.67 | 0 | 116.01 | 116.01
4 | Masonry and Partitioning | LS | LS | - | 13989033.18 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 174.88 | 6120800 |  | 0 | 25.69% | 1572290.75 | 25.69% | 1572290.75 | 0 | 8990.68 | 8990.68
4.2 | Internal Blockwork | m2 | 35000 | 238.17 | 8335950 |  | 0 | 23.42% | 1952628.74 | 23.42% | 1952628.74 | 0 | 8198.47 | 8198.47
4.3 | Drywall Partitioning | m3 | 1000 | 259.04 | 259040 |  | 0 | 27.84% | 72111.13 | 27.84% | 72111.13 | 0 | 278.38 | 278.38
5 | MEP Works | LS | LS | - | 215326.69 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 47939.27 | 47939.27 |  | 0 | 36.41% | 17452.51 | 36.41% | 17452.51 | 0 | 0.36 | 0.36
5.2 | Plumbing & Drainage | LS | 1 | 53989.49 | 53989.49 |  | 0 | 18.35% | 9908.79 | 18.35% | 9908.79 | 0 | 0.18 | 0.18
5.3 | Firefighting Piping | LS | 1 | 54954.76 | 54954.76 |  | 0 | 21.70% | 11923.01 | 21.70% | 11923.01 | 0 | 0.22 | 0.22
5.4 | HVAC Ducting | No. | 40 | 569.8 | 22792 |  | 0 | 25.14% | 5729.64 | 25.14% | 5729.64 | 0 | 10.06 | 10.06
5.5 | Low Current Systems | LS | 1 | 46400.19 | 46400.19 |  | 0 | 35.37% | 16411.29 | 35.37% | 16411.29 | 0 | 0.35 | 0.35
6 | Finishing Works | LS | LS | - | 14545763.06 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 56.52 | 1865160 |  | 0 | 8.76% | 163318.06 | 8.76% | 163318.06 | 0 | 2889.56 | 2889.56
6.2 | Waterproofing | m2 | 5000 | 223.53 | 1117650 |  | 0 | 32.80% | 366575.26 | 32.80% | 366575.26 | 0 | 1639.94 | 1639.94
6.3 | Tiling | m2 | 15000 | 225.15 | 3377250 |  | 0 | 20.74% | 700485.8 | 20.74% | 700485.8 | 0 | 3111.2 | 3111.2
6.4 | Painting | m2 | 40000 | 85.92 | 3436800 |  | 0 | 13.76% | 472964.95 | 13.76% | 472964.95 | 0 | 5504.71 | 5504.71
6.5 | Ceiling Works | m2 | 18000 | 148.22 | 2667960 |  | 0 | 30.24% | 806714.5 | 30.24% | 806714.5 | 0 | 5442.68 | 5442.68
6.6 | Joinery Installation | No. | 400 | 890.08 | 356032 |  | 0 | 31.15% | 110906.34 | 31.15% | 110906.34 | 0 | 124.6 | 124.6
6.7 | Door & Window Installation | No. | 800 | 1381.11 | 1104888 |  | 0 | 15.99% | 176675.71 | 15.99% | 176675.71 | 0 | 127.92 | 127.92
6.8 | Glazing | m2 | 12000 | 71.86 | 862320 |  | 0 | 16.92% | 145892.47 | 16.92% | 145892.47 | 0 | 2030.23 | 2030.23
7 | External Works & Landscaping | LS | LS | - | 3247534.59 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 833.2 | 83320 |  | 0 | 10.45% | 8706.71 | 10.45% | 8706.71 | 0 | 10.45 | 10.45
7.2 | Roadworks and Paving | m2 | 8000 | 196.14 | 1569120 |  | 0 | 20.84% | 327003.26 | 20.84% | 327003.26 | 0 | 1667.19 | 1667.19
7.3 | Kerbstone and Interlock | m2 | 7000 | 105.83 | 740810 |  | 0 | 15.26% | 113037.42 | 15.26% | 113037.42 | 0 | 1068.1 | 1068.1
7.4 | Landscaping | m3 | 1000 | 395.7 | 395700 |  | 0 | 17.51% | 69297.6 | 17.51% | 69297.6 | 0 | 175.13 | 175.13
7.5 | Boundary Wall | m3 | 1000 | 261.35 | 261350 |  | 0 | 18.82% | 49174.28 | 18.82% | 49174.28 | 0 | 188.15 | 188.15
8 | Final Works | LS | LS | - | 570908.09 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 198594.04 | 198594.04 |  | 0 | 35.00% | 69515.21 | 35.00% | 69515.21 | 0 | 0.35 | 0.35
8.2 | Snagging & De-snagging | LS | 1 | 100732.29 | 100732.29 |  | 0 | 8.77% | 8838.58 | 8.77% | 8838.58 | 0 | 0.09 | 0.09
8.3 | Cleaning | LS | 1 | 109804.06 | 109804.06 |  | 0 | 17.61% | 19341.4 | 17.61% | 19341.4 | 0 | 0.18 | 0.18
8.4 | Handover | LS | 1 | 154357.93 | 154357.93 |  | 0 | 14.55% | 22452.69 | 14.55% | 22452.69 | 0 | 0.15 | 0.15

## IPC_May_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 725950.22 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 45649.56 | 45649.56 | 46.70% | 21316.37 | 20.76% | 9476.07 | 67.45% | 30792.44 | 0.47 | 0.21 | 0.68
1.2 | Site Fencing and Hoarding | LS | 1 | 49634.33 | 49634.33 | 25.46% | 12639.18 | 23.08% | 11456.66 | 48.55% | 24095.84 | 0.25 | 0.23 | 0.48
1.3 | Temporary Facilities Setup | LS | 1 | 373880.31 | 373880.31 | 17.38% | 64987.63 | 29.04% | 108583.26 | 46.42% | 173570.89 | 0.17 | 0.29 | 0.46
1.4 | Soil Testing and Survey | LS | 1 | 181076.42 | 181076.42 | 21.21% | 38407.25 | 25.66% | 46466.49 | 46.87% | 84873.74 | 0.21 | 0.26 | 0.47
1.5 | Excavation | LS | 1 | 45338.44 | 45338.44 | 28.79% | 13054.89 | 18.79% | 8518.95 | 47.58% | 21573.84 | 0.29 | 0.19 | 0.48
1.6 | Dewatering | LS | 1 | 45692.28 | 45692.28 | 11.96% | 5466.34 | 33.68% | 15387.64 | 45.64% | 20853.98 | 0.12 | 0.34 | 0.46
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4343793.36 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 319 | 1595000 | 47.93% | 764477.88 | 12.41% | 197943.02 | 60.34% | 962420.9 | 2396.48 | 620.51 | 3016.99
2.2 | Raft Foundation | m3 | 3500 | 279.54 | 978390 | 50.08% | 489946.38 | 16.21% | 158639.47 | 66.29% | 648585.85 | 1752.69 | 567.5 | 2320.19
2.3 | Basement Slab and Walls | m3 | 4000 | 413.41 | 1653640 | 40.36% | 667420.16 | 21.95% | 362904.76 | 62.31% | 1030324.92 | 1614.43 | 877.83 | 2492.26
3 | Superstructure | LS | LS | - | 3316679.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 353.42 | 169641.6 | 39.76% | 67454.24 | 33.45% | 56748.3 | 73.21% | 124202.54 | 190.86 | 160.57 | 351.43
3.2 | Vertical Elements | m3 | 3600 | 240.25 | 864900 | 26.50% | 229195.06 | 20.31% | 175639.06 | 46.81% | 404834.12 | 953.99 | 731.07 | 1685.06
3.3 | Floor Slabs | m3 | 6000 | 255.05 | 1530300 | 40.23% | 615692.09 | 26.71% | 408738.47 | 66.94% | 1024430.56 | 2414.01 | 1602.58 | 4016.59
3.4 | Staircase Construction | m3 | 1000 | 300.57 | 300570 | 51.24% | 154021.58 | 8.89% | 26719.3 | 60.13% | 180740.88 | 512.43 | 88.9 | 601.33
3.5 | Lift Core Construction | m3 | 1000 | 202.75 | 202750 | 53.83% | 109148.76 | 13.08% | 26526.39 | 66.92% | 135675.15 | 538.34 | 130.83 | 669.17
3.6 | Roof Slab and Parapets | m3 | 360 | 256.87 | 92473.2 | 49.79% | 46046.33 | 21.23% | 19634.13 | 71.03% | 65680.46 | 179.26 | 76.44 | 255.7
4 | Masonry and Partitioning | LS | LS | - | 14176414.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 186.78 | 6537300 | 30.67% | 2004760.88 | 22.64% | 1480258.16 | 53.31% | 3485019.04 | 10733.27 | 7925.14 | 18658.41
4.2 | Internal Blockwork | m2 | 35000 | 222.7 | 7794500 | 39.66% | 3090993.54 | 6.08% | 473523.64 | 45.73% | 3564517.18 | 13879.63 | 2126.28 | 16005.91
4.3 | Drywall Partitioning | m3 | 1000 | 249.7 | 249700 | 28.08% | 70106.7 | 33.76% | 84300.85 | 61.84% | 154407.55 | 280.76 | 337.61 | 618.37
5 | MEP Works | LS | LS | - | 235540.58 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 46226.37 | 46226.37 | 47.99% | 22184.5 | 21.90% | 10124.58 | 69.89% | 32309.08 | 0.48 | 0.22 | 0.7
5.2 | Plumbing & Drainage | LS | 1 | 53566.91 | 53566.91 | 54.02% | 28934.98 | 6.16% | 3299.05 | 60.18% | 32234.03 | 0.54 | 0.06 | 0.6
5.3 | Firefighting Piping | LS | 1 | 45225.34 | 45225.34 | 29.69% | 13428.06 | 29.61% | 13392.5 | 59.30% | 26820.56 | 0.3 | 0.3 | 0.6
5.4 | HVAC Ducting | No. | 40 | 600.73 | 24029.2 | 44.83% | 10771.48 | 21.24% | 5103.76 | 66.07% | 15875.24 | 17.93 | 8.5 | 26.43
5.5 | Low Current Systems | LS | 1 | 48981.11 | 48981.11 | 18.70% | 9159.3 | 32.87% | 16101.8 | 51.57% | 25261.1 | 0.19 | 0.33 | 0.52
6 | Finishing Works | LS | LS | - | 14302832.75 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 58.13 | 1918290 | 52.03% | 998046.92 | 14.16% | 271723.57 | 66.19% | 1269770.49 | 17169.22 | 4674.41 | 21843.63
6.2 | Waterproofing | m2 | 5000 | 259.81 | 1299050 | 44.54% | 578613.69 | 16.04% | 208318.6 | 60.58% | 786932.29 | 2227.06 | 801.81 | 3028.87
6.3 | Tiling | m2 | 15000 | 255.33 | 3829950 | 38.88% | 1488947.49 | 25.08% | 960473.77 | 63.95% | 2449421.26 | 5831.46 | 3761.7 | 9593.16
6.4 | Painting | m2 | 40000 | 81.58 | 3263200 | 39.25% | 1280794.8 | 11.98% | 391064.31 | 51.23% | 1671859.11 | 15699.86 | 4793.63 | 20493.49
6.5 | Ceiling Works | m2 | 18000 | 150.19 | 2703420 | 38.05% | 1028541.41 | 25.91% | 700509.74 | 63.96% | 1729051.15 | 6848.27 | 4664.16 | 11512.43
6.6 | Joinery Installation | No. | 400 | 786.46 | 314584 | 34.33% | 107989.66 | 18.02% | 56693.66 | 52.35% | 164683.32 | 137.31 | 72.09 | 209.4
6.7 | Door & Window Installation | No. | 800 | 1492.96 | 1194368 | 38.27% | 457116.98 | 25.70% | 307011.75 | 63.98% | 764128.73 | 306.18 | 205.64 | 511.82
6.8 | Glazing | m2 | 12000 | 86.52 | 1038240 | 52.67% | 546892.8 | 8.91% | 92465.72 | 61.58% | 639358.52 | 6321 | 1068.72 | 7389.72
7 | External Works & Landscaping | LS | LS | - | 3303904.18 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 900.64 | 90064 | 29.92% | 26945.1 | 16.03% | 14440.43 | 45.95% | 41385.53 | 29.92 | 16.03 | 45.95
7.2 | Roadworks and Paving | m2 | 8000 | 218.8 | 1750400 | 25.90% | 453438.9 | 27.93% | 488823.33 | 53.83% | 942262.23 | 2072.39 | 2234.11 | 4306.5
7.3 | Kerbstone and Interlock | m2 | 7000 | 104.11 | 728770 | 60.84% | 443407.8 | 12.33% | 89839.94 | 73.17% | 533247.74 | 4259.03 | 862.93 | 5121.96
7.4 | Landscaping | m3 | 1000 | 405.6 | 405600 | 42.60% | 172767.19 | 25.88% | 104971.06 | 68.48% | 277738.25 | 425.95 | 258.8 | 684.75
7.5 | Boundary Wall | m3 | 1000 | 275.95 | 275950 | 49.65% | 137007.37 | 19.00% | 52419.31 | 68.65% | 189426.68 | 496.49 | 189.96 | 686.45
8 | Final Works | LS | LS | - | 512533.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 199837.56 | 199837.56 | 49.64% | 99203.05 | 5.97% | 11934.15 | 55.61% | 111137.2 | 0.5 | 0.06 | 0.56
8.2 | Snagging & De-snagging | LS | 1 | 100368.93 | 100368.93 | 62.72% | 62950.72 | 7.61% | 7634.29 | 70.33% | 70585.01 | 0.63 | 0.08 | 0.71
8.3 | Cleaning | LS | 1 | 94950.33 | 94950.33 | 24.68% | 23433.6 | 24.86% | 23600.82 | 49.54% | 47034.42 | 0.25 | 0.25 | 0.5
8.4 | Handover | LS | 1 | 142009.92 | 142009.92 | 33.36% | 47370.01 | 12.63% | 17932.04 | 45.98% | 65302.05 | 0.33 | 0.13 | 0.46

## IPC_Jun_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 723289.31 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 51518.23 | 51518.23 | 84.07% | 43309.96 | 13.42% | 6911.17 | 97.48% | 50221.13 | 0.84 | 0.13 | 0.97
1.2 | Site Fencing and Hoarding | LS | 1 | 45665.88 | 45665.88 | 55.83% | 25494.6 | 21.77% | 9939.76 | 77.59% | 35434.36 | 0.56 | 0.22 | 0.78
1.3 | Temporary Facilities Setup | LS | 1 | 401226.09 | 401226.09 | 58.61% | 235169.88 | 29.07% | 116616.71 | 87.68% | 351786.59 | 0.59 | 0.29 | 0.88
1.4 | Soil Testing and Survey | LS | 1 | 189319.92 | 189319.92 | 64.05% | 121265.47 | 20.03% | 37914.38 | 84.08% | 159179.85 | 0.64 | 0.2 | 0.84
1.5 | Excavation | LS | 1 | 54529.52 | 54529.52 | 42.68% | 23271.2 | 30.49% | 16627.74 | 73.17% | 39898.94 | 0.43 | 0.3 | 0.73
1.6 | Dewatering | LS | 1 | 46224.32 | 46224.32 | 71.83% | 33202.45 | 6.55% | 3026.43 | 78.38% | 36228.88 | 0.72 | 0.07 | 0.79
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4190907.6 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 333.2 | 1666000 | 61.04% | 1016922.14 | 14.58% | 242899.89 | 75.62% | 1259822.03 | 3051.99 | 728.99 | 3780.98
2.2 | Raft Foundation | m3 | 3500 | 243.11 | 850885 | 51.20% | 435670.79 | 21.80% | 185532.63 | 73.01% | 621203.42 | 1792.07 | 763.16 | 2555.23
2.3 | Basement Slab and Walls | m3 | 4000 | 352.11 | 1408440 | 66.26% | 933295.48 | 5.40% | 76032.35 | 71.66% | 1009327.83 | 2650.58 | 215.93 | 2866.51
3 | Superstructure | LS | LS | - | 3146331.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 368.29 | 176779.2 | 77.46% | 136928.67 | 7.15% | 12647.24 | 84.61% | 149575.91 | 371.8 | 34.34 | 406.14
3.2 | Vertical Elements | m3 | 3600 | 228.7 | 823320 | 77.90% | 641368.48 | 14.30% | 117707.07 | 92.20% | 759075.55 | 2804.41 | 514.68 | 3319.09
3.3 | Floor Slabs | m3 | 6000 | 285.31 | 1711860 | 81.76% | 1399659.13 | 18.24% | 312200.87 | 100.00% | 1711860 | 4905.75 | 1094.25 | 6000
3.4 | Staircase Construction | m3 | 1000 | 272.55 | 272550 | 93.48% | 254790.27 | 6.00% | 16360.78 | 99.49% | 271151.05 | 934.84 | 60.03 | 994.87
3.5 | Lift Core Construction | m3 | 1000 | 210.94 | 210940 | 88.57% | 186828.2 | 5.08% | 10719.77 | 93.65% | 197547.97 | 885.69 | 50.82 | 936.51
3.6 | Roof Slab and Parapets | m3 | 360 | 257.74 | 92786.4 | 62.39% | 57892.99 | 8.33% | 7730.47 | 70.73% | 65623.46 | 224.62 | 29.99 | 254.61
4 | Masonry and Partitioning | LS | LS | - | 13785838.56 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 161.09 | 5638150 | 89.42% | 5041415.63 | 6.24% | 351577.79 | 95.65% | 5392993.42 | 31295.65 | 2182.49 | 33478.14
4.2 | Internal Blockwork | m2 | 35000 | 240.47 | 8416450 | 48.78% | 4105825.2 | 30.18% | 2539971.82 | 78.96% | 6645797.02 | 17074.17 | 10562.53 | 27636.7
4.3 | Drywall Partitioning | m3 | 1000 | 252.45 | 252450 | 90.49% | 228444.49 | 7.38% | 18633.94 | 97.87% | 247078.43 | 904.91 | 73.81 | 978.72
5 | MEP Works | LS | LS | - | 228899.92 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 50020.19 | 50020.19 | 71.58% | 35803.48 | 11.68% | 5844.79 | 83.26% | 41648.27 | 0.72 | 0.12 | 0.84
5.2 | Plumbing & Drainage | LS | 1 | 53577.16 | 53577.16 | 75.79% | 40606.59 | 5.36% | 2874.37 | 81.16% | 43480.96 | 0.76 | 0.05 | 0.81
5.3 | Firefighting Piping | LS | 1 | 51834.76 | 51834.76 | 52.88% | 27411.03 | 31.79% | 16477.72 | 84.67% | 43888.75 | 0.53 | 0.32 | 0.85
5.4 | HVAC Ducting | No. | 40 | 597.82 | 23912.8 | 60.81% | 14540.28 | 15.66% | 3743.79 | 76.46% | 18284.07 | 24.32 | 6.26 | 30.58
5.5 | Low Current Systems | LS | 1 | 51649.38 | 51649.38 | 56.49% | 29175.01 | 33.53% | 17319.29 | 90.02% | 46494.3 | 0.56 | 0.34 | 0.9
6 | Finishing Works | LS | LS | - | 16248835.64 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 57.19 | 1887270 | 82.88% | 1564090.36 | 8.22% | 155192.41 | 91.10% | 1719282.77 | 27349.02 | 2713.63 | 30062.65
6.2 | Waterproofing | m2 | 5000 | 220.93 | 1104650 | 77.73% | 858668.79 | 5.69% | 62882.44 | 83.42% | 921551.23 | 3886.61 | 284.63 | 4171.24
6.3 | Tiling | m2 | 15000 | 250.32 | 3754800 | 65.86% | 2472937.67 | 33.52% | 1258440.16 | 99.38% | 3731377.83 | 9879.11 | 5027.33 | 14906.44
6.4 | Painting | m2 | 40000 | 87.62 | 3504800 | 62.20% | 2180134.26 | 13.39% | 469245.05 | 75.59% | 2649379.31 | 24881.7 | 5355.46 | 30237.16
6.5 | Ceiling Works | m2 | 18000 | 149.07 | 2683260 | 58.16% | 1560469 | 18.07% | 484793.68 | 76.22% | 2045262.68 | 10468.03 | 3252.12 | 13720.15
6.6 | Joinery Installation | No. | 400 | 880.92 | 352368 | 76.18% | 268442.91 | 8.52% | 30009.81 | 84.70% | 298452.72 | 304.73 | 34.07 | 338.8
6.7 | Door & Window Installation | No. | 800 | 1495.98 | 1196784 | 60.42% | 723128.11 | 24.58% | 294168.95 | 85.00% | 1017297.06 | 483.38 | 196.64 | 680.02
6.8 | Glazing | m2 | 12000 | 78.24 | 938880 | 80.64% | 757146.81 | 11.46% | 107606.33 | 92.10% | 864753.14 | 9677.23 | 1375.34 | 11052.57
7 | External Works & Landscaping | LS | LS | - | 3487519.41 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 807.88 | 80788 | 59.98% | 48458.74 | 31.24% | 25238.29 | 91.22% | 73697.03 | 59.98 | 31.24 | 91.22
7.2 | Roadworks and Paving | m2 | 8000 | 215.24 | 1721920 | 55.75% | 960025.92 | 22.80% | 392545.71 | 78.55% | 1352571.63 | 4460.26 | 1823.76 | 6284.02
7.3 | Kerbstone and Interlock | m2 | 7000 | 119.81 | 838670 | 60.08% | 503874.53 | 22.23% | 186409.85 | 82.31% | 690284.38 | 4205.61 | 1555.88 | 5761.49
7.4 | Landscaping | m3 | 1000 | 400.96 | 400960 | 58.83% | 235880.68 | 31.02% | 124364.6 | 89.85% | 360245.28 | 588.29 | 310.17 | 898.46
7.5 | Boundary Wall | m3 | 1000 | 262.67 | 262670 | 69.44% | 182409.05 | 13.91% | 36530.88 | 83.35% | 218939.93 | 694.44 | 139.08 | 833.52
8 | Final Works | LS | LS | - | 529074.24 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 219999.1 | 219999.1 | 49.31% | 108486.26 | 26.36% | 57993.24 | 75.67% | 166479.5 | 0.49 | 0.26 | 0.75
8.2 | Snagging & De-snagging | LS | 1 | 108207.31 | 108207.31 | 79.69% | 86231.82 | 6.99% | 7567.23 | 86.68% | 93799.05 | 0.8 | 0.07 | 0.87
8.3 | Cleaning | LS | 1 | 107142.72 | 107142.72 | 68.07% | 72927.62 | 29.14% | 31221.76 | 97.21% | 104149.38 | 0.68 | 0.29 | 0.97
8.4 | Handover | LS | 1 | 144936.4 | 144936.4 | 64.35% | 93270.52 | 28.71% | 41608.49 | 93.06% | 134879.01 | 0.64 | 0.29 | 0.93

## IPC_Jul_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 867110.55 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50766.59 | 50766.59 | 84.63% | 42963.28 | 9.57% | 4855.85 | 94.19% | 47819.13 | 0.85 | 0.1 | 0.95
1.2 | Site Fencing and Hoarding | LS | 1 | 46915.89 | 46915.89 | 86.91% | 40776.85 | 13.09% | 6139.04 | 100.00% | 46915.89 | 0.87 | 0.13 | 1
1.3 | Temporary Facilities Setup | LS | 1 | 380183.47 | 380183.47 | 91.70% | 348636.02 | 8.30% | 31547.45 | 100.00% | 380183.47 | 0.92 | 0.08 | 1
1.4 | Soil Testing and Survey | LS | 1 | 196988.85 | 196988.85 | 72.88% | 143560 | 27.12% | 53428.85 | 100.00% | 196988.85 | 0.73 | 0.27 | 1
1.5 | Excavation | LS | 1 | 45162.05 | 45162.05 | 72.26% | 32636.09 | 27.74% | 12525.96 | 100.00% | 45162.05 | 0.72 | 0.28 | 1
1.6 | Dewatering | LS | 1 | 50650.88 | 50650.88 | 88.90% | 45028.05 | 11.10% | 5622.83 | 100.00% | 50650.88 | 0.89 | 0.11 | 1
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4554308.79 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 336.27 | 1681350 | 65.27% | 1097370.98 | 19.91% | 334719.72 | 85.18% | 1432090.7 | 3263.36 | 995.39 | 4258.75
2.2 | Raft Foundation | m3 | 3500 | 267.12 | 934920 | 87.59% | 818892.31 | 6.82% | 63738.59 | 94.41% | 882630.9 | 3065.63 | 238.61 | 3304.24
2.3 | Basement Slab and Walls | m3 | 4000 | 381.74 | 1526960 | 91.12% | 1391438.39 | 8.88% | 135521.61 | 100.00% | 1526960 | 3644.99 | 355.01 | 4000
3 | Superstructure | LS | LS | - | 3360778.33 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 387.86 | 186172.8 | 81.84% | 152364.76 | 18.16% | 33808.04 | 100.00% | 186172.8 | 392.83 | 87.17 | 480
3.2 | Vertical Elements | m3 | 3600 | 226.74 | 816264 | 80.65% | 658302.2 | 19.35% | 157961.8 | 100.00% | 816264 | 2903.34 | 696.66 | 3600
3.3 | Floor Slabs | m3 | 6000 | 294.3 | 1765800 | 77.28% | 1364623.52 | 22.72% | 401176.48 | 100.00% | 1765800 | 4636.85 | 1363.15 | 6000
3.4 | Staircase Construction | m3 | 1000 | 265.54 | 265540 | 88.65% | 235397.43 | 11.35% | 30142.57 | 100.00% | 265540 | 886.49 | 113.51 | 1000
3.5 | Lift Core Construction | m3 | 1000 | 223.01 | 223010 | 73.65% | 164251.42 | 26.35% | 58758.58 | 100.00% | 223010 | 736.52 | 263.48 | 1000
3.6 | Roof Slab and Parapets | m3 | 360 | 223.79 | 80564.4 | 68.61% | 55275.35 | 26.76% | 21556.53 | 95.37% | 76831.88 | 247 | 96.32 | 343.32
4 | Masonry and Partitioning | LS | LS | - | 14026161.6 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 182.25 | 6378750 | 73.91% | 4714370.8 | 26.09% | 1664379.2 | 100.00% | 6378750 | 25867.6 | 9132.4 | 35000
4.2 | Internal Blockwork | m2 | 35000 | 254.55 | 8909250 | 66.50% | 5924230.37 | 33.50% | 2985019.63 | 100.00% | 8909250 | 23273.35 | 11726.65 | 35000
4.3 | Drywall Partitioning | m3 | 1000 | 226.78 | 226780 | 89.49% | 202934.47 | 10.51% | 23845.53 | 100.00% | 226780 | 894.85 | 105.15 | 1000
5 | MEP Works | LS | LS | - | 241758.43 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 48756.1 | 48756.1 | 73.95% | 36055.85 | 16.99% | 8284.12 | 90.94% | 44339.97 | 0.74 | 0.17 | 0.91
5.2 | Plumbing & Drainage | LS | 1 | 49309.03 | 49309.03 | 93.44% | 46073.13 | 6.56% | 3235.9 | 100.00% | 49309.03 | 0.93 | 0.07 | 1
5.3 | Firefighting Piping | LS | 1 | 47329.9 | 47329.9 | 76.68% | 36293.84 | 23.32% | 11036.06 | 100.00% | 47329.9 | 0.77 | 0.23 | 1
5.4 | HVAC Ducting | No. | 40 | 637.46 | 25498.4 | 62.31% | 15888.29 | 31.99% | 8155.89 | 94.30% | 24044.18 | 24.92 | 12.79 | 37.71
5.5 | Low Current Systems | LS | 1 | 47121.75 | 47121.75 | 53.88% | 25388.46 | 31.36% | 14775.81 | 85.24% | 40164.27 | 0.54 | 0.31 | 0.85
6 | Finishing Works | LS | LS | - | 16182008.1 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 57.92 | 1911360 | 75.28% | 1438914.16 | 24.72% | 472445.84 | 100.00% | 1911360 | 24843.13 | 8156.87 | 33000
6.2 | Waterproofing | m2 | 5000 | 249.71 | 1248550 | 81.33% | 1015434.79 | 18.67% | 233115.21 | 100.00% | 1248550 | 4066.46 | 933.54 | 5000
6.3 | Tiling | m2 | 15000 | 225.11 | 3376650 | 90.54% | 3057118.14 | 9.46% | 319531.86 | 100.00% | 3376650 | 13580.55 | 1419.45 | 15000
6.4 | Painting | m2 | 40000 | 79.26 | 3170400 | 74.83% | 2372310.04 | 11.07% | 350985.23 | 85.90% | 2723295.27 | 29930.73 | 4428.28 | 34359.01
6.5 | Ceiling Works | m2 | 18000 | 149.88 | 2697840 | 68.14% | 1838386.81 | 31.86% | 859453.19 | 100.00% | 2697840 | 12265.72 | 5734.28 | 18000
6.6 | Joinery Installation | No. | 400 | 795.94 | 318376 | 80.02% | 254777.3 | 14.68% | 46747.37 | 94.71% | 301524.67 | 320.1 | 58.73 | 378.83
6.7 | Door & Window Installation | No. | 800 | 1481.43 | 1185144 | 91.03% | 1078860.06 | 8.97% | 106283.94 | 100.00% | 1185144 | 728.26 | 71.74 | 800
6.8 | Glazing | m2 | 12000 | 81.2 | 974400 | 77.52% | 755376.19 | 10.67% | 104004.76 | 88.20% | 859380.95 | 9302.66 | 1280.85 | 10583.51
7 | External Works & Landscaping | LS | LS | - | 2995832.51 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 792.99 | 79299 | 66.60% | 52810.42 | 27.68% | 21949.71 | 94.28% | 74760.13 | 66.6 | 27.68 | 94.28
7.2 | Roadworks and Paving | m2 | 8000 | 229.09 | 1832720 | 71.79% | 1315711.93 | 28.21% | 517008.07 | 100.00% | 1832720 | 5743.21 | 2256.79 | 8000
7.3 | Kerbstone and Interlock | m2 | 7000 | 103.86 | 727020 | 60.37% | 438918.02 | 27.51% | 200021.5 | 87.88% | 638939.52 | 4226.05 | 1925.88 | 6151.93
7.4 | Landscaping | m3 | 1000 | 364.05 | 364050 | 53.48% | 194688.64 | 34.35% | 125036.35 | 87.82% | 319724.99 | 534.79 | 343.46 | 878.25
7.5 | Boundary Wall | m3 | 1000 | 279.38 | 279380 | 62.57% | 174812.77 | 32.24% | 90060.07 | 94.81% | 264872.84 | 625.72 | 322.36 | 948.08
8 | Final Works | LS | LS | - | 558008.64 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 195506.45 | 195506.45 | 69.63% | 136121.73 | 30.37% | 59384.72 | 100.00% | 195506.45 | 0.7 | 0.3 | 1
8.2 | Snagging & De-snagging | LS | 1 | 109557.26 | 109557.26 | 72.39% | 79303.74 | 27.61% | 30253.52 | 100.00% | 109557.26 | 0.72 | 0.28 | 1
8.3 | Cleaning | LS | 1 | 106350.89 | 106350.89 | 81.56% | 86738.27 | 18.44% | 19612.62 | 100.00% | 106350.89 | 0.82 | 0.18 | 1
8.4 | Handover | LS | 1 | 158462.03 | 158462.03 | 65.29% | 103466.72 | 34.71% | 54995.31 | 100.00% | 158462.03 | 0.65 | 0.35 | 1