## IPC_Jul_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 747360.66 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50312.56 | 50312.56 |  | 0 | 11.89% | 5981 | 11.89% | 5981 | 0 | 0.12 | 0.12
1.2 | Site Fencing and Hoarding | LS | 1 | 52764.23 | 52764.23 |  | 0 | 9.55% | 5037.06 | 9.55% | 5037.06 | 0 | 0.1 | 0.1
1.3 | Temporary Facilities Setup | LS | 1 | 428284.41 | 428284.41 |  | 0 | 18.02% | 77183.46 | 18.02% | 77183.46 | 0 | 0.18 | 0.18
1.4 | Soil Testing and Survey | LS | 1 | 199474.87 | 199474.87 |  | 0 | 16.22% | 32351.78 | 16.22% | 32351.78 | 0 | 0.16 | 0.16
1.5 | Excavation | LS | 1 | 45388.45 | 45388.45 |  | 0 | 28.42% | 12901.26 | 28.42% | 12901.26 | 0 | 0.28 | 0.28
1.6 | Dewatering | LS | 1 | 52685.37 | 52685.37 |  | 0 | 30.78% | 16214.09 | 30.78% | 16214.09 | 0 | 0.31 | 0.31
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4093804.05 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 352.36 | 1761800 |  | 0 | 7.87% | 138733.68 | 7.87% | 138733.68 | 0 | 393.73 | 393.73
2.2 | Raft Foundation | m3 | 3500 | 279.25 | 977375 |  | 0 | 26.41% | 258166.9 | 26.41% | 258166.9 | 0 | 924.5 | 924.5
2.3 | Basement Slab and Walls | m3 | 4000 | 352.96 | 1411840 |  | 0 | 15.73% | 222092.08 | 15.73% | 222092.08 | 0 | 629.23 | 629.23
3 | Superstructure | LS | LS | - | 2983749.82 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 400.24 | 192115.2 |  | 0 | 9.15% | 17584.28 | 9.15% | 17584.28 | 0 | 43.93 | 43.93
3.2 | Vertical Elements | m3 | 3600 | 233.22 | 839592 |  | 0 | 10.16% | 85315.32 | 10.16% | 85315.32 | 0 | 365.81 | 365.81
3.3 | Floor Slabs | m3 | 6000 | 273.08 | 1638480 |  | 0 | 27.71% | 453998.48 | 27.71% | 453998.48 | 0 | 1662.51 | 1662.51
3.4 | Staircase Construction | m3 | 1000 | 277.89 | 277890 |  | 0 | 17.89% | 49722.82 | 17.89% | 49722.82 | 0 | 178.93 | 178.93
3.5 | Lift Core Construction | m3 | 1000 | 193.72 | 193720 |  | 0 | 20.48% | 39664.73 | 20.48% | 39664.73 | 0 | 204.75 | 204.75
3.6 | Roof Slab and Parapets | m3 | 360 | 251.03 | 90370.8 |  | 0 | 33.73% | 30479.7 | 33.73% | 30479.7 | 0 | 121.42 | 121.42
4 | Masonry and Partitioning | LS | LS | - | 15443244.15 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 177.15 | 6200250 |  | 0 | 20.68% | 1281982.15 | 20.68% | 1281982.15 | 0 | 7236.7 | 7236.7
4.2 | Internal Blockwork | m2 | 35000 | 230.2 | 8057000 |  | 0 | 10.33% | 832288.36 | 10.33% | 832288.36 | 0 | 3615.5 | 3615.5
4.3 | Drywall Partitioning | m3 | 1000 | 239.66 | 239660 |  | 0 | 33.84% | 81110.28 | 33.84% | 81110.28 | 0 | 338.44 | 338.44
5 | MEP Works | LS | LS | - | 208872.41 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 52908.58 | 52908.58 |  | 0 | 28.17% | 14902.29 | 28.17% | 14902.29 | 0 | 0.28 | 0.28
5.2 | Plumbing & Drainage | LS | 1 | 51062.52 | 51062.52 |  | 0 | 5.59% | 2854.07 | 5.59% | 2854.07 | 0 | 0.06 | 0.06
5.3 | Firefighting Piping | LS | 1 | 53039.41 | 53039.41 |  | 0 | 23.38% | 12400.86 | 23.38% | 12400.86 | 0 | 0.23 | 0.23
5.4 | HVAC Ducting | No. | 40 | 629.33 | 25173.2 |  | 0 | 22.90% | 5764.65 | 22.90% | 5764.65 | 0 | 9.16 | 9.16
5.5 | Low Current Systems | LS | 1 | 46330.98 | 46330.98 |  | 0 | 16.26% | 7531.85 | 16.26% | 7531.85 | 0 | 0.16 | 0.16
6 | Finishing Works | LS | LS | - | 15128060.2 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 54.9 | 1811700 |  | 0 | 27.16% | 492060.84 | 27.16% | 492060.84 | 0 | 8962.86 | 8962.86
6.2 | Waterproofing | m2 | 5000 | 220.44 | 1102200 |  | 0 | 5.44% | 60014.21 | 5.44% | 60014.21 | 0 | 272.25 | 272.25
6.3 | Tiling | m2 | 15000 | 242.85 | 3642750 |  | 0 | 12.53% | 456462.7 | 12.53% | 456462.7 | 0 | 1879.61 | 1879.61
6.4 | Painting | m2 | 40000 | 77.3 | 3092000 |  | 0 | 31.98% | 988684.23 | 31.98% | 988684.23 | 0 | 12790.22 | 12790.22
6.5 | Ceiling Works | m2 | 18000 | 140.41 | 2527380 |  | 0 | 25.30% | 639410.98 | 25.30% | 639410.98 | 0 | 4553.88 | 4553.88
6.6 | Joinery Installation | No. | 400 | 746.25 | 298500 |  | 0 | 7.99% | 23855.55 | 7.99% | 23855.55 | 0 | 31.97 | 31.97
6.7 | Door & Window Installation | No. | 800 | 1466.38 | 1173104 |  | 0 | 24.25% | 284508.27 | 24.25% | 284508.27 | 0 | 194.02 | 194.02
6.8 | Glazing | m2 | 12000 | 84.17 | 1010040 |  | 0 | 24.04% | 242814.7 | 24.04% | 242814.7 | 0 | 2884.81 | 2884.81
7 | External Works & Landscaping | LS | LS | - | 3453968.91 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 827.02 | 82702 |  | 0 | 17.18% | 14205.2 | 17.18% | 14205.2 | 0 | 17.18 | 17.18
7.2 | Roadworks and Paving | m2 | 8000 | 225.3 | 1802400 |  | 0 | 26.37% | 475257.31 | 26.37% | 475257.31 | 0 | 2109.44 | 2109.44
7.3 | Kerbstone and Interlock | m2 | 7000 | 117.41 | 821870 |  | 0 | 7.20% | 59160.34 | 7.20% | 59160.34 | 0 | 503.88 | 503.88
7.4 | Landscaping | m3 | 1000 | 414.36 | 414360 |  | 0 | 22.60% | 93657.42 | 22.60% | 93657.42 | 0 | 226.03 | 226.03
7.5 | Boundary Wall | m3 | 1000 | 258.99 | 258990 |  | 0 | 33.93% | 87878.17 | 33.93% | 87878.17 | 0 | 339.31 | 339.31
8 | Final Works | LS | LS | - | 592979.49 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 190388.37 | 190388.37 |  | 0 | 14.81% | 28189.74 | 14.81% | 28189.74 | 0 | 0.15 | 0.15
8.2 | Snagging & De-snagging | LS | 1 | 93463.42 | 93463.42 |  | 0 | 14.22% | 13293.17 | 14.22% | 13293.17 | 0 | 0.14 | 0.14
8.3 | Cleaning | LS | 1 | 100092.29 | 100092.29 |  | 0 | 21.20% | 21219.52 | 21.20% | 21219.52 | 0 | 0.21 | 0.21
8.4 | Handover | LS | 1 | 159782.38 | 159782.38 |  | 0 | 29.53% | 47183.05 | 29.53% | 47183.05 | 0 | 0.3 | 0.3

## IPC_Aug_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 818181.44 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 47712.91 | 47712.91 | 28.46% | 13578.37 | 30.29% | 14453.71 | 58.75% | 28032.08 | 0.28 | 0.3 | 0.58
1.2 | Site Fencing and Hoarding | LS | 1 | 50505.98 | 50505.98 | 53.14% | 26839.44 | 22.53% | 11379.86 | 75.67% | 38219.3 | 0.53 | 0.23 | 0.76
1.3 | Temporary Facilities Setup | LS | 1 | 361357.49 | 361357.49 | 46.11% | 166632.56 | 21.78% | 78685.67 | 67.89% | 245318.23 | 0.46 | 0.22 | 0.68
1.4 | Soil Testing and Survey | LS | 1 | 182491.18 | 182491.18 | 51.58% | 94128.07 | 6.46% | 11786.27 | 58.04% | 105914.34 | 0.52 | 0.06 | 0.58
1.5 | Excavation | LS | 1 | 45310.77 | 45310.77 | 18.23% | 8261.85 | 32.81% | 14868.61 | 51.05% | 23130.46 | 0.18 | 0.33 | 0.51
1.6 | Dewatering | LS | 1 | 48951.82 | 48951.82 | 33.06% | 16184.45 | 31.48% | 15411.78 | 64.55% | 31596.23 | 0.33 | 0.31 | 0.64
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4171192.92 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 335.21 | 1676050 | 41.45% | 694732.87 | 18.99% | 318351.42 | 60.44% | 1013084.29 | 2072.53 | 949.71 | 3022.24
2.2 | Raft Foundation | m3 | 3500 | 263.5 | 922250 | 30.88% | 284803.6 | 21.30% | 196482.63 | 52.19% | 481286.23 | 1080.85 | 745.66 | 1826.51
2.3 | Basement Slab and Walls | m3 | 4000 | 355.36 | 1421440 | 47.49% | 674978.97 | 12.20% | 173349.63 | 59.68% | 848328.6 | 1899.42 | 487.81 | 2387.23
3 | Superstructure | LS | LS | - | 3349041.47 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 376.12 | 180537.6 | 46.77% | 84431.16 | 21.96% | 39638.23 | 68.72% | 124069.39 | 224.48 | 105.39 | 329.87
3.2 | Vertical Elements | m3 | 3600 | 213.5 | 768600 | 41.47% | 318773.62 | 18.18% | 139726.4 | 59.65% | 458500.02 | 1493.08 | 654.46 | 2147.54
3.3 | Floor Slabs | m3 | 6000 | 256.74 | 1540440 | 58.37% | 899198.27 | 17.05% | 262706.87 | 75.43% | 1161905.14 | 3502.37 | 1023.24 | 4525.61
3.4 | Staircase Construction | m3 | 1000 | 274.25 | 274250 | 63.18% | 173258.22 | 8.58% | 23521.19 | 71.75% | 196779.41 | 631.75 | 85.77 | 717.52
3.5 | Lift Core Construction | m3 | 1000 | 208.72 | 208720 | 60.94% | 127203.21 | 5.28% | 11027.38 | 66.23% | 138230.59 | 609.44 | 52.83 | 662.27
3.6 | Roof Slab and Parapets | m3 | 360 | 251.19 | 90428.4 | 36.61% | 33108.64 | 24.73% | 22365.93 | 61.35% | 55474.57 | 131.81 | 89.04 | 220.85
4 | Masonry and Partitioning | LS | LS | - | 13688126.46 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 182.22 | 6377700 | 71.01% | 4528605.68 | 6.29% | 401265.63 | 77.30% | 4929871.31 | 24852.41 | 2202.09 | 27054.5
4.2 | Internal Blockwork | m2 | 35000 | 224.12 | 7844200 | 52.66% | 4130693.9 | 8.93% | 700827.07 | 61.59% | 4831520.97 | 18430.72 | 3127.02 | 21557.74
4.3 | Drywall Partitioning | m3 | 1000 | 233.08 | 233080 | 53.81% | 125425.83 | 23.55% | 54894.87 | 77.36% | 180320.7 | 538.12 | 235.52 | 773.64
5 | MEP Works | LS | LS | - | 239873.74 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 48455.61 | 48455.61 | 41.16% | 19944.9 | 16.12% | 7811.82 | 57.28% | 27756.72 | 0.41 | 0.16 | 0.57
5.2 | Plumbing & Drainage | LS | 1 | 54897.46 | 54897.46 | 21.50% | 11801.37 | 32.93% | 18079.6 | 54.43% | 29880.97 | 0.21 | 0.33 | 0.54
5.3 | Firefighting Piping | LS | 1 | 45841.47 | 45841.47 | 50.09% | 22963.91 | 21.13% | 9687.13 | 71.23% | 32651.04 | 0.5 | 0.21 | 0.71
5.4 | HVAC Ducting | No. | 40 | 611.42 | 24456.8 | 63.05% | 15420.24 | 11.03% | 2697.66 | 74.08% | 18117.9 | 25.22 | 4.41 | 29.63
5.5 | Low Current Systems | LS | 1 | 52210.24 | 52210.24 | 39.77% | 20764.34 | 30.17% | 15753.4 | 69.94% | 36517.74 | 0.4 | 0.3 | 0.7
6 | Finishing Works | LS | LS | - | 14249683.94 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 51.89 | 1712370 | 33.50% | 573605.74 | 24.57% | 420772.99 | 58.07% | 994378.73 | 11054.26 | 8108.94 | 19163.2
6.2 | Waterproofing | m2 | 5000 | 233.7 | 1168500 | 47.20% | 551547.42 | 19.94% | 233011.99 | 67.14% | 784559.41 | 2360.07 | 997.06 | 3357.13
6.3 | Tiling | m2 | 15000 | 252.77 | 3791550 | 67.05% | 2542199.85 | 5.96% | 225800.11 | 73.00% | 2767999.96 | 10057.36 | 893.3 | 10950.66
6.4 | Painting | m2 | 40000 | 83.04 | 3321600 | 50.80% | 1687423.7 | 16.63% | 552402.73 | 67.43% | 2239826.43 | 20320.61 | 6652.25 | 26972.86
6.5 | Ceiling Works | m2 | 18000 | 139.43 | 2509740 | 39.09% | 980991.01 | 11.95% | 299935.42 | 51.04% | 1280926.43 | 7035.72 | 2151.15 | 9186.87
6.6 | Joinery Installation | No. | 400 | 838.73 | 335492 | 44.27% | 148524.2 | 7.22% | 24212.17 | 51.49% | 172736.37 | 177.08 | 28.87 | 205.95
6.7 | Door & Window Installation | No. | 800 | 1509.71 | 1207768 | 44.84% | 541561.86 | 15.94% | 192528.59 | 60.78% | 734090.45 | 358.72 | 127.53 | 486.25
6.8 | Glazing | m2 | 12000 | 77.41 | 928920 | 35.44% | 329198.93 | 22.51% | 209111.28 | 57.95% | 538310.21 | 4252.67 | 2701.35 | 6954.02
7 | External Works & Landscaping | LS | LS | - | 3445254.16 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 796.13 | 79613 | 27.32% | 21747.37 | 30.30% | 24121.63 | 57.61% | 45869 | 27.32 | 30.3 | 57.62
7.2 | Roadworks and Paving | m2 | 8000 | 201.88 | 1615040 | 53.39% | 862335.51 | 23.59% | 381053.72 | 76.99% | 1243389.23 | 4271.53 | 1887.53 | 6159.06
7.3 | Kerbstone and Interlock | m2 | 7000 | 111.99 | 783930 | 46.73% | 366330.34 | 7.93% | 62177.17 | 54.66% | 428507.51 | 3271.1 | 555.2 | 3826.3
7.4 | Landscaping | m3 | 1000 | 402.27 | 402270 | 65.90% | 265079.85 | 8.85% | 35609.95 | 74.75% | 300689.8 | 658.96 | 88.52 | 747.48
7.5 | Boundary Wall | m3 | 1000 | 273.78 | 273780 | 49.39% | 135207.81 | 7.35% | 20123.15 | 56.74% | 155330.96 | 493.86 | 73.5 | 567.36
8 | Final Works | LS | LS | - | 578901.59 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 200995.76 | 200995.76 | 32.06% | 64433.23 | 34.15% | 68634.48 | 66.20% | 133067.71 | 0.32 | 0.34 | 0.66
8.2 | Snagging & De-snagging | LS | 1 | 104858.5 | 104858.5 | 27.89% | 29242.47 | 30.83% | 32323.34 | 58.71% | 61565.81 | 0.28 | 0.31 | 0.59
8.3 | Cleaning | LS | 1 | 96496.38 | 96496.38 | 48.20% | 46509.23 | 14.97% | 14440.93 | 63.16% | 60950.16 | 0.48 | 0.15 | 0.63
8.4 | Handover | LS | 1 | 138480.63 | 138480.63 | 51.02% | 70653.18 | 18.44% | 25534.48 | 69.46% | 96187.66 | 0.51 | 0.18 | 0.69

## IPC_Sep_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 860944.13 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 48242.54 | 48242.54 | 67.52% | 32574.86 | 15.07% | 7271.78 | 82.60% | 39846.64 | 0.68 | 0.15 | 0.83
1.2 | Site Fencing and Hoarding | LS | 1 | 52478.25 | 52478.25 | 67.12% | 35222.46 | 15.60% | 8188.27 | 82.72% | 43410.73 | 0.67 | 0.16 | 0.83
1.3 | Temporary Facilities Setup | LS | 1 | 426439.97 | 426439.97 | 70.85% | 302153.77 | 29.15% | 124286.2 | 100.00% | 426439.97 | 0.71 | 0.29 | 1
1.4 | Soil Testing and Survey | LS | 1 | 193595.83 | 193595.83 | 68.60% | 132814.06 | 12.97% | 25107.2 | 81.57% | 157921.26 | 0.69 | 0.13 | 0.82
1.5 | Excavation | LS | 1 | 49347.36 | 49347.36 | 84.87% | 41879.71 | 8.21% | 4052.64 | 93.08% | 45932.35 | 0.85 | 0.08 | 0.93
1.6 | Dewatering | LS | 1 | 45675.72 | 45675.72 | 85.32% | 38971.5 | 14.63% | 6684.59 | 99.96% | 45656.09 | 0.85 | 0.15 | 1
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4583688.18 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 348.04 | 1740200 | 80.38% | 1398859.75 | 5.50% | 95669.04 | 85.88% | 1494528.79 | 4019.25 | 274.88 | 4294.13
2.2 | Raft Foundation | m3 | 3500 | 266.54 | 932890 | 72.26% | 674103.75 | 27.74% | 258786.25 | 100.00% | 932890 | 2529.09 | 970.91 | 3500
2.3 | Basement Slab and Walls | m3 | 4000 | 366.29 | 1465160 | 80.34% | 1177094.27 | 15.21% | 222895.91 | 95.55% | 1399990.18 | 3213.56 | 608.52 | 3822.08
3 | Superstructure | LS | LS | - | 3029863.91 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 425.5 | 204240 | 84.14% | 171839.95 | 15.86% | 32400.05 | 100.00% | 204240 | 403.85 | 76.15 | 480
3.2 | Vertical Elements | m3 | 3600 | 212.96 | 766656 | 94.03% | 720900.56 | 5.97% | 45755.44 | 100.00% | 766656 | 3385.15 | 214.85 | 3600
3.3 | Floor Slabs | m3 | 6000 | 292.97 | 1757820 | 83.37% | 1465488.92 | 14.51% | 254984.61 | 97.88% | 1720473.53 | 5002.18 | 870.34 | 5872.52
3.4 | Staircase Construction | m3 | 1000 | 262.59 | 262590 | 69.11% | 181469.83 | 30.89% | 81120.17 | 100.00% | 262590 | 691.08 | 308.92 | 1000
3.5 | Lift Core Construction | m3 | 1000 | 194.09 | 194090 | 87.10% | 169050.46 | 12.90% | 25039.54 | 100.00% | 194090 | 870.99 | 129.01 | 1000
3.6 | Roof Slab and Parapets | m3 | 360 | 236.97 | 85309.2 | 79.67% | 67966.73 | 20.33% | 17342.47 | 100.00% | 85309.2 | 286.82 | 73.18 | 360
4 | Masonry and Partitioning | LS | LS | - | 14462011.8 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 182.47 | 6386450 | 59.15% | 3777856.28 | 29.47% | 1881816.23 | 88.62% | 5659672.51 | 20703.99 | 10313.02 | 31017.01
4.2 | Internal Blockwork | m2 | 35000 | 214.66 | 7513100 | 84.66% | 6360458.36 | 15.34% | 1152641.64 | 100.00% | 7513100 | 29630.38 | 5369.62 | 35000
4.3 | Drywall Partitioning | m3 | 1000 | 244.57 | 244570 | 77.00% | 188319.94 | 6.45% | 15768.5 | 83.45% | 204088.44 | 770 | 64.47 | 834.47
5 | MEP Works | LS | LS | - | 221824.98 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 47841.28 | 47841.28 | 82.19% | 39319.21 | 12.00% | 5742.94 | 94.19% | 45062.15 | 0.82 | 0.12 | 0.94
5.2 | Plumbing & Drainage | LS | 1 | 48279.64 | 48279.64 | 80.95% | 39081.42 | 12.80% | 6179.29 | 93.75% | 45260.71 | 0.81 | 0.13 | 0.94
5.3 | Firefighting Piping | LS | 1 | 49509.61 | 49509.61 | 53.21% | 26346.3 | 33.39% | 16531.57 | 86.61% | 42877.87 | 0.53 | 0.33 | 0.86
5.4 | HVAC Ducting | No. | 40 | 656.51 | 26260.4 | 80.99% | 21268.55 | 17.10% | 4489.85 | 98.09% | 25758.4 | 32.4 | 6.84 | 39.24
5.5 | Low Current Systems | LS | 1 | 47348.91 | 47348.91 | 74.50% | 35275.7 | 20.01% | 9476.55 | 94.52% | 44752.25 | 0.75 | 0.2 | 0.95
6 | Finishing Works | LS | LS | - | 13961305.36 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 55.91 | 1845030 | 91.17% | 1682119.51 | 8.83% | 162910.49 | 100.00% | 1845030 | 30086.2 | 2913.8 | 33000
6.2 | Waterproofing | m2 | 5000 | 258.23 | 1291150 | 83.62% | 1079659.94 | 16.38% | 211490.06 | 100.00% | 1291150 | 4181 | 819 | 5000
6.3 | Tiling | m2 | 15000 | 216.84 | 3252600 | 68.65% | 2232918.82 | 16.33% | 531003.02 | 84.98% | 2763921.84 | 10297.54 | 2448.82 | 12746.36
6.4 | Painting | m2 | 40000 | 81.47 | 3258800 | 65.15% | 2123020.38 | 33.58% | 1094184.73 | 98.72% | 3217205.11 | 26058.92 | 13430.52 | 39489.44
6.5 | Ceiling Works | m2 | 18000 | 128.82 | 2318760 | 54.62% | 1266408.32 | 29.02% | 672946.59 | 83.64% | 1939354.91 | 9830.84 | 5223.93 | 15054.77
6.6 | Joinery Installation | No. | 400 | 859.24 | 343696 | 86.83% | 298441.63 | 8.39% | 28826.31 | 95.22% | 327267.94 | 347.33 | 33.55 | 380.88
6.7 | Door & Window Installation | No. | 800 | 1432.89 | 1146312 | 85.62% | 981445.6 | 14.38% | 164866.4 | 100.00% | 1146312 | 684.94 | 115.06 | 800
6.8 | Glazing | m2 | 12000 | 80.08 | 960960 | 69.54% | 668208.41 | 21.63% | 207821.47 | 91.16% | 876029.88 | 8344.26 | 2595.17 | 10939.43
7 | External Works & Landscaping | LS | LS | - | 3476443.18 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 848.67 | 84867 | 52.85% | 44855.26 | 30.09% | 25537.77 | 82.95% | 70393.03 | 52.85 | 30.09 | 82.94
7.2 | Roadworks and Paving | m2 | 8000 | 209.97 | 1679760 | 77.29% | 1298324.66 | 6.36% | 106890.51 | 83.66% | 1405215.17 | 6183.38 | 509.08 | 6692.46
7.3 | Kerbstone and Interlock | m2 | 7000 | 116.25 | 813750 | 71.75% | 583903.36 | 28.25% | 229846.64 | 100.00% | 813750 | 5022.82 | 1977.18 | 7000
7.4 | Landscaping | m3 | 1000 | 376.43 | 376430 | 73.19% | 275524.59 | 26.81% | 100905.41 | 100.00% | 376430 | 731.94 | 268.06 | 1000
7.5 | Boundary Wall | m3 | 1000 | 305.05 | 305050 | 57.57% | 175632.19 | 30.99% | 94519.8 | 88.56% | 270151.99 | 575.75 | 309.85 | 885.6
8 | Final Works | LS | LS | - | 502582.17 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 202958.79 | 202958.79 | 67.16% | 136313.39 | 32.00% | 64952.22 | 99.17% | 201265.61 | 0.67 | 0.32 | 0.99
8.2 | Snagging & De-snagging | LS | 1 | 103661.49 | 103661.49 | 68.13% | 70621.22 | 31.87% | 33040.27 | 100.00% | 103661.49 | 0.68 | 0.32 | 1
8.3 | Cleaning | LS | 1 | 98577.74 | 98577.74 | 68.44% | 67463.41 | 13.23% | 13042.19 | 81.67% | 80505.6 | 0.68 | 0.13 | 0.81
8.4 | Handover | LS | 1 | 158683.31 | 158683.31 | 70.65% | 112102.52 | 19.81% | 31442.71 | 90.46% | 143545.23 | 0.71 | 0.2 | 0.91

## IPC_Oct_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 820695.42 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 45761.85 | 45761.85 | 53.56% | 24509.09 | 12.99% | 5942.7 | 66.54% | 30451.79 | 0.54 | 0.13 | 0.67
1.2 | Site Fencing and Hoarding | LS | 1 | 54848.95 | 54848.95 | 61.52% | 33744.09 | 6.23% | 3419.09 | 67.76% | 37163.18 | 0.62 | 0.06 | 0.68
1.3 | Temporary Facilities Setup | LS | 1 | 363650.43 | 363650.43 | 60.09% | 218508.5 | 19.51% | 70966.24 | 79.60% | 289474.74 | 0.6 | 0.2 | 0.8
1.4 | Soil Testing and Survey | LS | 1 | 210699.01 | 210699.01 | 47.49% | 100063.63 | 19.86% | 41851.47 | 67.35% | 141915.1 | 0.47 | 0.2 | 0.67
1.5 | Excavation | LS | 1 | 48918.85 | 48918.85 | 39.85% | 19491.79 | 26.98% | 13197.74 | 66.82% | 32689.53 | 0.4 | 0.27 | 0.67
1.6 | Dewatering | LS | 1 | 46267.77 | 46267.77 | 65.59% | 30348.04 | 27.63% | 12783.17 | 93.22% | 43131.21 | 0.66 | 0.28 | 0.94
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4421738.73 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 350.08 | 1750400 | 57.27% | 1002435.86 | 7.97% | 139566.83 | 65.24% | 1142002.69 | 2863.45 | 398.67 | 3262.12
2.2 | Raft Foundation | m3 | 3500 | 281.84 | 986440 | 76.94% | 758930.36 | 14.30% | 141099.85 | 91.24% | 900030.21 | 2692.77 | 500.64 | 3193.41
2.3 | Basement Slab and Walls | m3 | 4000 | 392.49 | 1569960 | 37.94% | 595592.91 | 29.97% | 470568.18 | 67.91% | 1066161.09 | 1517.47 | 1198.93 | 2716.4
3 | Superstructure | LS | LS | - | 3010843.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 371.2 | 178176 | 62.30% | 111006.65 | 29.66% | 52853.31 | 91.97% | 163859.96 | 299.05 | 142.39 | 441.44
3.2 | Vertical Elements | m3 | 3600 | 237.99 | 856764 | 70.94% | 607753.37 | 5.34% | 45766.55 | 76.28% | 653519.92 | 2553.69 | 192.3 | 2745.99
3.3 | Floor Slabs | m3 | 6000 | 270.14 | 1620840 | 65.01% | 1053686.16 | 26.41% | 428143.27 | 91.42% | 1481829.43 | 3900.52 | 1584.89 | 5485.41
3.4 | Staircase Construction | m3 | 1000 | 301.72 | 301720 | 63.85% | 192639.06 | 9.41% | 28406.12 | 73.26% | 221045.18 | 638.47 | 94.15 | 732.62
3.5 | Lift Core Construction | m3 | 1000 | 221.57 | 221570 | 65.73% | 145640.29 | 7.82% | 17330.81 | 73.55% | 162971.1 | 657.31 | 78.22 | 735.53
3.6 | Roof Slab and Parapets | m3 | 360 | 254.3 | 91548 | 61.50% | 56305.47 | 29.91% | 27379.97 | 91.41% | 83685.44 | 221.41 | 107.67 | 329.08
4 | Masonry and Partitioning | LS | LS | - | 14897267.8 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 167.56 | 5864600 | 39.48% | 2315144.25 | 27.53% | 1614701.96 | 67.01% | 3929846.21 | 13816.81 | 9636.56 | 23453.37
4.2 | Internal Blockwork | m2 | 35000 | 223.37 | 7817950 | 67.05% | 5242147.98 | 20.72% | 1619626.41 | 87.77% | 6861774.39 | 23468.45 | 7250.87 | 30719.32
4.3 | Drywall Partitioning | m3 | 1000 | 223.29 | 223290 | 42.44% | 94755.12 | 21.36% | 47697.97 | 63.80% | 142453.09 | 424.36 | 213.61 | 637.97
5 | MEP Works | LS | LS | - | 227442.86 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 49909.64 | 49909.64 | 58.36% | 29127.17 | 12.35% | 6165.77 | 70.71% | 35292.94 | 0.58 | 0.12 | 0.7
5.2 | Plumbing & Drainage | LS | 1 | 53286.89 | 53286.89 | 46.98% | 25033.76 | 33.11% | 17643.36 | 80.09% | 42677.12 | 0.47 | 0.33 | 0.8
5.3 | Firefighting Piping | LS | 1 | 45926.79 | 45926.79 | 55.26% | 25377.29 | 15.38% | 7062.16 | 70.63% | 32439.45 | 0.55 | 0.15 | 0.7
5.4 | HVAC Ducting | No. | 40 | 573.8 | 22952 | 71.40% | 16388.01 | 7.76% | 1780.88 | 79.16% | 18168.89 | 28.56 | 3.1 | 31.66
5.5 | Low Current Systems | LS | 1 | 49988.29 | 49988.29 | 45.33% | 22660.06 | 30.04% | 15018.63 | 75.38% | 37678.69 | 0.45 | 0.3 | 0.75
6 | Finishing Works | LS | LS | - | 14385640.31 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 59.71 | 1970430 | 54.79% | 1079666.85 | 10.32% | 203262.05 | 65.11% | 1282928.9 | 18081.84 | 3404.15 | 21485.99
6.2 | Waterproofing | m2 | 5000 | 241.05 | 1205250 | 41.92% | 505283.46 | 33.75% | 406753.39 | 75.67% | 912036.85 | 2096.18 | 1687.42 | 3783.6
6.3 | Tiling | m2 | 15000 | 238.75 | 3581250 | 53.68% | 1922378.28 | 29.83% | 1068317 | 83.51% | 2990695.28 | 8051.85 | 4474.63 | 12526.48
6.4 | Painting | m2 | 40000 | 82.27 | 3290800 | 52.01% | 1711458.81 | 19.85% | 653372.85 | 71.86% | 2364831.66 | 20802.95 | 7941.81 | 28744.76
6.5 | Ceiling Works | m2 | 18000 | 127 | 2286000 | 71.56% | 1635865.53 | 7.10% | 162369.79 | 78.66% | 1798235.32 | 12880.83 | 1278.5 | 14159.33
6.6 | Joinery Installation | No. | 400 | 766.2 | 306480 | 86.22% | 264257.73 | 5.59% | 17141.43 | 91.82% | 281399.16 | 344.89 | 22.37 | 367.26
6.7 | Door & Window Installation | No. | 800 | 1294.48 | 1035584 | 52.61% | 544814.73 | 34.81% | 360496.75 | 87.42% | 905311.48 | 420.88 | 278.49 | 699.37
6.8 | Glazing | m2 | 12000 | 84.47 | 1013640 | 78.36% | 794238.76 | 9.05% | 91759.7 | 87.41% | 885998.46 | 9402.61 | 1086.3 | 10488.91
7 | External Works & Landscaping | LS | LS | - | 3083550.78 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 796.63 | 79663 | 46.72% | 37217.7 | 19.91% | 15863.08 | 66.63% | 53080.78 | 46.72 | 19.91 | 66.63
7.2 | Roadworks and Paving | m2 | 8000 | 195.19 | 1561520 | 53.23% | 831211.61 | 31.59% | 493213.72 | 84.82% | 1324425.33 | 4258.47 | 2526.84 | 6785.31
7.3 | Kerbstone and Interlock | m2 | 7000 | 101.58 | 711060 | 64.43% | 458120.06 | 9.34% | 66446.89 | 73.77% | 524566.95 | 4509.94 | 654.13 | 5164.07
7.4 | Landscaping | m3 | 1000 | 395.19 | 395190 | 61.71% | 243868.09 | 13.65% | 53962.58 | 75.36% | 297830.67 | 617.09 | 136.55 | 753.64
7.5 | Boundary Wall | m3 | 1000 | 300.93 | 300930 | 49.04% | 147587.95 | 17.63% | 53061.9 | 66.68% | 200649.85 | 490.44 | 176.33 | 666.77
8 | Final Works | LS | LS | - | 587592.98 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 181513.43 | 181513.43 | 60.93% | 110602.38 | 22.66% | 41135.29 | 83.60% | 151737.67 | 0.61 | 0.23 | 0.84
8.2 | Snagging & De-snagging | LS | 1 | 94127.98 | 94127.98 | 77.52% | 72971 | 13.46% | 12665.49 | 90.98% | 85636.49 | 0.78 | 0.13 | 0.91
8.3 | Cleaning | LS | 1 | 90677.78 | 90677.78 | 51.08% | 46318.9 | 24.53% | 22244.02 | 75.61% | 68562.92 | 0.51 | 0.25 | 0.76
8.4 | Handover | LS | 1 | 146220.21 | 146220.21 | 64.10% | 93733.96 | 14.32% | 20935.64 | 78.42% | 114669.6 | 0.64 | 0.14 | 0.78