## IPC_Oct_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 759630.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 53070.41 | 53070.41 |  | 0 | 41.48% | 22015.86 | 41.48% | 22015.86 | 0 | 0.41 | 0.41
1.2 | Site Fencing and Hoarding | LS | 1 | 51145.1 | 51145.1 |  | 0 | 22.96% | 11744.31 | 22.96% | 11744.31 | 0 | 0.23 | 0.23
1.3 | Temporary Facilities Setup | LS | 1 | 430597.94 | 430597.94 |  | 0 | 42.55% | 183218.74 | 42.55% | 183218.74 | 0 | 0.43 | 0.43
1.4 | Soil Testing and Survey | LS | 1 | 192472.37 | 192472.37 |  | 0 | 43.23% | 83197.03 | 43.23% | 83197.03 | 0 | 0.43 | 0.43
1.5 | Excavation | LS | 1 | 51488.01 | 51488.01 |  | 0 | 28.98% | 14919.68 | 28.98% | 14919.68 | 0 | 0.29 | 0.29
1.6 | Dewatering | LS | 1 | 47885.6 | 47885.6 |  | 0 | 39.58% | 18954.15 | 39.58% | 18954.15 | 0 | 0.4 | 0.4
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4139925.42 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 320.41 | 1602050 |  | 0 | 26.38% | 422606.32 | 26.38% | 422606.32 | 0 | 1318.95 | 1318.95
2.2 | Raft Foundation | m3 | 3500 | 240.62 | 842170 |  | 0 | 26.29% | 221398.43 | 26.29% | 221398.43 | 0 | 920.12 | 920.12
2.3 | Basement Slab and Walls | m3 | 4000 | 414.06 | 1656240 |  | 0 | 20.61% | 341416.6 | 20.61% | 341416.6 | 0 | 824.56 | 824.56
3 | Superstructure | LS | LS | - | 3364719.34 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 426.28 | 204614.4 |  | 0 | 35.83% | 73311.09 | 35.83% | 73311.09 | 0 | 171.98 | 171.98
3.2 | Vertical Elements | m3 | 3600 | 202.84 | 730224 |  | 0 | 23.90% | 174503 | 23.90% | 174503 | 0 | 860.3 | 860.3
3.3 | Floor Slabs | m3 | 6000 | 256.61 | 1539660 |  | 0 | 35.08% | 540057.54 | 35.08% | 540057.54 | 0 | 2104.58 | 2104.58
3.4 | Staircase Construction | m3 | 1000 | 264.59 | 264590 |  | 0 | 33.19% | 87804.24 | 33.19% | 87804.24 | 0 | 331.85 | 331.85
3.5 | Lift Core Construction | m3 | 1000 | 220.09 | 220090 |  | 0 | 28.22% | 62113.49 | 28.22% | 62113.49 | 0 | 282.22 | 282.22
3.6 | Roof Slab and Parapets | m3 | 360 | 232.28 | 83620.8 |  | 0 | 24.31% | 20328.53 | 24.31% | 20328.53 | 0 | 87.52 | 87.52
4 | Masonry and Partitioning | LS | LS | - | 14197615.78 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 173.85 | 6084750 |  | 0 | 25.66% | 1561559.67 | 25.66% | 1561559.67 | 0 | 8982.22 | 8982.22
4.2 | Internal Blockwork | m2 | 35000 | 225.01 | 7875350 |  | 0 | 25.42% | 2001571.38 | 25.42% | 2001571.38 | 0 | 8895.48 | 8895.48
4.3 | Drywall Partitioning | m3 | 1000 | 256.22 | 256220 |  | 0 | 22.81% | 58440.17 | 22.81% | 58440.17 | 0 | 228.09 | 228.09
5 | MEP Works | LS | LS | - | 225842.81 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 45668.67 | 45668.67 |  | 0 | 36.87% | 16838.07 | 36.87% | 16838.07 | 0 | 0.37 | 0.37
5.2 | Plumbing & Drainage | LS | 1 | 50814.62 | 50814.62 |  | 0 | 27.57% | 14009.11 | 27.57% | 14009.11 | 0 | 0.28 | 0.28
5.3 | Firefighting Piping | LS | 1 | 45400.35 | 45400.35 |  | 0 | 35.90% | 16296.64 | 35.90% | 16296.64 | 0 | 0.36 | 0.36
5.4 | HVAC Ducting | No. | 40 | 610.65 | 24426 |  | 0 | 27.56% | 6731.89 | 27.56% | 6731.89 | 0 | 11.02 | 11.02
5.5 | Low Current Systems | LS | 1 | 46952.32 | 46952.32 |  | 0 | 34.37% | 16135.43 | 34.37% | 16135.43 | 0 | 0.34 | 0.34
6 | Finishing Works | LS | LS | - | 15941328.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 51.17 | 1688610 |  | 0 | 18.96% | 320079.26 | 18.96% | 320079.26 | 0 | 6255.21 | 6255.21
6.2 | Waterproofing | m2 | 5000 | 239.48 | 1197400 |  | 0 | 16.04% | 192032.81 | 16.04% | 192032.81 | 0 | 801.87 | 801.87
6.3 | Tiling | m2 | 15000 | 239.27 | 3589050 |  | 0 | 27.89% | 1000849.93 | 27.89% | 1000849.93 | 0 | 4182.93 | 4182.93
6.4 | Painting | m2 | 40000 | 93.35 | 3734000 |  | 0 | 14.59% | 544766.21 | 14.59% | 544766.21 | 0 | 5835.74 | 5835.74
6.5 | Ceiling Works | m2 | 18000 | 144.53 | 2601540 |  | 0 | 37.80% | 983492.27 | 37.80% | 983492.27 | 0 | 6804.76 | 6804.76
6.6 | Joinery Installation | No. | 400 | 745.49 | 298196 |  | 0 | 21.67% | 64610.55 | 21.67% | 64610.55 | 0 | 86.67 | 86.67
6.7 | Door & Window Installation | No. | 800 | 1411.3 | 1129040 |  | 0 | 25.84% | 291700.12 | 25.84% | 291700.12 | 0 | 206.69 | 206.69
6.8 | Glazing | m2 | 12000 | 82.26 | 987120 |  | 0 | 32.43% | 320082.47 | 32.43% | 320082.47 | 0 | 3891.11 | 3891.11
7 | External Works & Landscaping | LS | LS | - | 2891991.46 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 761.78 | 76178 |  | 0 | 22.80% | 17369.85 | 22.80% | 17369.85 | 0 | 22.8 | 22.8
7.2 | Roadworks and Paving | m2 | 8000 | 207.9 | 1663200 |  | 0 | 16.25% | 270300.55 | 16.25% | 270300.55 | 0 | 1300.15 | 1300.15
7.3 | Kerbstone and Interlock | m2 | 7000 | 110.04 | 770280 |  | 0 | 36.56% | 281586.99 | 36.56% | 281586.99 | 0 | 2558.95 | 2558.95
7.4 | Landscaping | m3 | 1000 | 395.42 | 395420 |  | 0 | 16.22% | 64151.07 | 16.22% | 64151.07 | 0 | 162.24 | 162.24
7.5 | Boundary Wall | m3 | 1000 | 306.69 | 306690 |  | 0 | 22.80% | 69917.3 | 22.80% | 69917.3 | 0 | 227.97 | 227.97
8 | Final Works | LS | LS | - | 519254.68 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 185463.06 | 185463.06 |  | 0 | 22.12% | 41019.88 | 22.12% | 41019.88 | 0 | 0.22 | 0.22
8.2 | Snagging & De-snagging | LS | 1 | 93798.06 | 93798.06 |  | 0 | 33.50% | 31421.95 | 33.50% | 31421.95 | 0 | 0.33 | 0.33
8.3 | Cleaning | LS | 1 | 106707.26 | 106707.26 |  | 0 | 16.71% | 17835.55 | 16.71% | 17835.55 | 0 | 0.17 | 0.17
8.4 | Handover | LS | 1 | 161978.17 | 161978.17 |  | 0 | 42.70% | 69157.93 | 42.70% | 69157.93 | 0 | 0.43 | 0.43

## IPC_Nov_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 747142.66 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 45507.67 | 45507.67 | 43.67% | 19874.59 | 10.23% | 4657.62 | 53.91% | 24532.21 | 0.44 | 0.1 | 0.54
1.2 | Site Fencing and Hoarding | LS | 1 | 47273.56 | 47273.56 | 60.84% | 28761.95 | 7.32% | 3459.33 | 68.16% | 32221.28 | 0.61 | 0.07 | 0.68
1.3 | Temporary Facilities Setup | LS | 1 | 418232.25 | 418232.25 | 34.51% | 144326.12 | 8.42% | 35225.88 | 42.93% | 179552 | 0.35 | 0.08 | 0.43
1.4 | Soil Testing and Survey | LS | 1 | 186701.85 | 186701.85 | 32.64% | 60934.13 | 26.79% | 50014.26 | 59.43% | 110948.39 | 0.33 | 0.27 | 0.6
1.5 | Excavation | LS | 1 | 47389.97 | 47389.97 | 19.39% | 9188.39 | 29.24% | 13858.75 | 48.63% | 23047.14 | 0.19 | 0.29 | 0.48
1.6 | Dewatering | LS | 1 | 49522.56 | 49522.56 | 36.63% | 18140.66 | 26.19% | 12968.91 | 62.82% | 31109.57 | 0.37 | 0.26 | 0.63
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3805987.4 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 370.16 | 1850800 | 13.95% | 258211.18 | 34.47% | 638038.71 | 48.42% | 896249.89 | 697.57 | 1723.68 | 2421.25
2.2 | Raft Foundation | m3 | 3500 | 251.88 | 881580 | 33.83% | 298219.3 | 14.48% | 127647.05 | 48.31% | 425866.35 | 1183.97 | 506.78 | 1690.75
2.3 | Basement Slab and Walls | m3 | 4000 | 357.81 | 1431240 | 39.75% | 568952.57 | 24.31% | 347999.25 | 64.07% | 916951.82 | 1590.1 | 972.58 | 2562.68
3 | Superstructure | LS | LS | - | 3559516.34 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 396.57 | 190353.6 | 18.05% | 34362.2 | 28.32% | 53912.3 | 46.37% | 88274.5 | 86.65 | 135.95 | 222.6
3.2 | Vertical Elements | m3 | 3600 | 220.93 | 795348 | 8.97% | 71365.25 | 33.12% | 263410.38 | 42.09% | 334775.63 | 323.02 | 1192.28 | 1515.3
3.3 | Floor Slabs | m3 | 6000 | 304.07 | 1824420 | 47.69% | 870107.58 | 9.01% | 164341.59 | 56.70% | 1034449.17 | 2861.54 | 540.47 | 3402.01
3.4 | Staircase Construction | m3 | 1000 | 306.27 | 306270 | 23.43% | 71746.86 | 30.22% | 92569.21 | 53.65% | 164316.07 | 234.26 | 302.25 | 536.51
3.5 | Lift Core Construction | m3 | 1000 | 209.21 | 209210 | 46.90% | 98124.59 | 9.97% | 20864.97 | 56.88% | 118989.56 | 469.02 | 99.73 | 568.75
3.6 | Roof Slab and Parapets | m3 | 360 | 241.33 | 86878.8 | 12.63% | 10970.64 | 31.14% | 27053.65 | 43.77% | 38024.29 | 45.46 | 112.1 | 157.56
4 | Masonry and Partitioning | LS | LS | - | 14149020.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 159.77 | 5591950 | 21.08% | 1178856.01 | 27.24% | 1523330.75 | 48.32% | 2702186.76 | 7378.46 | 9534.52 | 16912.98
4.2 | Internal Blockwork | m2 | 35000 | 210.2 | 7357000 | 35.22% | 2591057.06 | 32.71% | 2406396.57 | 67.93% | 4997453.63 | 12326.63 | 11448.13 | 23774.76
4.3 | Drywall Partitioning | m3 | 1000 | 252.07 | 252070 | 46.54% | 117309.47 | 16.29% | 41073.2 | 62.83% | 158382.67 | 465.38 | 162.94 | 628.32
5 | MEP Works | LS | LS | - | 234685.53 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 52289.43 | 52289.43 | 29.75% | 15557.84 | 19.80% | 10350.85 | 49.55% | 25908.69 | 0.3 | 0.2 | 0.5
5.2 | Plumbing & Drainage | LS | 1 | 54661.51 | 54661.51 | 26.68% | 14583.98 | 28.48% | 15566.84 | 55.16% | 30150.82 | 0.27 | 0.28 | 0.55
5.3 | Firefighting Piping | LS | 1 | 52495.27 | 52495.27 | 36.18% | 18993.77 | 33.43% | 17549.36 | 69.61% | 36543.13 | 0.36 | 0.33 | 0.69
5.4 | HVAC Ducting | No. | 40 | 604.89 | 24195.6 | 20.86% | 5046.33 | 34.28% | 8294.95 | 55.14% | 13341.28 | 8.34 | 13.71 | 22.05
5.5 | Low Current Systems | LS | 1 | 48266.38 | 48266.38 | 35.59% | 17178.06 | 33.86% | 16344.83 | 69.45% | 33522.89 | 0.36 | 0.34 | 0.7
6 | Finishing Works | LS | LS | - | 15231015.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 52.46 | 1731180 | 51.25% | 887273.03 | 10.26% | 177600.51 | 61.51% | 1064873.54 | 16913.32 | 3385.45 | 20298.77
6.2 | Waterproofing | m2 | 5000 | 246.86 | 1234300 | 41.93% | 517583.54 | 17.76% | 219172.92 | 59.69% | 736756.46 | 2096.67 | 887.84 | 2984.51
6.3 | Tiling | m2 | 15000 | 248.99 | 3734850 | 33.33% | 1244875.98 | 22.51% | 840683.7 | 55.84% | 2085559.68 | 4999.7 | 3376.38 | 8376.08
6.4 | Painting | m2 | 40000 | 82.59 | 3303600 | 26.29% | 868421.04 | 26.30% | 868976.11 | 52.59% | 1737397.15 | 10514.84 | 10521.57 | 21036.41
6.5 | Ceiling Works | m2 | 18000 | 148.73 | 2677140 | 38.66% | 1035044.36 | 22.19% | 594135.48 | 60.86% | 1629179.84 | 6959.22 | 3994.73 | 10953.95
6.6 | Joinery Installation | No. | 400 | 782.26 | 312904 | 46.18% | 144514.68 | 18.02% | 56370.42 | 64.20% | 200885.1 | 184.74 | 72.06 | 256.8
6.7 | Door & Window Installation | No. | 800 | 1458.67 | 1166936 | 35.62% | 415678 | 15.61% | 182141.59 | 51.23% | 597819.59 | 284.97 | 124.87 | 409.84
6.8 | Glazing | m2 | 12000 | 71.35 | 856200 | 29.03% | 248525.58 | 28.91% | 247556.09 | 57.94% | 496081.67 | 3483.19 | 3469.6 | 6952.79
7 | External Works & Landscaping | LS | LS | - | 3505671.78 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 856.87 | 85687 | 31.10% | 26652.55 | 33.75% | 28919.33 | 64.85% | 55571.88 | 31.1 | 33.75 | 64.85
7.2 | Roadworks and Paving | m2 | 8000 | 221.97 | 1775760 | 19.02% | 337666.88 | 29.63% | 526225.47 | 48.65% | 863892.35 | 1521.23 | 2370.71 | 3891.94
7.3 | Kerbstone and Interlock | m2 | 7000 | 120.07 | 840490 | 19.03% | 159936.6 | 27.50% | 231120.68 | 46.53% | 391057.28 | 1332.03 | 1924.88 | 3256.91
7.4 | Landscaping | m3 | 1000 | 415.97 | 415970 | 32.03% | 133216.41 | 17.19% | 71515.49 | 49.22% | 204731.9 | 320.25 | 171.92 | 492.17
7.5 | Boundary Wall | m3 | 1000 | 280.05 | 280050 | 39.31% | 110095.02 | 30.10% | 84287 | 69.41% | 194382.02 | 393.13 | 300.97 | 694.1
8 | Final Works | LS | LS | - | 520258.51 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 205636.72 | 205636.72 | 47.17% | 97004.81 | 13.67% | 28112.24 | 60.84% | 125117.05 | 0.47 | 0.14 | 0.61
8.2 | Snagging & De-snagging | LS | 1 | 104854.3 | 104854.3 | 43.09% | 45180.53 | 9.66% | 10134.04 | 52.75% | 55314.57 | 0.43 | 0.1 | 0.53
8.3 | Cleaning | LS | 1 | 97148.63 | 97148.63 | 34.94% | 33943.45 | 32.18% | 31265.64 | 67.12% | 65209.09 | 0.35 | 0.32 | 0.67
8.4 | Handover | LS | 1 | 141534.42 | 141534.42 | 19.13% | 27073.01 | 34.02% | 48144.37 | 53.14% | 75217.38 | 0.19 | 0.34 | 0.53

## IPC_Dec_2026
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 755758.37 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 51766.27 | 51766.27 | 25.89% | 13401 | 28.95% | 14988.28 | 54.84% | 28389.28 | 0.26 | 0.29 | 0.55
1.2 | Site Fencing and Hoarding | LS | 1 | 46468.2 | 46468.2 | 49.12% | 22824.48 | 18.34% | 8521.15 | 67.46% | 31345.63 | 0.49 | 0.18 | 0.67
1.3 | Temporary Facilities Setup | LS | 1 | 388135.12 | 388135.12 | 35.02% | 135920.88 | 17.71% | 68751.1 | 52.73% | 204671.98 | 0.35 | 0.18 | 0.53
1.4 | Soil Testing and Survey | LS | 1 | 201909.1 | 201909.1 | 26.88% | 54281.51 | 31.23% | 63049.76 | 58.11% | 117331.27 | 0.27 | 0.31 | 0.58
1.5 | Excavation | LS | 1 | 53276.87 | 53276.87 | 10.65% | 5673.66 | 31.32% | 16685.3 | 41.97% | 22358.96 | 0.11 | 0.31 | 0.42
1.6 | Dewatering | LS | 1 | 50095.42 | 50095.42 | 21.64% | 10838.58 | 33.67% | 16866.94 | 55.31% | 27705.52 | 0.22 | 0.34 | 0.56
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3947741.26 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 381.6 | 1908000 | 52.54% | 1002506.76 | 11.33% | 216082.24 | 63.87% | 1218589 | 2627.11 | 566.25 | 3193.36
2.2 | Raft Foundation | m3 | 3500 | 231.03 | 808605 | 44.49% | 359752.98 | 16.11% | 130266.97 | 60.60% | 490019.95 | 1557.17 | 563.85 | 2121.02
2.3 | Basement Slab and Walls | m3 | 4000 | 371.87 | 1487480 | 20.88% | 310557.06 | 27.29% | 405925.53 | 48.17% | 716482.59 | 835.12 | 1091.58 | 1926.7
3 | Superstructure | LS | LS | - | 3121801.94 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 425.76 | 204364.8 | 36.01% | 73581.68 | 32.96% | 67354.53 | 68.96% | 140936.21 | 172.82 | 158.2 | 331.02
3.2 | Vertical Elements | m3 | 3600 | 228.5 | 822600 | 52.71% | 433589.98 | 12.02% | 98885.03 | 64.73% | 532475.01 | 1897.55 | 432.76 | 2330.31
3.3 | Floor Slabs | m3 | 6000 | 261.84 | 1571040 | 49.18% | 772679.85 | 15.39% | 241726.27 | 64.57% | 1014406.12 | 2950.96 | 923.18 | 3874.14
3.4 | Staircase Construction | m3 | 1000 | 302.59 | 302590 | 45.40% | 137362.93 | 10.81% | 32708.43 | 56.21% | 170071.36 | 453.96 | 108.09 | 562.05
3.5 | Lift Core Construction | m3 | 1000 | 212.85 | 212850 | 37.62% | 80078.7 | 16.50% | 35125.53 | 54.12% | 115204.23 | 376.22 | 165.02 | 541.24
3.6 | Roof Slab and Parapets | m3 | 360 | 242.75 | 87390 | 22.41% | 19585.44 | 18.17% | 15876.65 | 40.58% | 35462.09 | 80.68 | 65.4 | 146.08
4 | Masonry and Partitioning | LS | LS | - | 14552008.13 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 161.99 | 5669650 | 49.12% | 2784880.17 | 20.91% | 1185353.75 | 70.03% | 3970233.92 | 17191.68 | 7317.45 | 24509.13
4.2 | Internal Blockwork | m2 | 35000 | 223.63 | 7827050 | 13.53% | 1059072.81 | 32.42% | 2537445.47 | 45.95% | 3596518.28 | 4735.83 | 11346.62 | 16082.45
4.3 | Drywall Partitioning | m3 | 1000 | 257.44 | 257440 | 38.99% | 100368.01 | 9.18% | 23638.74 | 48.17% | 124006.75 | 389.87 | 91.82 | 481.69
5 | MEP Works | LS | LS | - | 225516.19 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 46344.46 | 46344.46 | 31.42% | 14559.81 | 17.35% | 8039.95 | 48.76% | 22599.76 | 0.31 | 0.17 | 0.48
5.2 | Plumbing & Drainage | LS | 1 | 52551.95 | 52551.95 | 21.63% | 11368.59 | 26.12% | 13728.45 | 47.76% | 25097.04 | 0.22 | 0.26 | 0.48
5.3 | Firefighting Piping | LS | 1 | 50764.2 | 50764.2 | 14.23% | 7224.54 | 32.08% | 16286.79 | 46.31% | 23511.33 | 0.14 | 0.32 | 0.46
5.4 | HVAC Ducting | No. | 40 | 578.67 | 23146.8 | 38.94% | 9012.7 | 17.36% | 4018.69 | 56.30% | 13031.39 | 15.57 | 6.94 | 22.51
5.5 | Low Current Systems | LS | 1 | 47670.35 | 47670.35 | 32.90% | 15682.53 | 29.74% | 14176.82 | 62.64% | 29859.35 | 0.33 | 0.3 | 0.63
6 | Finishing Works | LS | LS | - | 16071667.67 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 59.92 | 1977360 | 12.64% | 249860.65 | 31.58% | 624522.91 | 44.22% | 874383.56 | 4169.9 | 10422.61 | 14592.51
6.2 | Waterproofing | m2 | 5000 | 244.08 | 1220400 | 33.34% | 406863.18 | 24.34% | 297045.54 | 57.68% | 703908.72 | 1666.93 | 1217 | 2883.93
6.3 | Tiling | m2 | 15000 | 251.86 | 3777900 | 44.03% | 1663245.2 | 9.44% | 356577.73 | 53.46% | 2019822.93 | 6603.85 | 1415.78 | 8019.63
6.4 | Painting | m2 | 40000 | 81.63 | 3265200 | 15.42% | 503465.55 | 26.32% | 859393.64 | 41.74% | 1362859.19 | 6167.65 | 10527.91 | 16695.56
6.5 | Ceiling Works | m2 | 18000 | 149.34 | 2688120 | 30.64% | 823581.55 | 20.70% | 556416.15 | 51.34% | 1379997.7 | 5514.81 | 3725.83 | 9240.64
6.6 | Joinery Installation | No. | 400 | 891.89 | 356756 | 21.86% | 77994.4 | 32.41% | 115612.56 | 54.27% | 193606.96 | 87.45 | 129.63 | 217.08
6.7 | Door & Window Installation | No. | 800 | 1557.99 | 1246392 | 41.41% | 516159.08 | 6.20% | 77215.33 | 47.61% | 593374.41 | 331.3 | 49.56 | 380.86
6.8 | Glazing | m2 | 12000 | 79.09 | 949080 | 45.34% | 430317.04 | 23.19% | 220092.69 | 68.53% | 650409.73 | 5440.85 | 2782.81 | 8223.66
7 | External Works & Landscaping | LS | LS | - | 3083697.09 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 869.3 | 86930 | 39.15% | 34032.54 | 28.21% | 24526.72 | 67.36% | 58559.26 | 39.15 | 28.21 | 67.36
7.2 | Roadworks and Paving | m2 | 8000 | 214.86 | 1718880 | 28.27% | 485968.74 | 17.11% | 294156.99 | 45.39% | 780125.73 | 2261.79 | 1369.06 | 3630.85
7.3 | Kerbstone and Interlock | m2 | 7000 | 115.85 | 810950 | 17.26% | 139979.21 | 33.87% | 274697.18 | 51.13% | 414676.39 | 1208.28 | 2371.15 | 3579.43
7.4 | Landscaping | m3 | 1000 | 422.42 | 422420 | 32.85% | 138756 | 22.43% | 94741.23 | 55.28% | 233497.23 | 328.48 | 224.28 | 552.76
7.5 | Boundary Wall | m3 | 1000 | 295.21 | 295210 | 41.41% | 122241.13 | 16.98% | 50139.5 | 58.39% | 172380.63 | 414.08 | 169.84 | 583.92
8 | Final Works | LS | LS | - | 601693.94 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 216442.49 | 216442.49 | 16.31% | 35307.79 | 30.71% | 66478.26 | 47.03% | 101786.05 | 0.16 | 0.31 | 0.47
8.2 | Snagging & De-snagging | LS | 1 | 107818.6 | 107818.6 | 33.96% | 36617.81 | 32.62% | 35168.97 | 66.58% | 71786.78 | 0.34 | 0.33 | 0.67
8.3 | Cleaning | LS | 1 | 93906.13 | 93906.13 | 35.92% | 33734.7 | 33.09% | 31071.82 | 69.01% | 64806.52 | 0.36 | 0.33 | 0.69
8.4 | Handover | LS | 1 | 158181.07 | 158181.07 | 29.75% | 47058.51 | 27.74% | 43874.37 | 57.49% | 90932.88 | 0.3 | 0.28 | 0.58

## IPC_Jan_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 762629.26 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 53819.46 | 53819.46 | 50.44% | 27144.39 | 14.59% | 7850.47 | 65.02% | 34994.86 | 0.5 | 0.15 | 0.65
1.2 | Site Fencing and Hoarding | LS | 1 | 54724.86 | 54724.86 | 52.60% | 28784.11 | 19.91% | 10893.65 | 72.50% | 39677.76 | 0.53 | 0.2 | 0.73
1.3 | Temporary Facilities Setup | LS | 1 | 423202.95 | 423202.95 | 68.70% | 290758.26 | 20.80% | 88008.64 | 89.50% | 378766.9 | 0.69 | 0.21 | 0.9
1.4 | Soil Testing and Survey | LS | 1 | 219411.05 | 219411.05 | 57.84% | 126896.87 | 34.52% | 75730.9 | 92.35% | 202627.77 | 0.58 | 0.35 | 0.93
1.5 | Excavation | LS | 1 | 53196.4 | 53196.4 | 53.00% | 28192.29 | 14.05% | 7474.6 | 67.05% | 35666.89 | 0.53 | 0.14 | 0.67
1.6 | Dewatering | LS | 1 | 51945.1 | 51945.1 | 46.41% | 24109.87 | 25.46% | 13225.86 | 71.88% | 37335.73 | 0.46 | 0.25 | 0.71
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4219115.77 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 352.73 | 1763650 | 60.78% | 1071983.75 | 15.46% | 272701.07 | 76.24% | 1344684.82 | 3039.11 | 773.12 | 3812.23
2.2 | Raft Foundation | m3 | 3500 | 236.63 | 828205 | 76.98% | 637584.46 | 10.68% | 88471.37 | 87.67% | 726055.83 | 2694.44 | 373.88 | 3068.32
2.3 | Basement Slab and Walls | m3 | 4000 | 370.39 | 1481560 | 51.15% | 757772.35 | 30.55% | 452668.47 | 81.70% | 1210440.82 | 2045.88 | 1222.14 | 3268.02
3 | Superstructure | LS | LS | - | 3049073.73 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 405.83 | 194798.4 | 54.02% | 105239.15 | 21.50% | 41874.65 | 75.52% | 147113.8 | 259.32 | 103.18 | 362.5
3.2 | Vertical Elements | m3 | 3600 | 221.12 | 796032 | 71.36% | 568036.43 | 11.97% | 95301.51 | 83.33% | 663337.94 | 2568.91 | 430.99 | 2999.9
3.3 | Floor Slabs | m3 | 6000 | 296.35 | 1778100 | 72.41% | 1287466.6 | 8.23% | 146333.22 | 80.64% | 1433799.82 | 4344.41 | 493.79 | 4838.2
3.4 | Staircase Construction | m3 | 1000 | 267.86 | 267860 | 57.88% | 155048.47 | 8.58% | 22974.65 | 66.46% | 178023.12 | 578.84 | 85.77 | 664.61
3.5 | Lift Core Construction | m3 | 1000 | 193.01 | 193010 | 45.31% | 87460.32 | 30.86% | 59554.79 | 76.17% | 147015.11 | 453.14 | 308.56 | 761.7
3.6 | Roof Slab and Parapets | m3 | 360 | 235.99 | 84956.4 | 39.60% | 33645.4 | 33.46% | 28428.91 | 73.07% | 62074.31 | 142.57 | 120.47 | 263.04
4 | Masonry and Partitioning | LS | LS | - | 15122693.85 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 157.96 | 5528600 | 63.58% | 3514929.77 | 10.21% | 564557 | 73.79% | 4079486.77 | 22252.02 | 3574.05 | 25826.07
4.2 | Internal Blockwork | m2 | 35000 | 249.82 | 8743700 | 79.91% | 6987435.12 | 5.19% | 454016.06 | 85.11% | 7441451.18 | 27969.88 | 1817.37 | 29787.25
4.3 | Drywall Partitioning | m3 | 1000 | 241.65 | 241650 | 48.92% | 118223.52 | 15.27% | 36902.65 | 64.19% | 155126.17 | 489.23 | 152.71 | 641.94
5 | MEP Works | LS | LS | - | 236710.65 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 46676.92 | 46676.92 | 50.51% | 23577.99 | 25.91% | 12095.61 | 76.43% | 35673.6 | 0.51 | 0.26 | 0.77
5.2 | Plumbing & Drainage | LS | 1 | 51240.81 | 51240.81 | 62.43% | 31991 | 25.84% | 13239.43 | 88.27% | 45230.43 | 0.62 | 0.26 | 0.88
5.3 | Firefighting Piping | LS | 1 | 50193.74 | 50193.74 | 57.06% | 28638.16 | 13.81% | 6930.22 | 70.86% | 35568.38 | 0.57 | 0.14 | 0.71
5.4 | HVAC Ducting | No. | 40 | 623.42 | 24936.8 | 64.16% | 15999.08 | 17.15% | 4276.76 | 81.31% | 20275.84 | 25.66 | 6.86 | 32.52
5.5 | Low Current Systems | LS | 1 | 48963.42 | 48963.42 | 42.49% | 20803.62 | 29.55% | 14467.93 | 72.04% | 35271.55 | 0.42 | 0.3 | 0.72
6 | Finishing Works | LS | LS | - | 13611465.1 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 52.57 | 1734810 | 61.76% | 1071397.02 | 28.45% | 493502.53 | 90.21% | 1564899.55 | 20380.39 | 9387.53 | 29767.92
6.2 | Waterproofing | m2 | 5000 | 253.2 | 1266000 | 71.88% | 910025.83 | 8.43% | 106699.91 | 80.31% | 1016725.74 | 3594.1 | 421.41 | 4015.51
6.3 | Tiling | m2 | 15000 | 237.08 | 3556200 | 83.63% | 2973873.66 | 9.05% | 321803.97 | 92.67% | 3295677.63 | 12543.76 | 1357.36 | 13901.12
6.4 | Painting | m2 | 40000 | 81.72 | 3268800 | 63.27% | 2068315.46 | 14.91% | 487312.81 | 78.18% | 2555628.27 | 25309.78 | 5963.2 | 31272.98
6.5 | Ceiling Works | m2 | 18000 | 129.4 | 2329200 | 57.86% | 1347764.08 | 27.52% | 641001.97 | 85.38% | 1988766.05 | 10415.49 | 4953.65 | 15369.14
6.6 | Joinery Installation | No. | 400 | 816.12 | 326448 | 55.16% | 180054.79 | 23.22% | 75814.62 | 78.38% | 255869.41 | 220.62 | 92.9 | 313.52
6.7 | Door & Window Installation | No. | 800 | 1528.41 | 1222728 | 41.35% | 505553.65 | 32.67% | 399502.83 | 74.02% | 905056.48 | 330.77 | 261.38 | 592.15
6.8 | Glazing | m2 | 12000 | 83.97 | 1007640 | 46.66% | 470170.79 | 23.70% | 238821.33 | 70.36% | 708992.12 | 5599.27 | 2844.13 | 8443.4
7 | External Works & Landscaping | LS | LS | - | 3046110.99 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 819.32 | 81932 | 40.33% | 33042.82 | 24.38% | 19974.58 | 64.71% | 53017.4 | 40.33 | 24.38 | 64.71
7.2 | Roadworks and Paving | m2 | 8000 | 192.83 | 1542640 | 69.79% | 1076561.08 | 13.84% | 213445.14 | 83.62% | 1290006.22 | 5582.95 | 1106.91 | 6689.86
7.3 | Kerbstone and Interlock | m2 | 7000 | 119.1 | 833700 | 62.86% | 524046.01 | 14.67% | 122336.64 | 77.53% | 646382.65 | 4400.05 | 1027.18 | 5427.23
7.4 | Landscaping | m3 | 1000 | 422.12 | 422120 | 58.73% | 247927.58 | 5.71% | 24110.4 | 64.45% | 272037.98 | 587.34 | 57.12 | 644.46
7.5 | Boundary Wall | m3 | 1000 | 302.79 | 302790 | 32.66% | 98900.46 | 33.32% | 100893.79 | 65.98% | 199794.25 | 326.63 | 333.21 | 659.84
8 | Final Works | LS | LS | - | 532083.27 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 214007.26 | 214007.26 | 61.43% | 131463.58 | 28.52% | 61024.69 | 89.94% | 192488.27 | 0.61 | 0.29 | 0.9
8.2 | Snagging & De-snagging | LS | 1 | 90471.44 | 90471.44 | 50.61% | 45784.92 | 23.03% | 20834.31 | 73.64% | 66619.23 | 0.51 | 0.23 | 0.74
8.3 | Cleaning | LS | 1 | 109344.82 | 109344.82 | 33.83% | 36994.88 | 32.91% | 35982.13 | 66.74% | 72977.01 | 0.34 | 0.33 | 0.67
8.4 | Handover | LS | 1 | 148196.74 | 148196.74 | 70.60% | 104621.9 | 19.80% | 29339.18 | 90.39% | 133961.08 | 0.71 | 0.2 | 0.91