## IPC_Jan_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 819202.12 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 53536.2 | 53536.2 |  | 0 | 26.85% | 14375.65 | 26.85% | 14375.65 | 0 | 0.27 | 0.27
1.2 | Site Fencing and Hoarding | LS | 1 | 46001.19 | 46001.19 |  | 0 | 23.22% | 10680.69 | 23.22% | 10680.69 | 0 | 0.23 | 0.23
1.3 | Temporary Facilities Setup | LS | 1 | 398763.85 | 398763.85 |  | 0 | 15.21% | 60645.4 | 15.21% | 60645.4 | 0 | 0.15 | 0.15
1.4 | Soil Testing and Survey | LS | 1 | 195476.76 | 195476.76 |  | 0 | 22.61% | 44190.32 | 22.61% | 44190.32 | 0 | 0.23 | 0.23
1.5 | Excavation | LS | 1 | 50422.69 | 50422.69 |  | 0 | 29.91% | 15083.31 | 29.91% | 15083.31 | 0 | 0.3 | 0.3
1.6 | Dewatering | LS | 1 | 53867.8 | 53867.8 |  | 0 | 6.81% | 3667.27 | 6.81% | 3667.27 | 0 | 0.07 | 0.07
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4383098.33 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 331.96 | 1659800 |  | 0 | 27.08% | 449482.19 | 27.08% | 449482.19 | 0 | 1354.03 | 1354.03
2.2 | Raft Foundation | m3 | 3500 | 259.25 | 907375 |  | 0 | 18.38% | 166818.51 | 18.38% | 166818.51 | 0 | 643.47 | 643.47
2.3 | Basement Slab and Walls | m3 | 4000 | 402.88 | 1611520 |  | 0 | 19.10% | 307839.51 | 19.10% | 307839.51 | 0 | 764.1 | 764.1
3 | Superstructure | LS | LS | - | 3109173.32 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 359.53 | 172574.4 |  | 0 | 12.65% | 21830.55 | 12.65% | 21830.55 | 0 | 60.72 | 60.72
3.2 | Vertical Elements | m3 | 3600 | 221.74 | 798264 |  | 0 | 32.21% | 257148.77 | 32.21% | 257148.77 | 0 | 1159.69 | 1159.69
3.3 | Floor Slabs | m3 | 6000 | 260.03 | 1560180 |  | 0 | 30.12% | 469923.26 | 30.12% | 469923.26 | 0 | 1807.19 | 1807.19
3.4 | Staircase Construction | m3 | 1000 | 285.28 | 285280 |  | 0 | 22.29% | 63601.11 | 22.29% | 63601.11 | 0 | 222.94 | 222.94
3.5 | Lift Core Construction | m3 | 1000 | 212.59 | 212590 |  | 0 | 15.15% | 32212.18 | 15.15% | 32212.18 | 0 | 151.52 | 151.52
3.6 | Roof Slab and Parapets | m3 | 360 | 261.31 | 94071.6 |  | 0 | 9.55% | 8986.48 | 9.55% | 8986.48 | 0 | 34.39 | 34.39
4 | Masonry and Partitioning | LS | LS | - | 14970763.81 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 180.83 | 6329050 |  | 0 | 24.46% | 1548089.89 | 24.46% | 1548089.89 | 0 | 8561.02 | 8561.02
4.2 | Internal Blockwork | m2 | 35000 | 238.7 | 8354500 |  | 0 | 22.85% | 1908692.12 | 22.85% | 1908692.12 | 0 | 7996.2 | 7996.2
4.3 | Drywall Partitioning | m3 | 1000 | 248 | 248000 |  | 0 | 26.84% | 66562.13 | 26.84% | 66562.13 | 0 | 268.4 | 268.4
5 | MEP Works | LS | LS | - | 229008.87 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 48616.27 | 48616.27 |  | 0 | 16.21% | 7879.92 | 16.21% | 7879.92 | 0 | 0.16 | 0.16
5.2 | Plumbing & Drainage | LS | 1 | 49637.41 | 49637.41 |  | 0 | 26.68% | 13245.39 | 26.68% | 13245.39 | 0 | 0.27 | 0.27
5.3 | Firefighting Piping | LS | 1 | 50522.58 | 50522.58 |  | 0 | 15.91% | 8040.41 | 15.91% | 8040.41 | 0 | 0.16 | 0.16
5.4 | HVAC Ducting | No. | 40 | 635.28 | 25411.2 |  | 0 | 26.77% | 6803.31 | 26.77% | 6803.31 | 0 | 10.71 | 10.71
5.5 | Low Current Systems | LS | 1 | 48725.77 | 48725.77 |  | 0 | 8.88% | 4329.17 | 8.88% | 4329.17 | 0 | 0.09 | 0.09
6 | Finishing Works | LS | LS | - | 13620826.25 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 58.01 | 1914330 |  | 0 | 10.75% | 205848.21 | 10.75% | 205848.21 | 0 | 3548.5 | 3548.5
6.2 | Waterproofing | m2 | 5000 | 239.9 | 1199500 |  | 0 | 17.40% | 208677.92 | 17.40% | 208677.92 | 0 | 869.85 | 869.85
6.3 | Tiling | m2 | 15000 | 256.31 | 3844650 |  | 0 | 33.86% | 1301772.11 | 33.86% | 1301772.11 | 0 | 5078.9 | 5078.9
6.4 | Painting | m2 | 40000 | 85.32 | 3412800 |  | 0 | 31.70% | 1081858.71 | 31.70% | 1081858.71 | 0 | 12680.01 | 12680.01
6.5 | Ceiling Works | m2 | 18000 | 132.06 | 2377080 |  | 0 | 19.07% | 453397.47 | 19.07% | 453397.47 | 0 | 3433.27 | 3433.27
6.6 | Joinery Installation | No. | 400 | 761.26 | 304504 |  | 0 | 8.60% | 26191.59 | 8.60% | 26191.59 | 0 | 34.41 | 34.41
6.7 | Door & Window Installation | No. | 800 | 1466.15 | 1172920 |  | 0 | 27.68% | 324633.17 | 27.68% | 324633.17 | 0 | 221.42 | 221.42
6.8 | Glazing | m2 | 12000 | 72.19 | 866280 |  | 0 | 31.37% | 271736.46 | 31.37% | 271736.46 | 0 | 3764.18 | 3764.18
7 | External Works & Landscaping | LS | LS | - | 3314178.39 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 785.9 | 78590 |  | 0 | 9.68% | 7604.74 | 9.68% | 7604.74 | 0 | 9.68 | 9.68
7.2 | Roadworks and Paving | m2 | 8000 | 194.98 | 1559840 |  | 0 | 32.32% | 504192.32 | 32.32% | 504192.32 | 0 | 2585.87 | 2585.87
7.3 | Kerbstone and Interlock | m2 | 7000 | 112.55 | 787850 |  | 0 | 20.21% | 159243.33 | 20.21% | 159243.33 | 0 | 1414.87 | 1414.87
7.4 | Landscaping | m3 | 1000 | 380.19 | 380190 |  | 0 | 11.00% | 41834.64 | 11.00% | 41834.64 | 0 | 110.04 | 110.04
7.5 | Boundary Wall | m3 | 1000 | 258.23 | 258230 |  | 0 | 21.71% | 56052.04 | 21.71% | 56052.04 | 0 | 217.06 | 217.06
8 | Final Works | LS | LS | - | 517300.73 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 202295.88 | 202295.88 |  | 0 | 15.69% | 31738.69 | 15.69% | 31738.69 | 0 | 0.16 | 0.16
8.2 | Snagging & De-snagging | LS | 1 | 105007.83 | 105007.83 |  | 0 | 24.63% | 25859.33 | 24.63% | 25859.33 | 0 | 0.25 | 0.25
8.3 | Cleaning | LS | 1 | 98150.49 | 98150.49 |  | 0 | 12.58% | 12349.74 | 12.58% | 12349.74 | 0 | 0.13 | 0.13
8.4 | Handover | LS | 1 | 144040.4 | 144040.4 |  | 0 | 21.90% | 31543.7 | 21.90% | 31543.7 | 0 | 0.22 | 0.22

## IPC_Feb_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 728305.56 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 48245.64 | 48245.64 | 25.66% | 12380.21 | 12.62% | 6087.98 | 38.28% | 18468.19 | 0.26 | 0.13 | 0.39
1.2 | Site Fencing and Hoarding | LS | 1 | 45707.08 | 45707.08 | 9.13% | 4175.24 | 27.75% | 12684.68 | 36.89% | 16859.92 | 0.09 | 0.28 | 0.37
1.3 | Temporary Facilities Setup | LS | 1 | 404575.34 | 404575.34 | 21.02% | 85039.86 | 27.40% | 110855.27 | 48.42% | 195895.13 | 0.21 | 0.27 | 0.48
1.4 | Soil Testing and Survey | LS | 1 | 183937.93 | 183937.93 | 1.53% | 2819.15 | 28.82% | 53001.79 | 30.35% | 55820.94 | 0.02 | 0.29 | 0.31
1.5 | Excavation | LS | 1 | 51041.33 | 51041.33 | 30.24% | 15432.42 | 14.01% | 7149.43 | 44.24% | 22581.85 | 0.3 | 0.14 | 0.44
1.6 | Dewatering | LS | 1 | 49113.07 | 49113.07 | 1.23% | 604.41 | 33.04% | 16225.87 | 34.27% | 16830.28 | 0.01 | 0.33 | 0.34
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 3851232.82 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 364.8 | 1824000 |  | 0 | 28.77% | 524835.43 | 28.77% | 524835.43 | 0 | 1438.69 | 1438.69
2.2 | Raft Foundation | m3 | 3500 | 255.55 | 894425 | 23.53% | 210501.95 | 10.37% | 92781.64 | 33.91% | 303283.59 | 823.72 | 363.07 | 1186.79
2.3 | Basement Slab and Walls | m3 | 4000 | 373.08 | 1492320 | 39.17% | 584603.19 | 12.42% | 185330.39 | 51.59% | 769933.58 | 1566.96 | 496.76 | 2063.72
3 | Superstructure | LS | LS | - | 3507951.07 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 384.82 | 184713.6 | 34.71% | 64108.11 | 14.92% | 27567.33 | 49.63% | 91675.44 | 166.59 | 71.64 | 238.23
3.2 | Vertical Elements | m3 | 3600 | 233.55 | 840780 | 22.01% | 185060.09 | 8.29% | 69711.49 | 30.30% | 254771.58 | 792.38 | 298.49 | 1090.87
3.3 | Floor Slabs | m3 | 6000 | 265.21 | 1591260 | 9.93% | 157964.25 | 24.50% | 389907.13 | 34.43% | 547871.38 | 595.62 | 1470.18 | 2065.8
3.4 | Staircase Construction | m3 | 1000 | 299.55 | 299550 | 10.04% | 30083.77 | 29.98% | 89792.98 | 40.02% | 119876.75 | 100.43 | 299.76 | 400.19
3.5 | Lift Core Construction | m3 | 1000 | 222.62 | 222620 | 45.05% | 100283.17 | 12.20% | 27166.9 | 57.25% | 127450.07 | 450.47 | 122.03 | 572.5
3.6 | Roof Slab and Parapets | m3 | 360 | 240.88 | 86716.8 | 29.06% | 25201.25 | 22.04% | 19108.85 | 51.10% | 44310.1 | 104.62 | 79.33 | 183.95
4 | Masonry and Partitioning | LS | LS | - | 13226616.97 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 182.69 | 6394150 | 29.05% | 1857284.94 | 19.28% | 1232952.92 | 48.33% | 3090237.86 | 10166.32 | 6748.88 | 16915.2
4.2 | Internal Blockwork | m2 | 35000 | 233.81 | 8183350 | 21.41% | 1752253.89 | 32.31% | 2643712.25 | 53.72% | 4395966.14 | 7494.35 | 11307.1 | 18801.45
4.3 | Drywall Partitioning | m3 | 1000 | 229.61 | 229610 | 18.38% | 42200.38 | 31.89% | 73220.47 | 50.27% | 115420.85 | 183.79 | 318.89 | 502.68
5 | MEP Works | LS | LS | - | 241626.32 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 53585.63 | 53585.63 | 13.76% | 7372.96 | 16.26% | 8714.19 | 30.02% | 16087.15 | 0.14 | 0.16 | 0.3
5.2 | Plumbing & Drainage | LS | 1 | 49654.16 | 49654.16 | 35.43% | 17590.72 | 12.38% | 6144.99 | 47.80% | 23735.71 | 0.35 | 0.12 | 0.47
5.3 | Firefighting Piping | LS | 1 | 46690.33 | 46690.33 | 8.83% | 4121.06 | 23.69% | 11062.63 | 32.52% | 15183.69 | 0.09 | 0.24 | 0.33
5.4 | HVAC Ducting | No. | 40 | 610.54 | 24421.6 | 23.32% | 5696.19 | 23.13% | 5648.34 | 46.45% | 11344.53 | 9.33 | 9.25 | 18.58
5.5 | Low Current Systems | LS | 1 | 51940.85 | 51940.85 | 48.66% | 25274.88 | 8.60% | 4467.54 | 57.26% | 29742.42 | 0.49 | 0.09 | 0.58
6 | Finishing Works | LS | LS | - | 14006574.82 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 58.57 | 1932810 | 30.52% | 589920.06 | 6.70% | 129471.74 | 37.22% | 719391.8 | 10072.05 | 2210.55 | 12282.6
6.2 | Waterproofing | m2 | 5000 | 242.85 | 1214250 | 21.89% | 265765.44 | 24.53% | 297796.88 | 46.41% | 563562.32 | 1094.36 | 1226.26 | 2320.62
6.3 | Tiling | m2 | 15000 | 235.14 | 3527100 | 19.85% | 700282.5 | 14.05% | 495726.79 | 33.91% | 1196009.29 | 2978.15 | 2108.22 | 5086.37
6.4 | Painting | m2 | 40000 | 78.89 | 3155600 | 7.01% | 221109.24 | 30.37% | 958473.96 | 37.38% | 1179583.2 | 2802.75 | 12149.5 | 14952.25
6.5 | Ceiling Works | m2 | 18000 | 134.94 | 2428920 | 13.31% | 323337.25 | 26.80% | 650945.37 | 40.11% | 974282.62 | 2396.16 | 4823.96 | 7220.12
6.6 | Joinery Installation | No. | 400 | 754.21 | 301684 | 15.75% | 47519.53 | 28.44% | 85803.06 | 44.19% | 133322.59 | 63.01 | 113.77 | 176.78
6.7 | Door & Window Installation | No. | 800 | 1504.37 | 1203496 | 29.60% | 356183.31 | 12.09% | 145498.23 | 41.69% | 501681.54 | 236.77 | 96.72 | 333.49
6.8 | Glazing | m2 | 12000 | 77.58 | 930960 | 18.00% | 167537.51 | 26.60% | 247614.09 | 44.59% | 415151.6 | 2159.55 | 3191.73 | 5351.28
7 | External Works & Landscaping | LS | LS | - | 2972845.87 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 869.09 | 86909 | 0.97% | 844.57 | 34.53% | 30008.8 | 35.50% | 30853.37 | 0.97 | 34.53 | 35.5
7.2 | Roadworks and Paving | m2 | 8000 | 190.9 | 1527200 | 6.72% | 102576.8 | 32.70% | 499346.05 | 39.41% | 601922.85 | 537.33 | 2615.75 | 3153.08
7.3 | Kerbstone and Interlock | m2 | 7000 | 107.66 | 753620 | 40.77% | 307232.94 | 9.41% | 70945.23 | 50.18% | 378178.17 | 2853.73 | 658.97 | 3512.7
7.4 | Landscaping | m3 | 1000 | 370.15 | 370150 | 22.80% | 84383.48 | 6.55% | 24232.85 | 29.34% | 108616.33 | 227.97 | 65.47 | 293.44
7.5 | Boundary Wall | m3 | 1000 | 254.39 | 254390 | 23.54% | 59893.11 | 11.81% | 30044.95 | 35.35% | 89938.06 | 235.44 | 118.11 | 353.55
8 | Final Works | LS | LS | - | 532279.81 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 196020.81 | 196020.81 | 17.18% | 33675.43 | 14.64% | 28699.33 | 31.82% | 62374.76 | 0.17 | 0.15 | 0.32
8.2 | Snagging & De-snagging | LS | 1 | 90963.13 | 90963.13 | 8.57% | 7791.15 | 31.83% | 28950.53 | 40.39% | 36741.68 | 0.09 | 0.32 | 0.41
8.3 | Cleaning | LS | 1 | 106756.77 | 106756.77 | 34.44% | 36761.93 | 14.69% | 15681.03 | 49.12% | 52442.96 | 0.34 | 0.15 | 0.49
8.4 | Handover | LS | 1 | 148079.98 | 148079.98 | 36.80% | 54496.68 | 5.54% | 8200.49 | 42.34% | 62697.17 | 0.37 | 0.06 | 0.43

## IPC_Mar_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 779912.23 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 46003.51 | 46003.51 | 76.53% | 35205.1 | 6.66% | 3063.95 | 83.19% | 38269.05 | 0.77 | 0.07 | 0.84
1.2 | Site Fencing and Hoarding | LS | 1 | 47605.35 | 47605.35 | 41.40% | 19710.23 | 30.05% | 14307.26 | 71.46% | 34017.49 | 0.41 | 0.3 | 0.71
1.3 | Temporary Facilities Setup | LS | 1 | 374567.17 | 374567.17 | 55.38% | 207437.93 | 11.82% | 44264.5 | 67.20% | 251702.43 | 0.55 | 0.12 | 0.67
1.4 | Soil Testing and Survey | LS | 1 | 217342.24 | 217342.24 | 36.33% | 78949.65 | 27.27% | 59278.42 | 63.60% | 138228.07 | 0.36 | 0.27 | 0.63
1.5 | Excavation | LS | 1 | 46057.57 | 46057.57 | 47.47% | 21863.58 | 33.12% | 15255.31 | 80.59% | 37118.89 | 0.47 | 0.33 | 0.8
1.6 | Dewatering | LS | 1 | 49952.69 | 49952.69 | 41.63% | 20795.92 | 25.05% | 12515.12 | 66.69% | 33311.04 | 0.42 | 0.25 | 0.67
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4160486.96 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 356.6 | 1783000 | 60.52% | 1079038.93 | 21.91% | 390712.38 | 82.43% | 1469751.31 | 3025.91 | 1095.66 | 4121.57
2.2 | Raft Foundation | m3 | 3500 | 247.91 | 867685 | 60.56% | 525472.72 | 6.26% | 54276.21 | 66.82% | 579748.93 | 2119.61 | 218.94 | 2338.55
2.3 | Basement Slab and Walls | m3 | 4000 | 388.66 | 1554640 | 50.04% | 777983.36 | 21.57% | 335368.91 | 71.61% | 1113352.27 | 2001.71 | 862.89 | 2864.6
3 | Superstructure | LS | LS | - | 3325590.95 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 424.99 | 203995.2 | 48.02% | 97952.65 | 21.31% | 43462.31 | 69.32% | 141414.96 | 230.48 | 102.27 | 332.75
3.2 | Vertical Elements | m3 | 3600 | 215.62 | 776232 | 41.58% | 322758.13 | 32.53% | 252481.31 | 74.11% | 575239.44 | 1496.88 | 1170.95 | 2667.83
3.3 | Floor Slabs | m3 | 6000 | 261.81 | 1570860 | 27.90% | 438261.2 | 30.41% | 477637.71 | 58.31% | 915898.91 | 1673.97 | 1824.37 | 3498.34
3.4 | Staircase Construction | m3 | 1000 | 260.96 | 260960 | 54.72% | 142786.55 | 7.99% | 20855.93 | 62.71% | 163642.48 | 547.16 | 79.92 | 627.08
3.5 | Lift Core Construction | m3 | 1000 | 189.45 | 189450 | 37.43% | 70904.8 | 24.98% | 47318.89 | 62.40% | 118223.69 | 374.27 | 249.77 | 624.04
3.6 | Roof Slab and Parapets | m3 | 360 | 238.02 | 85687.2 | 41.99% | 35982.51 | 14.62% | 12527.18 | 56.61% | 48509.69 | 151.17 | 52.63 | 203.8
4 | Masonry and Partitioning | LS | LS | - | 14013875.19 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 165.52 | 5793200 | 39.76% | 2303213.15 | 29.19% | 1690994.36 | 68.95% | 3994207.51 | 13915.01 | 10216.25 | 24131.26
4.2 | Internal Blockwork | m2 | 35000 | 247.85 | 8674750 | 42.97% | 3727214.44 | 17.37% | 1506963.69 | 60.34% | 5234178.13 | 15038.19 | 6080.14 | 21118.33
4.3 | Drywall Partitioning | m3 | 1000 | 258.81 | 258810 | 59.34% | 153583.28 | 11.44% | 29596.2 | 70.78% | 183179.48 | 593.42 | 114.35 | 707.77
5 | MEP Works | LS | LS | - | 243082.34 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 51267.19 | 51267.19 | 52.68% | 27007.69 | 17.94% | 9197.7 | 70.62% | 36205.39 | 0.53 | 0.18 | 0.71
5.2 | Plumbing & Drainage | LS | 1 | 52415.02 | 52415.02 | 27.25% | 14285.1 | 28.42% | 14894.7 | 55.67% | 29179.8 | 0.27 | 0.28 | 0.55
5.3 | Firefighting Piping | LS | 1 | 52253.69 | 52253.69 | 61.09% | 31922.14 | 10.33% | 5395.41 | 71.42% | 37317.55 | 0.61 | 0.1 | 0.71
5.4 | HVAC Ducting | No. | 40 | 551.67 | 22066.8 | 72.74% | 16050.49 | 10.72% | 2364.76 | 83.45% | 18415.25 | 29.09 | 4.29 | 33.38
5.5 | Low Current Systems | LS | 1 | 49256.66 | 49256.66 | 60.20% | 29651.1 | 20.61% | 10152.54 | 80.81% | 39803.64 | 0.6 | 0.21 | 0.81
6 | Finishing Works | LS | LS | - | 15745132.37 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 58.72 | 1937760 | 53.05% | 1028064.64 | 9.00% | 174372.49 | 62.05% | 1202437.13 | 17507.91 | 2969.56 | 20477.47
6.2 | Waterproofing | m2 | 5000 | 244.26 | 1221300 | 57.97% | 707975.7 | 10.93% | 133452.6 | 68.90% | 841428.3 | 2898.45 | 546.35 | 3444.8
6.3 | Tiling | m2 | 15000 | 231.72 | 3475800 | 58.55% | 2035032.01 | 8.05% | 279936.36 | 66.60% | 2314968.37 | 8782.29 | 1208.08 | 9990.37
6.4 | Painting | m2 | 40000 | 78.16 | 3126400 | 51.40% | 1607056.01 | 6.12% | 191395.1 | 57.52% | 1798451.11 | 20561.11 | 2448.76 | 23009.87
6.5 | Ceiling Works | m2 | 18000 | 135.16 | 2432880 | 68.11% | 1656913.27 | 9.44% | 229676.03 | 77.55% | 1886589.3 | 12258.9 | 1699.29 | 13958.19
6.6 | Joinery Installation | No. | 400 | 874.44 | 349776 | 53.21% | 186108.49 | 16.07% | 56216.78 | 69.28% | 242325.27 | 212.83 | 64.29 | 277.12
6.7 | Door & Window Installation | No. | 800 | 1525.18 | 1220144 | 33.91% | 413691.61 | 22.87% | 279057.61 | 56.78% | 692749.22 | 271.24 | 182.97 | 454.21
6.8 | Glazing | m2 | 12000 | 76.36 | 916320 | 38.94% | 356830.15 | 30.84% | 282618.87 | 69.78% | 639449.02 | 4673 | 3701.14 | 8374.14
7 | External Works & Landscaping | LS | LS | - | 3378130.52 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 822.9 | 82290 | 56.96% | 46873.68 | 8.69% | 7150.97 | 65.65% | 54024.65 | 56.96 | 8.69 | 65.65
7.2 | Roadworks and Paving | m2 | 8000 | 219.59 | 1756720 | 37.93% | 666363.65 | 18.38% | 322855.76 | 56.31% | 989219.41 | 3034.58 | 1470.27 | 4504.85
7.3 | Kerbstone and Interlock | m2 | 7000 | 109.6 | 767200 | 60.54% | 464432.79 | 5.70% | 43749.34 | 66.24% | 508182.13 | 4237.53 | 399.17 | 4636.7
7.4 | Landscaping | m3 | 1000 | 370.38 | 370380 | 51.72% | 191568.77 | 10.84% | 40148.99 | 62.56% | 231717.76 | 517.22 | 108.4 | 625.62
7.5 | Boundary Wall | m3 | 1000 | 281.66 | 281660 | 29.88% | 84154.26 | 27.84% | 78427.9 | 57.72% | 162582.16 | 298.78 | 278.45 | 577.23
8 | Final Works | LS | LS | - | 517755.42 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 181479.99 | 181479.99 | 45.85% | 83205.07 | 11.53% | 20916.01 | 57.37% | 104121.08 | 0.46 | 0.12 | 0.58
8.2 | Snagging & De-snagging | LS | 1 | 99023.62 | 99023.62 | 57.12% | 56564.24 | 9.70% | 9605.67 | 66.82% | 66169.91 | 0.57 | 0.1 | 0.67
8.3 | Cleaning | LS | 1 | 108852.18 | 108852.18 | 32.73% | 35629.94 | 32.70% | 35595.52 | 65.43% | 71225.46 | 0.33 | 0.33 | 0.66
8.4 | Handover | LS | 1 | 151362.94 | 151362.94 | 32.88% | 49764.21 | 30.44% | 46071.77 | 63.32% | 95835.98 | 0.33 | 0.3 | 0.63

## IPC_Apr_2027
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 783108.73 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 54762.39 | 54762.39 | 70.65% | 38688.48 | 29.35% | 16073.91 | 100.00% | 54762.39 | 0.71 | 0.29 | 1
1.2 | Site Fencing and Hoarding | LS | 1 | 46122.17 | 46122.17 | 94.86% | 43752.93 | 5.14% | 2369.24 | 100.00% | 46122.17 | 0.95 | 0.05 | 1
1.3 | Temporary Facilities Setup | LS | 1 | 426520.04 | 426520.04 | 76.69% | 327092.38 | 20.20% | 86166.56 | 96.89% | 413258.94 | 0.77 | 0.2 | 0.97
1.4 | Soil Testing and Survey | LS | 1 | 199710.84 | 199710.84 | 88.24% | 176218.67 | 6.59% | 13161.67 | 94.83% | 189380.34 | 0.88 | 0.07 | 0.95
1.5 | Excavation | LS | 1 | 45697.51 | 45697.51 | 85.17% | 38918.39 | 14.83% | 6779.12 | 100.00% | 45697.51 | 0.85 | 0.15 | 1
1.6 | Dewatering | LS | 1 | 49641.43 | 49641.43 | 73.97% | 36717.98 | 26.03% | 12923.45 | 100.00% | 49641.43 | 0.74 | 0.26 | 1
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2 | Substructure | LS | LS | - | 4129467.28 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 337.92 | 1689600 | 73.18% | 1236444.87 | 26.82% | 453155.13 | 100.00% | 1689600 | 3658.99 | 1341.01 | 5000
2.2 | Raft Foundation | m3 | 3500 | 274.31 | 960085 | 63.17% | 606478.91 | 30.59% | 293644.52 | 93.75% | 900123.43 | 2210.93 | 1070.48 | 3281.41
2.3 | Basement Slab and Walls | m3 | 4000 | 378.17 | 1512680 | 68.83% | 1041214.65 | 31.17% | 471465.35 | 100.00% | 1512680 | 2753.3 | 1246.7 | 4000
3 | Superstructure | LS | LS | - | 3238405.58 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 376.55 | 180744 | 59.47% | 107482.6 | 34.82% | 62939.19 | 94.29% | 170421.79 | 285.44 | 167.15 | 452.59
3.2 | Vertical Elements | m3 | 3600 | 219.9 | 791640 | 74.23% | 587635.63 | 25.77% | 204004.37 | 100.00% | 791640 | 2672.29 | 927.71 | 3600
3.3 | Floor Slabs | m3 | 6000 | 291.46 | 1748760 | 68.69% | 1201265.46 | 28.81% | 503840.55 | 97.50% | 1705106.01 | 4121.54 | 1728.68 | 5850.22
3.4 | Staircase Construction | m3 | 1000 | 273.08 | 273080 | 80.98% | 221137.62 | 19.02% | 51942.38 | 100.00% | 273080 | 809.79 | 190.21 | 1000
3.5 | Lift Core Construction | m3 | 1000 | 212.92 | 212920 | 81.54% | 173610.6 | 6.40% | 13624.57 | 87.94% | 187235.17 | 815.38 | 63.99 | 879.37
3.6 | Roof Slab and Parapets | m3 | 360 | 254.98 | 91792.8 | 65.61% | 60223.51 | 20.86% | 19144.36 | 86.46% | 79367.87 | 236.19 | 75.08 | 311.27
4 | Masonry and Partitioning | LS | LS | - | 13826957.98 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 174.3 | 6100500 | 82.09% | 5007830.17 | 17.91% | 1092669.83 | 100.00% | 6100500 | 28731.1 | 6268.9 | 35000
4.2 | Internal Blockwork | m2 | 35000 | 225.24 | 7883400 | 78.60% | 6196292.29 | 8.05% | 634606.03 | 86.65% | 6830898.32 | 27509.73 | 2817.47 | 30327.2
4.3 | Drywall Partitioning | m3 | 1000 | 265.86 | 265860 | 68.81% | 182939.49 | 21.29% | 56609.88 | 90.10% | 239549.37 | 688.1 | 212.93 | 901.03
5 | MEP Works | LS | LS | - | 224417.02 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 53284.72 | 53284.72 | 92.92% | 49512.03 | 7.08% | 3772.69 | 100.00% | 53284.72 | 0.93 | 0.07 | 1
5.2 | Plumbing & Drainage | LS | 1 | 51565.17 | 51565.17 | 68.02% | 35072.57 | 22.81% | 11761.11 | 90.82% | 46833.68 | 0.68 | 0.23 | 0.91
5.3 | Firefighting Piping | LS | 1 | 52661.64 | 52661.64 | 84.16% | 44317.97 | 15.70% | 8267.67 | 99.86% | 52585.64 | 0.84 | 0.16 | 1
5.4 | HVAC Ducting | No. | 40 | 589.95 | 23598 | 86.39% | 20387.19 | 5.91% | 1394.72 | 92.30% | 21781.91 | 34.56 | 2.36 | 36.92
5.5 | Low Current Systems | LS | 1 | 48498.92 | 48498.92 | 65.57% | 31802.52 | 25.73% | 12479.95 | 91.31% | 44282.47 | 0.66 | 0.26 | 0.92
6 | Finishing Works | LS | LS | - | 14172563.72 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 58.25 | 1922250 | 91.67% | 1762175.04 | 8.33% | 160074.96 | 100.00% | 1922250 | 30251.93 | 2748.07 | 33000
6.2 | Waterproofing | m2 | 5000 | 262.75 | 1313750 | 87.95% | 1155449.56 | 12.05% | 158300.44 | 100.00% | 1313750 | 4397.52 | 602.48 | 5000
6.3 | Tiling | m2 | 15000 | 260.45 | 3906750 | 61.06% | 2385452.4 | 30.74% | 1200815.64 | 91.80% | 3586268.04 | 9158.96 | 4610.54 | 13769.5
6.4 | Painting | m2 | 40000 | 79.93 | 3197200 | 71.86% | 2297561.03 | 15.01% | 479976.23 | 86.87% | 2777537.26 | 28744.66 | 6004.96 | 34749.62
6.5 | Ceiling Works | m2 | 18000 | 129.39 | 2329020 | 94.80% | 2208007.96 | 5.20% | 121012.04 | 100.00% | 2329020 | 17064.75 | 935.25 | 18000
6.6 | Joinery Installation | No. | 400 | 818.51 | 327404 | 91.00% | 297925.65 | 9.00% | 29478.35 | 100.00% | 327404 | 363.99 | 36.01 | 400
6.7 | Door & Window Installation | No. | 800 | 1296.1 | 1036880 | 88.28% | 915370.5 | 11.72% | 121509.5 | 100.00% | 1036880 | 706.25 | 93.75 | 800
6.8 | Glazing | m2 | 12000 | 71.88 | 862560 | 68.94% | 594625.65 | 29.95% | 258367.85 | 98.89% | 852993.5 | 8272.48 | 3594.43 | 11866.91
7 | External Works & Landscaping | LS | LS | - | 2996370.3 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 859.92 | 85992 | 62.92% | 54103.64 | 25.68% | 22084.24 | 88.60% | 76187.88 | 62.92 | 25.68 | 88.6
7.2 | Roadworks and Paving | m2 | 8000 | 217.15 | 1737200 | 73.34% | 1274044.91 | 26.66% | 463155.09 | 100.00% | 1737200 | 5867.12 | 2132.88 | 8000
7.3 | Kerbstone and Interlock | m2 | 7000 | 101.42 | 709940 | 82.39% | 584906.02 | 17.61% | 125033.98 | 100.00% | 709940 | 5767.17 | 1232.83 | 7000
7.4 | Landscaping | m3 | 1000 | 366.78 | 366780 | 80.31% | 294577.63 | 19.69% | 72202.37 | 100.00% | 366780 | 803.15 | 196.85 | 1000
7.5 | Boundary Wall | m3 | 1000 | 259.32 | 259320 | 84.55% | 219256.37 | 11.23% | 29113.65 | 95.78% | 248370.02 | 845.51 | 112.27 | 957.78
8 | Final Works | LS | LS | - | 551337.98 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 192630.2 | 192630.2 | 86.74% | 167081.67 | 13.26% | 25548.53 | 100.00% | 192630.2 | 0.87 | 0.13 | 1
8.2 | Snagging & De-snagging | LS | 1 | 102541.71 | 102541.71 | 68.83% | 70577.72 | 30.22% | 30988.13 | 99.05% | 101565.85 | 0.69 | 0.3 | 0.99
8.3 | Cleaning | LS | 1 | 91447.88 | 91447.88 | 77.02% | 70436.71 | 18.57% | 16986.36 | 95.60% | 87423.07 | 0.77 | 0.19 | 0.96
8.4 | Handover | LS | 1 | 148134.68 | 148134.68 | 57.43% | 85078.09 | 29.80% | 44150.16 | 87.24% | 129228.25 | 0.57 | 0.3 | 0.87