## IPC_Jan_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 800000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.2 | Site Fencing and Hoarding | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.3 | Temporary Facilities Setup | LS | 1 | 400000 | 400000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.4 | Soil Testing and Survey | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.5 | Excavation | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.6 | Dewatering | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% |  | 0.00% |  | 0.00%
2 | Substructure | LS | LS | - | 4171246.4441 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 347.0935 | 1735467.5271 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.2 | Raft Foundation | m3 | 3500 | 256.5835 | 898042.1254 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.3 | Basement Slab and Walls | m3 | 4000 | 384.4342 | 1537736.7916 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3 | Superstructure | LS | LS | - | 3254131.9438 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 390.2876 | 187338.03 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.2 | Vertical Elements | m3 | 3600 | 219.4401 | 789984.23 |  | 0 |  | 259863.2336 | 32.89% | 259863.2336 | 0 | 1184.2105 | 1184.2105
3.3 | Floor Slabs | m3 | 6000 | 281.9823 | 1691893.7484 |  | 0 |  | 556543.9962 | 32.89% | 556543.9962 | 0 | 1973.6842 | 1973.6842
3.4 | Staircase Construction | m3 | 1000 | 287.784 | 287784.0243 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.5 | Lift Core Construction | m3 | 1000 | 209.924 | 209923.9731 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.6 | Roof Slab and Parapets | m3 | 360 | 242.2443 | 87207.938 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
4 | Masonry and Partitioning | LS | LS | - | 14387707.0906 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 171.1719 | 5991015.1585 |  | 0 |  | 2096853.6034 | 35.00% | 2096853.6034 | 0 | 12249.9901 | 12249.9901
4.2 | Internal Blockwork | m2 | 35000 | 232.8414 | 8149450.2811 |  | 0 |  | 2874259.2866 | 35.27% | 2874259.2866 | 0 | 12344.2774 | 12344.2774
4.3 | Drywall Partitioning | m3 | 1000 | 247.2417 | 247241.651 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5 | MEP Works | LS | LS | - | 224148.8633 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 50000 | 50000 |  | 0 |  | 17917.0718 | 35.83% | 17917.0718 | 0 | 0.35834 | 0.35834
5.2 | Plumbing & Drainage | LS | 1 | 50000 | 50000 |  | 0 |  | 17543.0411 | 35.09% | 17543.0411 | 0 | 0.35086 | 0.35086
5.3 | Firefighting Piping | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.4 | HVAC Ducting | No. | 40 | 603.7216 | 24148.8633 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.5 | Low Current Systems | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6 | Finishing Works | LS | LS | - | 14899239.1353 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 54.742 | 1806485.4943 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.2 | Waterproofing | m2 | 5000 | 243.0888 | 1215444.0622 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.3 | Tiling | m2 | 15000 | 239.1284 | 3586925.4533 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.4 | Painting | m2 | 40000 | 85.1121 | 3404483.944 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.5 | Ceiling Works | m2 | 18000 | 137.6293 | 2477326.7594 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.6 | Joinery Installation | No. | 400 | 813.0631 | 325225.2299 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.7 | Door & Window Installation | No. | 800 | 1419.0867 | 1135269.3527 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.8 | Glazing | m2 | 12000 | 79.0066 | 948078.8396 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7 | External Works & Landscaping | LS | LS | - | 3211869.8309 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 837.0285 | 83702.853 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.2 | Roadworks and Paving | m2 | 8000 | 210.411 | 1683287.7932 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.3 | Kerbstone and Interlock | m2 | 7000 | 111.1702 | 778191.3636 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.4 | Landscaping | m3 | 1000 | 384.321 | 384321.0218 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.5 | Boundary Wall | m3 | 1000 | 282.3668 | 282366.7993 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8 | Final Works | LS | LS | - | 550000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.2 | Snagging & De-snagging | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.3 | Cleaning | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.4 | Handover | LS | 1 | 150000 | 150000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0

## IPC_Feb_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 800000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.2 | Site Fencing and Hoarding | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.3 | Temporary Facilities Setup | LS | 1 | 400000 | 400000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.4 | Soil Testing and Survey | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.5 | Excavation | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.6 | Dewatering | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% |  | 0.00% |  | 0.00%
2 | Substructure | LS | LS | - | 4171246.4441 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 347.0935 | 1735467.5271 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.2 | Raft Foundation | m3 | 3500 | 256.5835 | 898042.1254 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.3 | Basement Slab and Walls | m3 | 4000 | 384.4342 | 1537736.7916 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3 | Superstructure | LS | LS | - | 3254131.9438 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 390.2876 | 187338.03 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.2 | Vertical Elements | m3 | 3600 | 219.4401 | 789984.23 |  | 259863.2336 |  | 249468.7042 | 64.47% | 509331.9378 | 1184.2105 | 1136.8421 | 2321.0526
3.3 | Floor Slabs | m3 | 6000 | 281.9823 | 1691893.7484 |  | 556543.9962 |  | 534282.2363 | 64.47% | 1090826.2325 | 1973.6842 | 1894.7368 | 3868.4211
3.4 | Staircase Construction | m3 | 1000 | 287.784 | 287784.0243 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.5 | Lift Core Construction | m3 | 1000 | 209.924 | 209923.9731 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.6 | Roof Slab and Parapets | m3 | 360 | 242.2443 | 87207.938 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
4 | Masonry and Partitioning | LS | LS | - | 14387707.0906 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 171.1719 | 5991015.1585 |  | 2096853.6034 |  | 2052185.3735 | 69.25% | 4149038.9768 | 12249.9901 | 11989.0346 | 24239.0247
4.2 | Internal Blockwork | m2 | 35000 | 232.8414 | 8149450.2811 |  | 2874259.2866 |  | 2733894.2277 | 68.82% | 5608153.5142 | 12344.2774 | 11741.442 | 24085.7194
4.3 | Drywall Partitioning | m3 | 1000 | 247.2417 | 247241.651 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5 | MEP Works | LS | LS | - | 224148.8633 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 50000 | 50000 |  | 17917.0718 |  | 16414.1094 | 68.66% | 34331.1813 | 0.35834 | 0.32828 | 0.68662
5.2 | Plumbing & Drainage | LS | 1 | 50000 | 50000 |  | 17543.0411 |  | 17073.843 | 69.23% | 34616.8841 | 0.35086 | 0.34148 | 0.69234
5.3 | Firefighting Piping | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.4 | HVAC Ducting | No. | 40 | 603.7216 | 24148.8633 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.5 | Low Current Systems | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6 | Finishing Works | LS | LS | - | 14899239.1353 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 54.742 | 1806485.4943 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.2 | Waterproofing | m2 | 5000 | 243.0888 | 1215444.0622 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.3 | Tiling | m2 | 15000 | 239.1284 | 3586925.4533 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.4 | Painting | m2 | 40000 | 85.1121 | 3404483.944 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.5 | Ceiling Works | m2 | 18000 | 137.6293 | 2477326.7594 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.6 | Joinery Installation | No. | 400 | 813.0631 | 325225.2299 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.7 | Door & Window Installation | No. | 800 | 1419.0867 | 1135269.3527 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.8 | Glazing | m2 | 12000 | 79.0066 | 948078.8396 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7 | External Works & Landscaping | LS | LS | - | 3211869.8309 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 837.0285 | 83702.853 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.2 | Roadworks and Paving | m2 | 8000 | 210.411 | 1683287.7932 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.3 | Kerbstone and Interlock | m2 | 7000 | 111.1702 | 778191.3636 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.4 | Landscaping | m3 | 1000 | 384.321 | 384321.0218 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.5 | Boundary Wall | m3 | 1000 | 282.3668 | 282366.7993 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8 | Final Works | LS | LS | - | 550000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.2 | Snagging & De-snagging | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.3 | Cleaning | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.4 | Handover | LS | 1 | 150000 | 150000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0

## IPC_Mar_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 800000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.2 | Site Fencing and Hoarding | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.3 | Temporary Facilities Setup | LS | 1 | 400000 | 400000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.4 | Soil Testing and Survey | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.5 | Excavation | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.6 | Dewatering | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% |  | 0.00% |  | 0.00%
2 | Substructure | LS | LS | - | 4171246.4441 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 347.0935 | 1735467.5271 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.2 | Raft Foundation | m3 | 3500 | 256.5835 | 898042.1254 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.3 | Basement Slab and Walls | m3 | 4000 | 384.4342 | 1537736.7916 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3 | Superstructure | LS | LS | - | 3254131.9438 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 390.2876 | 187338.03 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.2 | Vertical Elements | m3 | 3600 | 219.4401 | 789984.23 |  | 509331.9378 |  | 270257.7629 | 98.68% | 779589.7007 | 2321.0526 | 1231.5789 | 3552.6316
3.3 | Floor Slabs | m3 | 6000 | 281.9823 | 1691893.7484 |  | 1090826.2325 |  | 578805.756 | 98.68% | 1669631.9885 | 3868.4211 | 2052.6316 | 5921.0526
3.4 | Staircase Construction | m3 | 1000 | 287.784 | 287784.0243 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.5 | Lift Core Construction | m3 | 1000 | 209.924 | 209923.9731 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.6 | Roof Slab and Parapets | m3 | 360 | 242.2443 | 87207.938 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
4 | Masonry and Partitioning | LS | LS | - | 14387707.0906 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 171.1719 | 5991015.1585 |  | 4149038.9768 |  | 1740056.7025 | 98.30% | 5889095.6793 | 24239.0247 | 10165.5534 | 34404.5781
4.2 | Internal Blockwork | m2 | 35000 | 232.8414 | 8149450.2811 |  | 5608153.5142 |  | 2397294.1355 | 98.23% | 8005447.6497 | 24085.7194 | 10295.8226 | 34381.5421
4.3 | Drywall Partitioning | m3 | 1000 | 247.2417 | 247241.651 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5 | MEP Works | LS | LS | - | 224148.8633 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 50000 | 50000 |  | 34331.1813 |  | 14859.7657 | 98.38% | 49190.947 | 0.68662 | 0.2972 | 0.98382
5.2 | Plumbing & Drainage | LS | 1 | 50000 | 50000 |  | 34616.8841 |  | 14575.4314 | 98.38% | 49192.3155 | 0.69234 | 0.29151 | 0.98385
5.3 | Firefighting Piping | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.4 | HVAC Ducting | No. | 40 | 603.7216 | 24148.8633 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.5 | Low Current Systems | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6 | Finishing Works | LS | LS | - | 14899239.1353 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 54.742 | 1806485.4943 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.2 | Waterproofing | m2 | 5000 | 243.0888 | 1215444.0622 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.3 | Tiling | m2 | 15000 | 239.1284 | 3586925.4533 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.4 | Painting | m2 | 40000 | 85.1121 | 3404483.944 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.5 | Ceiling Works | m2 | 18000 | 137.6293 | 2477326.7594 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.6 | Joinery Installation | No. | 400 | 813.0631 | 325225.2299 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.7 | Door & Window Installation | No. | 800 | 1419.0867 | 1135269.3527 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.8 | Glazing | m2 | 12000 | 79.0066 | 948078.8396 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7 | External Works & Landscaping | LS | LS | - | 3211869.8309 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 837.0285 | 83702.853 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.2 | Roadworks and Paving | m2 | 8000 | 210.411 | 1683287.7932 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.3 | Kerbstone and Interlock | m2 | 7000 | 111.1702 | 778191.3636 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.4 | Landscaping | m3 | 1000 | 384.321 | 384321.0218 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.5 | Boundary Wall | m3 | 1000 | 282.3668 | 282366.7993 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8 | Final Works | LS | LS | - | 550000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.2 | Snagging & De-snagging | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.3 | Cleaning | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.4 | Handover | LS | 1 | 150000 | 150000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0

## IPC_Apr_2025
Activity Code | Activity Name | Unit | BOQ Qty | Unit Rate | Total BOQ Amount | Previous % | Previous Amount | Current % | Current Amount | Cumulative % | Cumulative Amount | Previous Qty | Current Qty | Cumulative Qty
1 | Pre-construction & Site Preparation | LS | LS | - | 800000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
1.1 | Site Clearing | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.2 | Site Fencing and Hoarding | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.3 | Temporary Facilities Setup | LS | 1 | 400000 | 400000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.4 | Soil Testing and Survey | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.5 | Excavation | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.6 | Dewatering | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
1.7 | Shoring and Piling | LS | LS | - |  | 0.00% |  | 0.00% |  | 0.00%
2 | Substructure | LS | LS | - | 4171246.4441 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
2.1 | Pile Cap Construction | m | 5000 | 347.0935 | 1735467.5271 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.2 | Raft Foundation | m3 | 3500 | 256.5835 | 898042.1254 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
2.3 | Basement Slab and Walls | m3 | 4000 | 384.4342 | 1537736.7916 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3 | Superstructure | LS | LS | - | 3254131.9438 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
3.1 | Ground Floor Slab | m3 | 480 | 390.2876 | 187338.03 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.2 | Vertical Elements | m3 | 3600 | 219.4401 | 789984.23 |  | 779589.7007 |  | 10394.5293 | 100.00% | 789984.23 | 3552.6316 | 47.3684 | 3600
3.3 | Floor Slabs | m3 | 6000 | 281.9823 | 1691893.7484 |  | 1669631.9885 |  | 22261.7598 | 100.00% | 1691893.7484 | 5921.0526 | 78.9474 | 6000
3.4 | Staircase Construction | m3 | 1000 | 287.784 | 287784.0243 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.5 | Lift Core Construction | m3 | 1000 | 209.924 | 209923.9731 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
3.6 | Roof Slab and Parapets | m3 | 360 | 242.2443 | 87207.938 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
4 | Masonry and Partitioning | LS | LS | - | 14387707.0906 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
4.1 | External Blockwork | m2 | 35000 | 171.1719 | 5991015.1585 |  | 5889095.6793 |  | 101919.4792 | 100.00% | 5991015.1585 | 34404.5781 | 595.4219 | 35000
4.2 | Internal Blockwork | m2 | 35000 | 232.8414 | 8149450.2811 |  | 8005447.6497 |  | 144002.6314 | 100.00% | 8149450.2811 | 34381.5421 | 618.4579 | 35000
4.3 | Drywall Partitioning | m3 | 1000 | 247.2417 | 247241.651 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5 | MEP Works | LS | LS | - | 224148.8633 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
5.1 | Electrical Conduits | LS | 1 | 50000 | 50000 |  | 49190.947 |  | 809.053 | 100.00% | 50000 | 0.98382 | 0.016181 | 1
5.2 | Plumbing & Drainage | LS | 1 | 50000 | 50000 |  | 49192.3155 |  | 807.6845 | 100.00% | 50000 | 0.98385 | 0.016154 | 1
5.3 | Firefighting Piping | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.4 | HVAC Ducting | No. | 40 | 603.7216 | 24148.8633 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
5.5 | Low Current Systems | LS | 1 | 50000 | 50000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6 | Finishing Works | LS | LS | - | 14899239.1353 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
6.1 | Plastering | m2 | 33000 | 54.742 | 1806485.4943 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.2 | Waterproofing | m2 | 5000 | 243.0888 | 1215444.0622 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.3 | Tiling | m2 | 15000 | 239.1284 | 3586925.4533 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.4 | Painting | m2 | 40000 | 85.1121 | 3404483.944 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.5 | Ceiling Works | m2 | 18000 | 137.6293 | 2477326.7594 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.6 | Joinery Installation | No. | 400 | 813.0631 | 325225.2299 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.7 | Door & Window Installation | No. | 800 | 1419.0867 | 1135269.3527 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
6.8 | Glazing | m2 | 12000 | 79.0066 | 948078.8396 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7 | External Works & Landscaping | LS | LS | - | 3211869.8309 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
7.1 | External MEP Connections | No. | 100 | 837.0285 | 83702.853 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.2 | Roadworks and Paving | m2 | 8000 | 210.411 | 1683287.7932 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.3 | Kerbstone and Interlock | m2 | 7000 | 111.1702 | 778191.3636 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.4 | Landscaping | m3 | 1000 | 384.321 | 384321.0218 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
7.5 | Boundary Wall | m3 | 1000 | 282.3668 | 282366.7993 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8 | Final Works | LS | LS | - | 550000 | 0.00% | 0 | 0.00% | 0 | 0.00% | 0
8.1 | Testing & Commissioning | LS | 1 | 200000 | 200000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.2 | Snagging & De-snagging | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.3 | Cleaning | LS | 1 | 100000 | 100000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0
8.4 | Handover | LS | 1 | 150000 | 150000 |  | 0 |  | 0 | 0.00% | 0 | 0 | 0 | 0